## re-estimate (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- बेनडोल सडक नयाँबस्ती | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/07/11
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -White wall | 1 | 3.88 | 0.1 | 2.2859 | 0.88692
|  | 3 | 0.3566 | 0.3566 | 2.2859 | 0.87204 |  |  |  |  | kmnfd] sfd -Rofgn PËn 6L cflb_ x6fpg] sfo{ lemSg], 5'6\ofpg] / /fd¦/L yGsfpg] ;d]t
|  | 1 | 0.6 | 0.6 | 1.15 | 0.414
| Sub-total |  |  |  |  | 2.173 | m3 | 1950 | 4237.2778
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -White wall | 1 | 10.53 | 0.46 | 0.75 | 3.6329
| Sub-total |  |  |  |  | 3.6329 | m3 | 64.63 | 234.7911
| VAT calculation | [7 empty] | 25.298
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at backyard | 1 | 0.6 | 0.6 | 0.9 | 0.324
| Sub-total |  |  |  |  | 0.324 | m3 | 663.31 | 214.9124
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing | 1 | 10.53 | 0.46 |  | 4.8438
|  | 1 | 0.6 | 0.6 |  | 0.36
| Sub-total |  |  |  |  | 5.2038 | sqm | 1014.97 | 5281.7009
| VAT calculation | [7 empty] | 582.9484
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for footing | 1 | 10.53 | 0.46 | 0.05 | 0.24219
|  | 1 | 0.6 | 0.6 | 0.05 | 0.018
| Sub-total |  |  |  |  | 0.26019 | m3 | 12983.1 | 3378.0728
| VAT calculation | [7 empty] | 273.2396
6 | ;'k/ :6«Sr/, 8]s :n]a ljdx?df l;d]G6 s+lqm6 ug]{ sfd -!M!.%M#_
| -for footing | 1 | 0.6 | 0.6 | 0.225 | 0.081
|  | 1 | 0.23 | 0.23 | 2.475 | 0.13093
| -sill/lintel/DPC bands | 2 | 11.48 | 0.23 | 0.075 | 0.39606
|  | 2 | 9.4602 | 0.23 | 0.075 | 0.32638
| Sub-total |  |  |  |  | 0.93436 | m3 | 16512.62 | 15428.8067
| VAT calculation | [7 empty] | 1104.4568
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for footing | 1 | 2.4 |  | 0.225 | 0.54
|  | 1 | 0.92 |  | 2.475 | 2.277
| Sub-total |  |  |  |  | 2.817 | m2 | 915.42 | 2578.7381
| VAT calculation | [7 empty] | 171.4883
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For column footing | 6 | 0.6 | 0.39506 | 1.4222 | 0.0014222
| -For column | 4 | 3.075 | 0.88889 | 10.9333 | 0.010933
| -For column stirrups | 16 | 0.71117 | 0.39506 | 4.4953 | 0.0044953
| -For bands | 4 | 20.4402 | 0.61728 | 50.4696 | 0.05047
| -For stirrups | 135 | 0.27939 | 0.39506 | 14.9006 | 0.014901
| Sub-total |  |  |  |  | 0.082221 | MT | 131940 | 10848.2478
| VAT calculation | [7 empty] | 1135.1441
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | [10 empty] | 37.666
| -wall at backyard | 1 | 11.48 | 0.23 | 0.63487 | 1.6763 |  |  |  |  | 11.6324 | 11.48
|  | 1 | 0.406 | 0.23 | 2.5037 | 0.2338
| -deduction for sill/lintel/DPC bands | -2 | 11.48 | 0.23 | 0.075 | -0.39606
| - at instead white wall | 1 | 9.4602 | 0.23 | 2.35 | 5.1132 | [5 empty] | 2.9749 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -deduction for sill/lintel/DPC bands | -2 | 9.4602 | 0.23 | 0.075 | -0.32638
|  | 3 | 0.3566 | 0.3566 | 2.35 | 0.8965
| -for footing | 1 | 10.53 | 0.46 | 0.2 | 0.96876
| -at back yard window | 12 | 0.83816 | 0.23 | 1.2444 | 2.8788
| Sub-total |  |  |  |  | 11.0449 | m3 | 14362.76 | 158635.8406
| VAT calculation | [7 empty] | 14806.0331
10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 2 | 72.7696 |  | 1.8 | 261.9705
| Sub-total |  |  |  |  | 261.9705 | sqm | 405.86 | 106323.3458
| VAT calculation | [7 empty] | 3802.7794
11 | $=% X @) dL=dL= kmnfd] kftfsf] k¦m]ddf !@ x !@ dL=dL=;f]ln8 sf]/ :Sjfo/ /8sf] lu¦n agfO{ vfS;L nufO{ /]8cS;fO8 tyf cNd'lgod k]G6 ;d]t u/L hf]8\g]
| -window | 6 | 1.1938 |  | 1.6519 | 11.8329
| Sub-total |  |  |  |  | 11.8329 | sqm | 2575.34 | 30473.7725
| VAT calculation | [7 empty] | 3744.7793
12 | lh=cfO{=sf9]tf/ -jf/ j]8 jfo/_ nufpg] .
| -at boundary | 1 | 95.5523 |  |  | 95.5523
| Sub-total |  |  |  |  | 95.5523 | rm | 82.59 | 7891.662
| VAT calculation | [7 empty] | 247.4596
13 | %) dL=dL=Aof;sf] :6]Gn];l:6nsf] x\of08/]ndf @ ld6/sf] b"/Ldf %) dL=dL=Aof;sf] :6]Gn];l:6ns} 7f8f] kf]i6 /fvL x\of08/]n / e"O+sf] aLrdf tLg tx t];f]{ @% dL=dL=Aof;sf] :6]Gn];l:6nsf] d]Da/ /fvL @Ú–^Æ b]lv #Ú–)Æ ;Dd prfO{ ePsf] /]lnË pknAw u/fO{ h8fg u/L /+u ;d]t nufpg] sfd .
| -at boundary | 1 | 7.8735 |  |  | 7.8735
| Sub-total |  |  |  |  | 7.8735 | rm | 4132.8 | 32539.6594
| VAT calculation | [7 empty] | 4230.1557
14 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -wall | 2 | 72.7696 |  | 1.8 | 261.9705
| Sub-total |  |  |  |  | 261.9705 | sqm | 251.77 | 65956.312
| VAT calculation | [7 empty] | 4337.3931
15 | kmnfd] u]6 !^ u]h -%)X%)X% dL=dL=sf] k¦m]d ;lxt_ agfO{ hf]8\g] /]8 cS;fO8 k]lG6Ë / Hofnf ;d]t .
| -at door | 2 | 1.0158 |  | 2.5398 | 5.1601
| Sub-total |  |  |  |  | 5.1601 | sqm | 8306.71 | 42863.0706
| VAT 13% for material | [7 empty] | 5572.1992
16 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
17 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 532419.5853
| Total Estimated | 532419.5853 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 89.2154
| User Contribution | 57419.5853 |  | 10.7846
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on C11: Windows User: white wall
Note on C12: Windows User: column as wall support and including footing area
Note on D60: DELL: column part not included
Note on D61: DELL: For RCC column peripheri and ht =3 ft from GL and 225mm depth footing

## grill item changed (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- बेनडोल सडक नयाँबस्ती | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/07/11
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -White wall | 1 | 3.88 | 0.1 | 2.2859 | 0.88692
|  | 3 | 0.3566 | 0.3566 | 2.2859 | 0.87204 |  |  |  |  | kmnfd] sfd -Rofgn PËn 6L cflb_ x6fpg] sfo{ lemSg], 5'6\ofpg] / /fd¦/L yGsfpg] ;d]t
|  | 1 | 0.6 | 0.6 | 1.15 | 0.414
| Sub-total |  |  |  |  | 2.173 | m3 | 1950 | 4237.2778
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -White wall | 1 | 10.53 | 0.46 | 0.75 | 3.6329
| Sub-total |  |  |  |  | 3.6329 | m3 | 64.63 | 234.7911
| VAT calculation | [7 empty] | 25.298
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at backyard | 1 | 0.6 | 0.6 | 0.9 | 0.324
| Sub-total |  |  |  |  | 0.324 | m3 | 663.31 | 214.9124
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing | 1 | 10.53 | 0.46 |  | 4.8438
|  | 1 | 0.6 | 0.6 |  | 0.36
| Sub-total |  |  |  |  | 5.2038 | sqm | 1014.97 | 5281.7009
| VAT calculation | [7 empty] | 582.9484
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for footing | 1 | 10.53 | 0.46 | 0.05 | 0.24219
|  | 1 | 0.6 | 0.6 | 0.05 | 0.018
| Sub-total |  |  |  |  | 0.26019 | m3 | 12983.1 | 3378.0728
| VAT calculation | [7 empty] | 273.2396
6 | ;'k/ :6«Sr/, 8]s :n]a ljdx?df l;d]G6 s+lqm6 ug]{ sfd -!M!.%M#_
| -for footing | 1 | 0.6 | 0.6 | 0.225 | 0.081
|  | 1 | 0.23 | 0.23 | 2.475 | 0.13093
| -sill/lintel/DPC bands | 2 | 11.48 | 0.23 | 0.075 | 0.39606
|  | 2 | 9.4602 | 0.23 | 0.075 | 0.32638
| Sub-total |  |  |  |  | 0.93436 | m3 | 16512.62 | 15428.8067
| VAT calculation | [7 empty] | 1104.4568
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for footing | 1 | 2.4 |  | 0.225 | 0.54
|  | 1 | 0.92 |  | 2.475 | 2.277
| Sub-total |  |  |  |  | 2.817 | m2 | 915.42 | 2578.7381
| VAT calculation | [7 empty] | 171.4883
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For column footing | 6 | 0.6 | 0.39506 | 1.4222 | 0.0014222
| -For column | 4 | 3.075 | 0.88889 | 10.9333 | 0.010933
| -For column stirrups | 16 | 0.71117 | 0.39506 | 4.4953 | 0.0044953
| -For bands | 4 | 20.4402 | 0.61728 | 50.4696 | 0.05047
| -For stirrups | 135 | 0.27939 | 0.39506 | 14.9006 | 0.014901
| Sub-total |  |  |  |  | 0.082221 | MT | 131940 | 10848.2478
| VAT calculation | [7 empty] | 1135.1441
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | [10 empty] | 37.666
| -wall at backyard | 1 | 11.48 | 0.23 | 0.63487 | 1.6763 |  |  |  |  | 11.6324 | 11.48
|  | 1 | 0.406 | 0.23 | 2.5037 | 0.2338
| -deduction for sill/lintel/DPC bands | -2 | 11.48 | 0.23 | 0.075 | -0.39606
| - at instead white wall | 1 | 9.4602 | 0.23 | 2.35 | 5.1132 | [5 empty] | 2.9749 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -deduction for sill/lintel/DPC bands | -2 | 9.4602 | 0.23 | 0.075 | -0.32638
|  | 3 | 0.3566 | 0.3566 | 2.35 | 0.8965
| -for footing | 1 | 10.53 | 0.46 | 0.2 | 0.96876
| -at back yard window | 12 | 0.83816 | 0.23 | 1.2444 | 2.8788
| Sub-total |  |  |  |  | 11.0449 | m3 | 14362.76 | 158635.8406
| VAT calculation | [7 empty] | 14806.0331
10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 2 | 72.7696 |  | 1.8 | 261.9705
| Sub-total |  |  |  |  | 261.9705 | sqm | 405.86 | 106323.3458
| VAT calculation | [7 empty] | 3802.7794
11 | $=% X @) dL=dL= kmnfd] kftfsf] k¦m]ddf !@ x !@ dL=dL=;f]ln8 sf]/ :Sjfo/ /8sf] lu¦n agfO{ vfS;L nufO{ /]8cS;fO8 tyf cNd'lgod k]G6 ;d]t u/L hf]8\g]
| -window | 6 | 1.1938 |  | 1.6519 | 11.8329
| Sub-total |  |  |  |  | 11.8329 | sqm | 2575.34 | 30473.7725
| VAT calculation | [7 empty] | 3744.7793
12 | lh=cfO{=sf9]tf/ -jf/ j]8 jfo/_ nufpg] .
| -at boundary | 1 | 95.5523 |  |  | 95.5523
| Sub-total |  |  |  |  | 95.5523 | rm | 82.59 | 7891.662
| VAT calculation | [7 empty] | 247.4596
13 | %) dL=dL=Aof;sf] :6]Gn];l:6nsf] x\of08/]ndf @ ld6/sf] b"/Ldf %) dL=dL=Aof;sf] :6]Gn];l:6ns} 7f8f] kf]i6 /fvL x\of08/]n / e"O+sf] aLrdf tLg tx t];f]{ @% dL=dL=Aof;sf] :6]Gn];l:6nsf] d]Da/ /fvL @Ú–^Æ b]lv #Ú–)Æ ;Dd prfO{ ePsf] /]lnË pknAw u/fO{ h8fg u/L /+u ;d]t nufpg] sfd .
| -at boundary | 1 | 7.8735 |  |  | 7.8735
| Sub-total |  |  |  |  | 7.8735 | rm | 4132.8 | 32539.6594
| VAT calculation | [7 empty] | 4230.1557
14 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -wall | 2 | 72.7696 |  | 1.8 | 261.9705
| Sub-total |  |  |  |  | 261.9705 | sqm | 251.77 | 65956.312
| VAT calculation | [7 empty] | 4337.3931
15 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -MS Equal angle of 35mm*35mm*2mm For door | 4 | 8.1271 | 1.04 | 33.8087 | 33.8087
| -MS sheet 900mm wide or as per required and of 14G with 2mm | 4 | 2.4383 | 14.13 | 137.8116 | 137.8116
| Sub-total |  |  |  |  | 171.6204 | Kg | 181.17 | 31092.4606
| VAT calculation | [7 empty] | 2204.4662
16 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
17 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 517281.2423
| Total Estimated | 517281.2423 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 91.8263
| User Contribution | 42281.2423 |  | 8.1737
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on C11: Windows User: white wall
Note on C12: Windows User: column as wall support and including footing area
Note on D60: DELL: column part not included
Note on D61: DELL: For RCC column peripheri and ht =3 ft from GL and 225mm depth footing

## callapsible gate added
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- राष्ट्रिय मा. बि. वाल निर्माण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/21
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -White wall | 1 | 3.88 | 0.1 | 2.2859 | 0.88692
|  | 3 | 0.3566 | 0.3566 | 2.2859 | 0.87204 |  |  |  |  | kmnfd] sfd -Rofgn PËn 6L cflb_ x6fpg] sfo{ lemSg], 5'6\ofpg] / /fd¦/L yGsfpg] ;d]t
|  | 1 | 0.6 | 0.6 | 1.15 | 0.414
| Sub-total |  |  |  |  | 2.173 | m3 | 1950 | 4237.2778
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -White wall | 1 | 10.53 | 0.46 | 0.6 | 2.9063
| Sub-total |  |  |  |  | 2.9063 | m3 | 64.63 | 187.8329
| VAT calculation | [7 empty] | 20.2384
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at backyard | 1 | 0.6 | 0.6 | 0.9 | 0.324
| Sub-total |  |  |  |  | 0.324 | m3 | 663.31 | 214.9124
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing | 1 | 10.53 | 0.46 |  | 4.8438
|  | 1 | 0.6 | 0.6 |  | 0.36
| Sub-total |  |  |  |  | 5.2038 | sqm | 1014.97 | 5281.7009
| VAT calculation | [7 empty] | 582.9484
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for footing | 1 | 10.53 | 0.46 | 0.05 | 0.24219
|  | 1 | 0.6 | 0.6 | 0.05 | 0.018
| Sub-total |  |  |  |  | 0.26019 | m3 | 12983.1 | 3378.0728
| VAT calculation | [7 empty] | 273.2396
6 | ;'k/ :6«Sr/, 8]s :n]a ljdx?df l;d]G6 s+lqm6 ug]{ sfd -!M!.%M#_
| -for footing | 1 | 0.6 | 0.6 | 0.225 | 0.081
|  | 1 | 0.23 | 0.23 | 2.475 | 0.13093
| -sill/lintel/DPC bands | 2 | 11.48 | 0.23 | 0.075 | 0.39606
|  | 2 | 9.4602 | 0.23 | 0.075 | 0.32638
| Sub-total |  |  |  |  | 0.93436 | m3 | 16512.62 | 15428.8067
| VAT calculation | [7 empty] | 1104.4568
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for footing | 1 | 2.4 |  | 0.225 | 0.54
|  | 1 | 0.92 |  | 2.475 | 2.277
| Sub-total |  |  |  |  | 2.817 | m2 | 915.42 | 2578.7381
| VAT calculation | [7 empty] | 171.4883
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For column footing | 6 | 0.6 | 0.39506 | 1.4222 | 0.0014222
| -For column | 4 | 3.075 | 0.88889 | 10.9333 | 0.010933
| -For column stirrups | 16 | 0.71117 | 0.39506 | 4.4953 | 0.0044953
| -For bands | 4 | 20.4402 | 0.61728 | 50.4696 | 0.05047
| -For stirrups | 135 | 0.27939 | 0.39506 | 14.9006 | 0.014901
| Sub-total |  |  |  |  | 0.082221 | MT | 131940 | 10848.2478
| VAT calculation | [7 empty] | 1135.1441
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | [10 empty] | 37.666
| -wall at backyard | 1 | 11.48 | 0.23 | 0.63487 | 1.6763 |  |  |  |  | 11.6324 | 11.48
|  | 1 | 0.406 | 0.23 | 2.5037 | 0.2338
| -deduction for sill/lintel/DPC bands | -2 | 11.48 | 0.23 | 0.075 | -0.39606
| - at instead white wall | 1 | 9.4602 | 0.23 | 2.35 | 5.1132 | [5 empty] | 2.9749 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -deduction for sill/lintel/DPC bands | -2 | 9.4602 | 0.23 | 0.075 | -0.32638
|  | 3 | 0.3566 | 0.3566 | 2.35 | 0.8965
| -for footing | 1 | 10.53 | 0.46 | 0.2 | 0.96876
| -at back yard window | 12 | 0.83816 | 0.23 | 1.2444 | 2.8788
| Sub-total |  |  |  |  | 11.0449 | m3 | 14362.76 | 158635.8406
| VAT calculation | [7 empty] | 14806.0331
10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 2 | 72.7696 |  | 1.8 | 261.9705
| Sub-total |  |  |  |  | 261.9705 | sqm | 405.86 | 106323.3458
| VAT calculation | [7 empty] | 3802.7794
11 | $=% X @) dL=dL= kmnfd] kftfsf] k¦m]ddf !@ x !@ dL=dL=;f]ln8 sf]/ :Sjfo/ /8sf] lu¦n agfO{ vfS;L nufO{ /]8cS;fO8 tyf cNd'lgod k]G6 ;d]t u/L hf]8\g]
| -window | 6 | 1.1938 |  | 1.6519 | 11.8329
| -door | 1 | 0.885 |  | 2.05 | 1.8142
| Sub-total |  |  |  |  | 13.6472 | sqm | 2575.34 | 35146.0831
| VAT calculation | [7 empty] | 4318.9377
12 | lh=cfO{=sf9]tf/ -jf/ j]8 jfo/_ nufpg] .
| -at boundary | 1 | 95.5523 |  |  | 95.5523
| Sub-total |  |  |  |  | 95.5523 | rm | 82.59 | 7891.662
| VAT calculation | [7 empty] | 247.4596
13 | %) dL=dL=Aof;sf] :6]Gn];l:6nsf] x\of08/]ndf @ ld6/sf] b"/Ldf %) dL=dL=Aof;sf] :6]Gn];l:6ns} 7f8f] kf]i6 /fvL x\of08/]n / e"O+sf] aLrdf tLg tx t];f]{ @% dL=dL=Aof;sf] :6]Gn];l:6nsf] d]Da/ /fvL @Ú–^Æ b]lv #Ú–)Æ ;Dd prfO{ ePsf] /]lnË pknAw u/fO{ h8fg u/L /+u ;d]t nufpg] sfd .
| -at boundary | 1 | 7.8735 |  |  | 7.8735
| Sub-total |  |  |  |  | 7.8735 | rm | 4132.8 | 32539.6594
| VAT calculation | [7 empty] | 4230.1557
14 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -wall | 2 | 72.7696 |  | 1.8 | 261.9705
| Sub-total |  |  |  |  | 261.9705 | sqm | 251.77 | 65956.312
| VAT calculation | [7 empty] | 4337.3931
15 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (Kg)
| -MS Equal angle of 35mm*35mm*2mm For door | 4 | 8.1271 | 1.04 | 33.8087 | 33.8087
| -MS sheet 900mm wide or as per required and of 14G with 2mm | 4 | 2.4383 | 14.13 | 137.8116 | 137.8116
| Sub-total |  |  |  |  | 171.6204 | Kg | 181.17 | 31092.4606
| VAT calculation | [7 empty] | 2204.4662
16 | kmnfd] sf]nfK;Lan u]6 k]lG6Ë / h8fg ;d]t ug]{
| -at block D | 1 | 3.23 |  | 2.535 | 8.1881
| Sub-total |  |  |  |  | 8.1881 | sqm | 6391.43 | 52333.3484
| VAT calculation | [7 empty] | 6803.3353
17 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
18 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 581612.3772
| Total Estimated | 581612.3772 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 81.6695
| User Contribution | 106612.3772 |  | 18.3305
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on C11: Windows User: white wall
Note on C12: Windows User: column as wall support and including footing area
Note on D60: DELL: column part not included
Note on D61: DELL: For RCC column peripheri and ht =3 ft from GL and 225mm depth footing

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 581612.3772 |  |  |  |  | Total Valuated Amount : |  | 494627.2695
Work Started : | [7 empty] | Work Finished:
Project:- राष्ट्रिय मा. बि. वाल निर्माण | [7 empty] | F.Y:2081/2082
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2082/02/03
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd . | m3 | 2.173 | 1950 | 4237.2778 | 4.8615 | 1950 | 9480.0186 | 5242.7408
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | m3 | 2.9063 | 64.63 | 187.8329 | 2.7911 | 64.63 | 180.3868 | -7.446
| VAT calculation |  |  |  | 20.2384 |  |  | 19.4361 | -0.80229
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | m3 | 0.324 | 663.31 | 214.9124 | 0.5346 | 663.31 | 354.6055 | 139.6931
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd | sqm | 5.2038 | 1014.97 | 5281.7009 | 0.25174 | 1014.97 | 255.507 | -5026.1939
| VAT calculation |  |  |  | 582.9484 |  |  | 28.2006 | -554.7478
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_ | m3 | 0.26019 | 12983.1 | 3378.0728 | 0.38663 | 12983.1 | 5019.701 | 1641.6282
| VAT calculation |  |  |  | 273.2396 |  |  | 406.0248 | 132.7852
6 | ;'k/ :6«Sr/, 8]s :n]a ljdx?df l;d]G6 s+lqm6 ug]{ sfd -!M!.%M#_ | m3 | 0.93436 | 16512.62 | 15428.8067 | 0.61441 | 16512.62 | 10145.4951 | -5283.3115
| VAT calculation |  |  |  | 1104.4568 |  |  | 726.2559 | -378.201
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd | m2 | 2.817 | 915.42 | 2578.7381 | 5.9662 | 915.42 | 5461.6117 | 2882.8735
| VAT calculation |  |  |  | 171.4883 |  |  | 363.202 | 191.7136
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | MT | 0.082221 | 131940 | 10848.2478 | 0.036819 | 131940 | 4857.8367 | -5990.4111
| VAT calculation |  |  |  | 1135.1441 |  |  | 508.3166 | -626.8275
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | m3 | 11.0449 | 14362.76 | 158635.8406 | 16.1522 | 14362.76 | 231990.0192 | 73354.1786
| VAT calculation |  |  |  | 14806.0331 |  |  | 21652.433 | 6846.3999
10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/ | sqm | 261.9705 | 405.86 | 106323.3458 | 219.307 | 405.86 | 89007.9414 | -17315.4044
| VAT calculation |  |  |  | 3802.7794 |  |  | 3183.4737 | -619.3058
11 | $=% X @) dL=dL= kmnfd] kftfsf] k¦m]ddf !@ x !@ dL=dL=;f]ln8 sf]/ :Sjfo/ /8sf] lu¦n agfO{ vfS;L nufO{ /]8cS;fO8 tyf cNd'lgod k]G6 ;d]t u/L hf]8\g] | sqm | 13.6472 | 2575.34 | 35146.0831 | 11.8939 | 2575.34 | 30630.926 | -4515.1571
| VAT calculation |  |  |  | 4318.9377 |  |  | 3764.0911 | -554.8465
12 | lh=cfO{=sf9]tf/ -jf/ j]8 jfo/_ nufpg] . | rm | 95.5523 | 82.59 | 7891.662 | 0 | 82.59 | 0 | -7891.662
| VAT calculation |  |  |  | 247.4596 |  |  | 0 | -247.4596
13 | %) dL=dL=Aof;sf] :6]Gn];l:6nsf] x\of08/]ndf @ ld6/sf] b"/Ldf %) dL=dL=Aof;sf] :6]Gn];l:6ns} 7f8f] kf]i6 /fvL x\of08/]n / e"O+sf] aLrdf tLg tx t];f]{ @% dL=dL=Aof;sf] :6]Gn];l:6nsf] d]Da/ /fvL @Ú–^Æ b]lv #Ú–)Æ ;Dd prfO{ ePsf] /]lnË pknAw u/fO{ h8fg u/L /+u ;d]t nufpg] sfd . | rm | 7.8735 | 4132.8 | 32539.6594 | 0 | 4132.8 | 0 | -32539.6594
| VAT calculation |  |  |  | 4230.1557 |  |  | 0 | -4230.1557
14 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd | sqm | 261.9705 | 251.77 | 65956.312 | 219.307 | 251.77 | 55214.9249 | -10741.3871
| VAT calculation |  |  |  | 4337.3931 |  |  | 3631.0222 | -706.3709
15 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | Kg | 171.6204 | 181.17 | 31092.4606 | 88.8892 | 181.17 | 16104.0564 | -14988.4042
| VAT calculation |  |  |  | 2204.4662 |  |  | 1141.7832 | -1062.6831
16 | kmnfd] sf]nfK;Lan u]6 k]lG6Ë / h8fg ;d]t ug]{ | sqm | 8.1881 | 6391.43 | 52333.3484 | 0 | 6391.43 | 0 | -52333.3484
| VAT calculation |  |  |  | 6803.3353 |  |  | 0 | -6803.3353
17 | Provisional sum for unforseen works | PS | 1 | 5000 | 5000 | 0 | 5000 | 0 | -5000
18 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0
| Total |  |  |  | 581612.3772 |  |  | 494627.2695 | -86985.1077

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- राष्ट्रिय मा. बि. वाल निर्माण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/21
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -White wall | 1 | 3.88 | 0.1 | 2.2859 | 0.88692
|  | 3 | 0.3566 | 0.3566 | 2.2859 | 0.87204 | [5 empty] | kmnfd] sfd -Rofgn PËn 6L cflb_ x6fpg] sfo{ lemSg], 5'6\ofpg] / /fd¦/L yGsfpg] ;d]t
| -at backyard wall | 1 | 11.73 | 0.23 | 1.15 | 3.1026
| Sub-total |  |  |  |  | 4.8615 | m3 | 1950 | 9480.0186
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -White wall | 1 | 10.3373 | 0.45 | 0.6 | 2.7911
| Sub-total |  |  |  |  | 2.7911 | m3 | 64.63 | 180.3868
| VAT calculation | [7 empty] | 19.4361
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at backyard wall | 2 | 0.9 | 0.9 | 0.33 | 0.5346
| Sub-total |  |  |  |  | 0.5346 | m3 | 663.31 | 354.6055
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing | 0 | 10.3373 | 0.45 |  | 0
| -at front wall | 2 | 9.2959 | 0.23 | 0.05 | 0.21381
|  | 6 | 0.35558 | 0.35558 | 0.05 | 0.037932
| Sub-total |  |  |  |  | 0.25174 | sqm | 1014.97 | 255.507
| VAT calculation | [7 empty] | 28.2006
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -at front wall | 2 | 9.2959 | 0.23 | 0.05 | 0.21381
|  | 6 | 0.35558 | 0.35558 | 0.05 | 0.037932
| -at backyard wall | 1 | 11.73 | 0.23 | 0.05 | 0.1349
| Sub-total |  |  |  |  | 0.38663 | m3 | 12983.1 | 5019.701
| VAT calculation | [7 empty] | 406.0248
6 | ;'k/ :6«Sr/, 8]s :n]a ljdx?df l;d]G6 s+lqm6 ug]{ sfd -!M!.%M#_
| -for footing | 2 | 0.9 | 0.9 | 0.225 | 0.3645
|  | 2 | 0.23 | 0.23 | 2.3621 | 0.24991
| Sub-total |  |  |  |  | 0.61441 | m3 | 16512.62 | 10145.4951
| VAT calculation | [7 empty] | 726.2559
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for footing | 2 | 0.9 |  | 0.9 | 1.62
|  | 2 | 0.92 |  | 2.3621 | 4.3462
| Sub-total |  |  |  |  | 5.9662 | m2 | 915.42 | 5461.6117
| VAT calculation | [7 empty] | 363.202
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For column footing | 22 | 0.6 | 0.88889 | 11.7333 | 0.011733
| -For column | 8 | 2.8955 | 0.88889 | 20.5899 | 0.02059
| -For column stirrups | 16 | 0.71117 | 0.39506 | 4.4953 | 0.0044953
| Sub-total |  |  |  |  | 0.036819 | MT | 131940 | 4857.8367
| VAT calculation | [7 empty] | 508.3166
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | [11 empty] | 37.666
| -wall at backyard | 0 | 11.48 | 0.23 | 0.63487 | 0 | [5 empty] | 11.6324 | 11.48
|  | 0 | 0.406 | 0.23 | 2.5037 | 0
| -wall at backyard | 1 | 11.73 | 0.23 | 1.75 | 4.7213
| -deduction for column part | -2 | 0.23 | 0.23 | 1.75 | -0.18515
| -wall at front | 1 | 2.9717 | 0.23 | 2.1335 | 1.4582
|  | 1 | 0.35558 | 0.35558 | 2.1335 | 0.26976
|  | 1 | 2.9717 | 1.23 | 2.1335 | 7.7982
|  | 1 | 0.35558 | 0.35558 | 2.1335 | 0.26976
|  | 1 | 2.9717 | 0.23 | 2.1335 | 1.4582
|  | 1 | 0.35558 | 0.35558 | 2.1335 | 0.26976
|  | 1 | 0.43178 | 0.1 | 2.1335 | 0.09212
| -deduction for sill/lintel/DPC bands | 0 | 11.48 | 0.23 | 0.075 | 0
| - at instead white wall | 0 | 9.4602 | 0.23 | 2.35 | 0 | [6 empty] | 2.9749 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -deduction for sill/lintel/DPC bands | 0 | 9.4602 | 0.23 | 0.075 | 0
|  | 0 | 0.3566 | 0.3566 | 2.35 | 0
| -for footing | 0 | 10.53 | 0.46 | 0.2 | 0
| -at back yard window | 0 | 0.83816 | 0.23 | 1.2444 | 0
| Sub-total |  |  |  |  | 16.1522 | m3 | 14362.76 | 231990.0192
| VAT calculation | [7 empty] | 21652.433
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | [11 empty] | 37.666
| -window top cover at backyard | 1 | 17.1 | 0.23 | 0.125 | 0.49163 |  |  |  |  | 21.49
| -front side right part of gate | 1 | 0.35558 | 0.35558 | 0.12 | 0.015173
|  | 1 | 2.75 | 0.23 | 0.12 | 0.0759
|  | 1 | 0.35558 | 0.35558 | 0.12 | 0.015173
|  | 1 | 2.69 | 0.23 | 0.12 | 0.074244
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 0.95 | 0.23 | 0.12 | 0.02622
|  | 1 | 2.73 | 0.23 | 0.25 | 0.15698
|  | 1 | 0.58 | 0.23 | 0.6 | 0.08004
| -front side left part of gate | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 3.02 | 0.23 | 0.12 | 0.083352
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 3.13 | 0.23 | 0.12 | 0.086388
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 3.17 | 0.23 | 0.12 | 0.087492
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
| -window backyard | 12 | 0.83 | 0.23 | 1.2 | 2.749
| Sub-total |  |  |  |  | 4.0174 | m3 | 14362.76 | 57701.127
| VAT calculation | [7 empty] | 5385.4463
10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 0 | 72.7696 |  | 1.8 | 0 |  |  |  |  | inner face of gate side wall | 0 | 1.3
|  | 1 | 3 |  | 1.37 | 4.11 | [5 empty] | 3 | 1.44
|  | 1 | 3 |  | 1.41 | 4.23 | [5 empty] | 3 | 1.38
|  | 1 | 3 |  | 1.415 | 4.245 | [5 empty] | 3 | 1.45
|  | 1 | 3 |  | 1.455 | 4.365 | [5 empty] | 3 | 1.46
|  | 1 | 3 |  | 1.505 | 4.515 | [5 empty] | 3 | 1.55
|  | 1 | 3 |  | 1.485 | 4.455 | [5 empty] | 3 | 1.42
|  | 1 | 3.42 |  | 1.47 | 5.0274 |  |  |  |  | upto inner face to gate | 3.42 | 1.52
[11 empty] | outer face of gate side new wall | 0 | 1.7
|  |  | 0.14 |  | 1.7 | 0.238 | [5 empty] | 0.14 | 1.7
|  |  | 3.01 |  | 1.6 | 4.816 | [5 empty] | 3.01 | 1.6
|  |  | 0.58 |  | 1.7 | 0.986 | [5 empty] | 0.58 | 1.7
|  |  | 3.12 |  | 1.64 | 5.1168 | [5 empty] | 3.12 | 1.64
|  |  | 0.6 |  | 1.65 | 0.99 | [5 empty] | 0.6 | 1.65
|  |  | 3.16 |  | 1.65 | 5.214 | [5 empty] | 3.16 | 1.65
|  |  | 0.66 |  | 1.65 | 1.089 | [5 empty] | 0.66 | 1.65
|  |  | 2.96 |  | 1.71 | 5.0616 | [5 empty] | 2.96 | 1.71
|  |  | 0.62 |  | 1.72 | 1.0664 | [5 empty] | 0.62 | 1.72
|  |  | 2.96 |  | 1.735 | 5.1356 | [5 empty] | 2.96 | 1.735
|  |  | 0.63 |  | 1.7 | 1.071 | [5 empty] | 0.63 | 1.7
|  |  | 2.92 |  | 1.635 | 4.7742 | [5 empty] | 2.92 | 1.635
|  |  | 0.61 |  | 1.6 | 0.976 | [5 empty] | 0.61 | 1.6
|  |  | 0.44 |  | 1.55 | 0.682 |  |  |  |  | upto gate | 0.44 | 1.55
[11 empty] | back compound inner face wall | 0 | 1.5
|  |  | 3 |  | 1.5 | 4.5 | [5 empty] | 3 | 1.5
|  |  | 3 |  | 1.525 | 4.575 | [5 empty] | 3 | 1.55
|  |  | 3 |  | 1.55 | 4.65 | [5 empty] | 3 | 1.55
|  |  | 3 |  | 1.55 | 4.65 | [5 empty] | 3 | 1.55
|  |  | 3 |  | 1.635 | 4.905 | [5 empty] | 3 | 1.72
|  |  | 3.06 |  | 1.65 | 5.049 | [5 empty] | 3.06 | 1.65
|  |  | 0.16 |  | 1.61 | 0.2576 |  |  |  |  | break point of old wall and new wall | 0.16 | 1.61
| -window | 10 | 0.83816 |  | 1.2 | 10.0579 |  |  |  |  | old wall | 0 | 1.6
|  |  | 0.6 |  | 1.6 | 0.96 | [5 empty] | 0.6 | 1.6
|  |  | 15 |  | 0.2 | 3 |  |  |  |  | inner face complete | 15 | 0.2
[11 empty] | outside face of back compound | 0 | 1.75 | DPC to top of new wall
|  |  | 4 |  | 1.75 | 7 | [5 empty] | 4 | 1.75
|  |  | 4 |  | 1.75 | 7 | [5 empty] | 4 | 1.75
|  |  | 4.21 |  | 1.75 | 7.3675 | [5 empty] | 4.21 | 1.75 | new wall complete
|  |  | 0.49 |  | 2.1 | 1.029 | [5 empty] | 0.49 | 2.1 | old wall starts
|  |  | 0 |  | 2.1 | 0 | [5 empty] | 0 | 2.1
|  |  | 3.17 |  | 2.1 | 6.657 | [5 empty] | 3.17 | 2.1
|  |  | 0.48 |  | 2.1 | 1.008 | [5 empty] | 0.48 | 2.1
|  |  | 3.11 |  | 2.1 | 6.531 | [5 empty] | 3.11 | 2.1
|  |  | 0.6 |  | 2.1 | 1.26 | [5 empty] | 0.6 | 2.1
|  |  | 3.1 |  | 2.1 | 6.51 | [5 empty] | 3.1 | 2.1
|  |  | 0.6 |  | 2.1 | 1.26 | [5 empty] | 0.6 | 2.1
|  |  | 3.11 |  | 2.155 | 6.7021 | [5 empty] | 3.11 | 2.155
|  |  | 0.6 |  | 2.2 | 1.32 | [5 empty] | 0.6 | 2.2
|  |  | 3.1 |  | 2.24 | 6.944 | [5 empty] | 3.1 | 2.24
|  |  | 0.58 |  | 2.2 | 1.276 | [5 empty] | 0.58 | 2.2
|  |  | 3.15 |  | 2.275 | 7.1662 | [5 empty] | 3.15 | 2.275
|  |  | 3.25 |  | 2.3 | 7.475 | [5 empty] | 3.25 | 2.3
|  |  | 0.57 |  | 2.3 | 1.311 | [5 empty] | 0.57 | 2.3
|  |  | 0.97 |  | 2.3 | 2.231 | [5 empty] | 0.97 | 2.3
[11 empty] | baniya gaun baato to gate side | 0 | 1.76
|  |  | 0.48 |  | 1.75 | 0.84 | [5 empty] | 0.48 | 1.75
|  |  | 2.75 |  | 1.75 | 4.8125 | [5 empty] | 2.75 | 1.75
|  |  | 0.57 |  | 1.75 | 0.9975 | [5 empty] | 0.57 | 1.75
|  |  | 2.65 |  | 1.775 | 4.7037 | [5 empty] | 2.65 | 1.8
|  |  | 0.58 |  | 1.8 | 1.044 | [5 empty] | 0.58 | 1.8
|  |  | 1.16 |  | 1.8 | 2.088 | [5 empty] | 1.16 | 1.8
|  |  | 0.6 |  | 1.8 | 1.08 | [5 empty] | 0.6 | 1.8
|  |  | 2.7431 |  | 1.8 | 4.9375 | [5 empty] | 2.7431 | 1.8
|  |  | 0.58 |  | 2.1335 | 1.2374 | [5 empty] | 0.58 | 2.1335
| -Chautari | 1 | 15 |  | 0.45 | 6.75
| Sub-total |  |  |  |  | 219.307 | sqm | 405.86 | 89007.9414
| VAT calculation | [7 empty] | 3183.4737
11 | $=% X @) dL=dL= kmnfd] kftfsf] k¦m]ddf !@ x !@ dL=dL=;f]ln8 sf]/ :Sjfo/ /8sf] lu¦n agfO{ vfS;L nufO{ /]8cS;fO8 tyf cNd'lgod k]G6 ;d]t u/L hf]8\g]
| -window | 6 | 1.2 |  | 1.6519 | 11.8939
| -door | 0 | 0.885 |  | 2.05 | 0
| Sub-total |  |  |  |  | 11.8939 | sqm | 2575.34 | 30630.926 |  | 28262.52
| VAT calculation | [7 empty] | 3764.0911
12 | lh=cfO{=sf9]tf/ -jf/ j]8 jfo/_ nufpg] .
| -at boundary | 0 | 95.5523 |  |  | 0
| Sub-total |  |  |  |  | 0 | rm | 82.59 | 0
| VAT calculation | [7 empty] | 0
13 | %) dL=dL=Aof;sf] :6]Gn];l:6nsf] x\of08/]ndf @ ld6/sf] b"/Ldf %) dL=dL=Aof;sf] :6]Gn];l:6ns} 7f8f] kf]i6 /fvL x\of08/]n / e"O+sf] aLrdf tLg tx t];f]{ @% dL=dL=Aof;sf] :6]Gn];l:6nsf] d]Da/ /fvL @Ú–^Æ b]lv #Ú–)Æ ;Dd prfO{ ePsf] /]lnË pknAw u/fO{ h8fg u/L /+u ;d]t nufpg] sfd .
| -at boundary | 0 | 7.8735 |  |  | 0
| Sub-total |  |  |  |  | 0 | rm | 4132.8 | 0
| VAT calculation | [7 empty] | 0
14 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd |  | Area (m2)
| -wall | 1 | 219.307 |  |  | 219.307
| Sub-total |  |  |  |  | 219.307 | sqm | 251.77 | 55214.9249
| VAT calculation | [7 empty] | 3631.0222
15 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (Kg) |  |  |  | by actual measurement in digital weighing machine
| -MS Equal angle of 35mm*35mm*2mm For door | 0 | 8.1271 | 1.04 | 0 | 0 |  |  |  |  | 279
| -MS sheet 900mm wide or as per required and of 14G with 2mm | 2 |  |  | 61 | 61
| -MS Rectangular Hollow section of 40mm*25mm*1.8mm for window | 6 | 2.54 | 1.83 | 27.8892 | 27.8892
| Sub-total |  |  |  |  | 88.8892 | Kg | 181.17 | 16104.0564
| VAT calculation | [7 empty] | 1141.7832
16 | kmnfd] sf]nfK;Lan u]6 k]lG6Ë / h8fg ;d]t ug]{
| -at block D | 0 | 3.23 |  | 2.535 | 0
| Sub-total |  |  |  |  | 0 | sqm | 6391.43 | 0
| VAT calculation | [7 empty] | 0
17 | Provisional sum for unforseen works | 0 |  |  |  | 0 | PS | 5000 | 0
18 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 557713.8428
| Total Estimated | 557713.8428 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 85.1691
| User Contribution | 82713.8428 |  | 14.8309
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on C11: Windows User: white wall
Note on D58: DELL: column part not included
Note on D59: DELL: For RCC column peripheri and ht =3 ft from GL and 225mm depth footing

## Sheet2
e'O{tNnfdf lrDgL e§fsf] O{6f pknAw ug]{,
l;d]G6 d;nf -!M^_ tof/ u/L uf/f] nufpg]
sfd #) dL6/;Dd 9'jfgL ;lxt
b/ ljZn]if0fsf] nflu ! 3=ld= lnOPsf]
;¦f]t ;fwg | tx÷lsl;d | kl/df0f | PsfO{ | b/ k¦lt PsfO{ | /sd | k¦To]s ;¦f]t ;fwgsf] hDdf
>lds | s_ l;kfn' | 1.5 | hjfg | 1225 | 1837.5
| v_ HofdL | 2.2 | hjfg | 920 | 2024
| u_ HofdL | 0.2 | hjfg | 920 | 184 | 4045.5
| O{6f | 560 | uf]6f | 15.145 | 8481.2
lgdf{0f ;fdu¦L | l;d]G6 | 0.07 | d]=6= | 12131 | 849.17
| afn'jf vf]nfsf] | 0.3 | 3=dL= | 3177.9 | 953.37
| kfgL | 100 | nL6/ | 0.28 | 28 | 10311.74
| v6sf] ;ffdfg | -u_ sf] #Ü n] |  |  |  | 5.52
|  |  |  | jf:tljs b//]6 |  | 14362.76
| b/ k¦lt 3=dL=sf] |  |  | !%Ü 7]s]bf/ cf]e/x]8 |  | 2154.41
?= | 16517.17 |  |  | hDdf b/ /]6 |  | 16517.17
;¦f]t ;fwg | tx÷lsl;d | kl/df0f | PsfO{ | b/ k¦lt PsfO{ | /sd | k¦To]s ;¦f]t ;fwgsf] hDdf
>lds | s_ l;kfn' | 1.5 | hjfg | 1225 | 1837.5
| v_ HofdL | 2.2 | hjfg | 920 | 2024
| u_ HofdL | 0.2 | hjfg | 920 | 184 | 4045.5
| O{6f | 0 | uf]6f | 15.145 | 0
lgdf{0f ;fdu¦L | l;d]G6 | 0.07 | d]=6= | 12131 | 849.17
| afn'jf vf]nfsf] | 0.3 | 3=dL= | 3177.9 | 953.37
| kfgL | 100 | nL6/ | 0.28 | 28 | 1830.54
| v6sf] ;ffdfg | -u_ sf] #Ü n] |  |  |  | 5.52
|  |  |  | jf:tljs b//]6 |  | 5881.56
| b/ k¦lt 3=dL=sf] |  |  | !%Ü 7]s]bf/ cf]e/x]8 |  | 882.23
?= | 6763.79 |  |  | hDdf b/ /]6 |  | 6763.79

## Sheet1 (hidden)
S.No. | Description of work
1 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
6 | ;'k/ :6«Sr/, 8]s :n]a ljdx?df l;d]G6 s+lqm6 ug]{ sfd -!M!.%M#_
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
11 | $=% X @) dL=dL= kmnfd] kftfsf] k¦m]ddf !@ x !@ dL=dL=;f]ln8 sf]/ :Sjfo/ /8sf] lu¦n agfO{ vfS;L nufO{ /]8cS;fO8 tyf cNd'lgod k]G6 ;d]t u/L hf]8\g]
12 | lh=cfO{=sf9]tf/ -jf/ j]8 jfo/_ nufpg] .
13 | %) dL=dL=Aof;sf] :6]Gn];l:6nsf] x\of08/]ndf @ ld6/sf] b"/Ldf %) dL=dL=Aof;sf] :6]Gn];l:6ns} 7f8f] kf]i6 /fvL x\of08/]n / e"O+sf] aLrdf tLg tx t];f]{ @% dL=dL=Aof;sf] :6]Gn];l:6nsf] d]Da/ /fvL @Ú–^Æ b]lv #Ú–)Æ ;Dd prfO{ ePsf] /]lnË pknAw u/fO{ h8fg u/L /+u ;d]t nufpg] sfd .
14 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
15 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{
16 | kmnfd] sf]nfK;Lan u]6 k]lG6Ë / h8fg ;d]t ug]{
17 | Provisional sum for unforseen works
18 | Information board (सुचना पाटि)