## new (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- कुर्थली सामुदायिक ट्रस्ट निर्माण | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 1.8mm thickness for vertical post | 12 | 4.5718 | 3.97 | 217.7995 | 217.7995
| -MS square pipe of 2"*2" of 1.8mm thickness for horizontal member | 4 | 10.0579 | 2.72 | 109.4301 | 109.4301
|  | 2 | 12.1914 | 2.72 | 66.3212 | 66.3212
| -MS square pipe of 2"*2" of 1.8mm thickness for inclined member | 8 | 4.8766 | 2.72 | 106.114 | 106.114
| -MS square pipe of 2"*2" of 1.6mm thickness for king post member | 4 | 1.0667 | 2.43 | 10.3688 | 10.3688
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for diagnol member | 2 | 1.1938 | 1.83 | 4.3695 | 4.3695
|  | 2 | 1.0667 | 1.83 | 3.9043 | 3.9043
|  | 2 | 0.96617 | 1.83 | 3.5362 | 3.5362
|  | 2 | 0.91436 | 1.83 | 3.3465 | 3.3465
| -MS square pipe of 50mm * 50mm of 2.6mm thickness for vertical member | 2 | 0.81286 | 1.83 | 2.9751 | 2.9751
|  | 2 | 0.60957 | 1.83 | 2.231 | 2.231
|  | 2 | 0.40628 | 1.83 | 1.487 | 1.487
|  | 2 | 0.20319 | 1.83 | 0.74368 | 0.74368
| -MS square pipe of 2"*2" of 1.8mm thickness for purlins | 10 | 9.6007 | 2.72 | 261.1399 | 261.1399
| sub-total |  |  |  |  | 793.7667 | Kg | 181.17 | 143806.7063
| -VAT 13% for materials | [7 empty] | 10195.9454
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
|  | 2 | 4.8766 | 9.6007 |  | 93.6371
| sub-total |  |  |  |  | 93.6371 | sqm | 1070.9 | 100275.9973
| -VAT 13% for materials | [7 empty] | 10453.5728
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| ;-for footing | 12 | 0.9 | 0.9 | 0.91436 | 8.8875
| sub-total |  |  |  |  | 8.8875 | cum | 663.31 | 5895.1904
3 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf
| ;-for footing | 12 | 0.75 | 0.75 | 0.15 | 1.0125
| sub-total |  |  |  |  | 1.0125 | cum | 4473.15 | 4529.0644
| -VAT 13% for materials | [7 empty] | 407.1359
3 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| ;-for footing | 12 | 0.75 | 0.75 | 0.05 | 0.3375
| sub-total |  |  |  |  | 0.3375 | cum | 12983.1 | 4381.7963
| -VAT 13% for materials | [7 empty] | 354.4271
3 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| ;-for footing | 12 | 0.6 | 0.6 | 0.6 | 2.592
| sub-total |  |  |  |  | 2.592 | cum | 13568.9 | 35170.5888
| -VAT 13% for materials | [7 empty] | 3209.2744
3 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
4 | Information board | 1 |  |  |  | 1 | PS | 500 | 500
| Grand Total | [7 empty] | 324179.6989
| Total Estimated | 324179.6989 |  | 100
| Budget allocated | 400000
| Municipal payment | 380000 |  | 117.2189
| User Contribution | -55820.3011 |  | -17.2189
| Contingencies | 12000 |  | 3
| Maintanince | 8000 |  | 2

## as per mistry (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- कुर्थली सामुदायिक ट्रस्ट निर्माण | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 1.8mm thickness for vertical post | 15 | 5.1813 | 3.97 | 308.5492 | 308.5492
| -MS square pipe of 2"*2" of 1.8mm thickness for horizontal member | 5 | 10.0579 | 2.72 | 136.7876 | 136.7876
| -MS square pipe of 2"*2" of 1.8mm thickness for inclined member | 10 | 4.9781 | 2.72 | 135.4031 | 135.4031
| -MS square pipe of 2"*2" of 1.6mm thickness for king post member | 5 | 1.0667 | 2.43 | 12.961 | 12.961
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for diagnol member | 10 | 1.2191 | 1.83 | 22.3103 | 22.3103
|  | 10 | 1.092 | 1.83 | 19.9844 | 19.9844
|  | 10 | 0.99055 | 1.83 | 18.1271 | 18.1271
|  | 10 | 0.93965 | 1.83 | 17.1956 | 17.1956
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for vertical member | 10 | 0.81286 | 1.83 | 14.8754 | 14.8754
|  | 10 | 0.60957 | 1.83 | 11.1551 | 11.1551
|  | 10 | 0.40628 | 1.83 | 7.4349 | 7.4349
|  | 10 | 0.20319 | 1.83 | 3.7184 | 3.7184
| -MS square pipe of 2"*2" of 1.8mm thickness for purlins | 12 | 13.4105 | 2.72 | 437.7202 | 437.7202
| sub-total |  |  |  |  | 1146.2223 | Kg | 181.17 | 207661.096
| -VAT 13% for materials | [7 empty] | 14723.2437
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
|  | 2 | 4.9781 | 13.4105 |  | 133.5169
| sub-total |  |  |  |  | 133.5169 | sqm | 1070.9 | 142983.2262
| -VAT 13% for materials | [7 empty] | 14905.7163
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| ;-for footing | 15 | 0.45 | 0.45 | 0.88997 | 2.7033
| sub-total |  |  |  |  | 2.7033 | cum | 663.31 | 1793.1204
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| ;-for footing | 15 | 0.45 | 0.45 |  | 3.0375
| -for flooring | 1 | 12.1914 | 9.1436 |  | 111.4728
| sub-total |  |  |  |  | 114.5103 | sqm | 1014.97 | 116224.4867
| -VAT 13% for materials | [7 empty] | 12827.8525
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| ;-for footing | 15 | 0.45 | 0.45 | 0.075 | 0.22781
| sub-total |  |  |  |  | 0.22781 | cum | 12983.1 | 2957.7125
| -VAT 13% for materials | [7 empty] | 239.2383
6 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -for footing | 15 | 0.45 | 0.45 | 0.75 | 2.2781
|  | 15 | 0.3 | 0.3 | 0.45 | 0.6075
| -for flooring | 1 | 12.1914 | 9.1436 | 0.075 | 8.3605
| sub-total |  |  |  |  | 11.2461 | cum | 13568.9 | 152596.9702
| -VAT 13% for materials | [7 empty] | 13924.2922
7 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for footing | 8 | 4.2417 | 0.23 | 0.3 | 2.3414
|  | 4 | 2.7178 | 0.23 | 0.3 | 0.7501
| -wall | 2 | 9.1436 | 0.23 | 0.9 | 3.7854
|  | 2 | 11.7342 | 0.23 | 0.9 | 4.858
| sub-total |  |  |  |  | 11.7349 | cum | 14362.76 | 168545.8548
| -VAT 13% for materials | [7 empty] | 15730.9691
8 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 4 | 9.1436 |  | 0.9 | 32.9168
|  | 4 | 11.7342 |  | 0.9 | 42.2432
| sub-total |  |  |  |  | 75.16 | sqm | 405.86 | 30504.4425
| -VAT 13% for materials | [7 empty] | 1091.0272
9 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
10 | Information board | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 902209.2486
| Total Estimated | 902209.2486 |  | 100
| Budget allocated | 400000
| Municipal payment | 380000 |  | 42.1188
| User Contribution | 522209.2486 |  | 57.8812
| Contingencies | 12000 |  | 3
| Maintanince | 8000 |  | 2

## final (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- कुर्थली सामुदायिक ट्रस्ट निर्माण | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 1.8mm thickness for vertical post | 12 | 5.1813 | 3.97 | 246.8394 | 246.8394
| -MS square pipe of 2"*2" of 1.8mm thickness for horizontal member | 4 | 10.0579 | 2.72 | 109.4301 | 109.4301
| -MS square pipe of 2"*2" of 1.8mm thickness for inclined member | 8 | 4.9781 | 2.72 | 108.3225 | 108.3225
| -MS square pipe of 2"*2" of 1.6mm thickness for king post member | 4 | 1.0667 | 2.43 | 10.3688 | 10.3688
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for diagnol member | 8 | 1.2191 | 1.83 | 17.8482 | 17.8482
|  | 8 | 1.092 | 1.83 | 15.9875 | 15.9875
|  | 8 | 0.99055 | 1.83 | 14.5017 | 14.5017
|  | 8 | 0.93965 | 1.83 | 13.7565 | 13.7565
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for vertical member | 8 | 0.81286 | 1.83 | 11.9003 | 11.9003
|  | 8 | 0.60957 | 1.83 | 8.9241 | 8.9241
|  | 8 | 0.40628 | 1.83 | 5.9479 | 5.9479
|  | 8 | 0.20319 | 1.83 | 2.9747 | 2.9747
| -MS square pipe of 2"*2" of 1.6mm thickness for purlins | 12 | 13.4105 | 2.43 | 391.0515 | 391.0515
| sub-total |  |  |  |  | 957.8532 | Kg | 181.17 | 173534.2626
| -VAT 13% for materials | [7 empty] | 12303.6394
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
|  | 2 | 4.9284 | 12.6486 |  | 124.6739
| sub-total |  |  |  |  | 124.6739 | sqm | 1070.9 | 133513.3122
| -VAT 13% for materials | [7 empty] | 13918.4966
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -for footing | 12 | 0.45 | 0.45 | 0.88997 | 2.1626
| sub-total |  |  |  |  | 2.1626 | cum | 663.31 | 1434.4963
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing | 12 | 0.45 | 0.45 |  | 2.43
| -for tie beam | 0 | 3.4044 | 0.23 |  | 0
|  | 0 | 3.5812 | 0.23 |  | 0
| sub-total |  |  |  |  | 2.43 | sqm | 1014.97 | 2466.3771
| -VAT 13% for materials | [7 empty] | 272.2173
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for footing | 12 | 0.45 | 0.45 | 0.075 | 0.18225
| -for tie beam | 0 | 3.4044 | 0.23 | 0.05 | 0
|  | 0 | 3.5812 | 0.23 | 0.05 | 0
| sub-total |  |  |  |  | 0.18225 | cum | 12983.1 | 2366.17
| -VAT 13% for materials | [7 empty] | 191.3906
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | Nos. | Length (m) | Unit length (Kg/m) | Total Weight (Kg) | Total Weight (MT)
| -for tie beam | 4 | 40.833 | 0.88889 | 145.184 | 0.14518
| -stirrups | 143 | 0.81439 | 0.39506 | 46.0078 | 0.046008
| -for tie beam | 4 | 30.833 | 0.88889 | 109.6284 | 0.10963
| -stirrups | 95 | 0.81439 | 0.39506 | 30.5646 | 0.030565
| sub-total |  |  |  |  | 0 | MT | 131940 | 0
| -VAT 13% for materials | [7 empty] | 0
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for footing | 12 | 1.8 |  | 0.45 | 9.72
| -for column | 12 | 1.2 |  | 0.3 | 4.32
| -for tie beam | 0 | 3.8098 |  | 0.46 | 0
|  | 0 | 3.6321 |  | 0.46 | 0
|  | 0 | 3.7336 |  | 0.46 | 0
| sub-total |  |  |  |  | 14.04 | sqm | 915.42 | 12852.4968
| -VAT 13% for materials | [7 empty] | 854.7023
8 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -for footing | 12 | 0.45 | 0.45 | 0.45 | 1.0935
| -for column | 12 | 0.3 | 0.3 | 0.75 | 0.81
| -tie beam | 0 | 12.1914 | 0.23 | 0.23 | 0
|  | 0 | 9.1436 | 0.23 | 0.23 | 0
| -deduction for overlap part | 0 | 0.076196 | 0.23 | 0.23 | 0
| sub-total |  |  |  |  | 1.9035 | cum | 13568.9 | 25828.4011
| -VAT 13% for materials | [7 empty] | 2356.8109
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for footing | 4 | 3.8098 | 0.23 | 0.45 | 1.5773
|  | 4 | 3.6321 | 0.23 | 0.45 | 1.5037
|  | 2 | 3.7336 | 0.23 | 0.45 | 0.77286
| sub-total |  |  |  |  | 3.8538 | cum | 14362.76 | 55351.5118
| -VAT 13% for materials | [7 empty] | 5166.1486
10 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
11 | Information board | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 448410.4337
| Total Estimated | 448410.4337 |  | 100
| Budget allocated | 400000
| Municipal payment | 380000 |  | 84.7438
| User Contribution | 68410.4337 |  | 15.2562
| Contingencies | 12000 |  | 3
| Maintanince | 8000 |  | 2

## 400000 final
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- कुर्थली सामुदायिक ट्रस्ट निर्माण | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 1.8mm thickness for vertical post | 12 | 5.1813 | 3.97 | 246.8394 | 246.8394
| -MS square pipe of 2"*2" of 1.8mm thickness for horizontal member | 4 | 10.0579 | 2.72 | 109.4301 | 109.4301
| -MS square pipe of 2"*2" of 1.8mm thickness for inclined member | 8 | 4.9781 | 2.72 | 108.3225 | 108.3225
| -MS square pipe of 2"*2" of 1.6mm thickness for king post member | 4 | 1.0667 | 2.43 | 10.3688 | 10.3688
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for diagnol member | 8 | 1.2191 | 1.83 | 17.8482 | 17.8482
|  | 8 | 1.092 | 1.83 | 15.9875 | 15.9875
|  | 8 | 0.99055 | 1.83 | 14.5017 | 14.5017
|  | 8 | 0.93965 | 1.83 | 13.7565 | 13.7565
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for vertical member | 8 | 0.81286 | 1.83 | 11.9003 | 11.9003
|  | 8 | 0.60957 | 1.83 | 8.9241 | 8.9241
|  | 8 | 0.40628 | 1.83 | 5.9479 | 5.9479
|  | 8 | 0.20319 | 1.83 | 2.9747 | 2.9747
| -MS square pipe of 2"*2" of 1.6mm thickness for purlins | 12 | 13.4105 | 2.43 | 391.0515 | 391.0515
| sub-total |  |  |  |  | 957.8532 | Kg | 181.17 | 173534.2626
| -VAT 13% for materials | [7 empty] | 12303.6394
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
|  | 2 | 4.9284 | 12.6486 |  | 124.6739
| sub-total |  |  |  |  | 124.6739 | sqm | 1070.9 | 133513.3122
| -VAT 13% for materials | [7 empty] | 13918.4966
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -for footing | 12 | 0.45 | 0.45 | 0.88997 | 2.1626
| sub-total |  |  |  |  | 2.1626 | cum | 663.31 | 1434.4963
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing | 12 | 0.45 | 0.45 |  | 2.43
| -for tie beam | 0 | 3.4044 | 0.23 |  | 0
|  | 0 | 3.5812 | 0.23 |  | 0
| sub-total |  |  |  |  | 2.43 | sqm | 1014.97 | 2466.3771
| -VAT 13% for materials | [7 empty] | 272.2173
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for footing | 12 | 0.45 | 0.45 | 0.075 | 0.18225
| -for tie beam | 0 | 3.4044 | 0.23 | 0.05 | 0
|  | 0 | 3.5812 | 0.23 | 0.05 | 0
| sub-total |  |  |  |  | 0.18225 | cum | 12983.1 | 2366.17
| -VAT 13% for materials | [7 empty] | 191.3906
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | Nos. | Length (m) | Unit length (Kg/m) | Total Weight (Kg) | Total Weight (MT)
| -for tie beam | 4 | 40.833 | 0.88889 | 145.184 | 0.14518
| -stirrups | 143 | 0.81439 | 0.39506 | 46.0078 | 0.046008
| -for tie beam | 4 | 30.833 | 0.88889 | 109.6284 | 0.10963
| -stirrups | 95 | 0.81439 | 0.39506 | 30.5646 | 0.030565
| sub-total |  |  |  |  | 0 | MT | 131940 | 0
| -VAT 13% for materials | [7 empty] | 0
6 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for footing | 12 | 1.8 |  | 0.45 | 9.72
| -for column | 12 | 1.2 |  | 0.3 | 4.32
| -for tie beam | 0 | 3.8098 |  | 0.46 | 0
|  | 0 | 3.6321 |  | 0.46 | 0
|  | 0 | 3.7336 |  | 0.46 | 0
| sub-total |  |  |  |  | 14.04 | sqm | 915.42 | 12852.4968
| -VAT 13% for materials | [7 empty] | 854.7023
7 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -for footing | 12 | 0.45 | 0.45 | 0.45 | 1.0935
| -for column | 12 | 0.3 | 0.3 | 0.75 | 0.81
| -tie beam | 0 | 12.1914 | 0.23 | 0.23 | 0
|  | 0 | 9.1436 | 0.23 | 0.23 | 0
| -deduction for overlap part | 0 | 0.076196 | 0.23 | 0.23 | 0
| sub-total |  |  |  |  | 1.9035 | cum | 13568.9 | 25828.4011
| -VAT 13% for materials | [7 empty] | 2356.8109
8 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for footing | 4 | 3.8098 | 0.23 | 0.5 | 1.7525
|  | 4 | 3.6321 | 0.23 | 0.5 | 1.6708
|  | 2 | 3.7336 | 0.23 | 0.5 | 0.85873
| sub-total |  |  |  |  | 4.282 | cum | 14362.76 | 61501.6798
| -VAT 13% for materials | [7 empty] | 5740.1651
9 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
10 | Information board | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 455134.6182
| Total Estimated | 455134.6182 |  | 100
| Budget allocated | 400000
| Municipal payment | 380000 |  | 83.4918
| User Contribution | 75134.6182 |  | 16.5082
| Contingencies | 12000 |  | 3
| Maintanince | 8000 |  | 2