## just 15%
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- कालिका भगवती मन्दिर परिसरमा विभिन्न भौतिक संरचना निर्माण (शौचालय निर्माण) | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2082/02/17
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -For roof slab | 1 | 3.886 | 3.3526 |  | 13.0284
|  | -1 | 10.5275 | 0.23 |  | -2.4213
|  | -1 | 1.9811 | 0.115 |  | -0.22783
| Sub-total |  |  |  |  | 10.3792 | m2 | 915.42 | 9501.3436
| VAT calculation | [7 empty] | 631.8477
2 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit length (kg/m) | Weight (kg) | Weight (MT)
| -For roof slab | 44 | 3.886 | 0.39506 | 67.5494 | 0.067549
|  | 104 | 3.3526 | 0.39506 | 137.7478 | 0.13775
| Sub-total |  |  |  |  | 0.2053 | MT | 131940 | 27086.9179
| VAT calculation | [7 empty] | 2834.3337
3 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -For roof slab | 1 | 3.886 | 3.3526 | 0.1 | 1.3028
| Sub-total |  |  |  |  | 1.3028 | m3 | 13568.9 | 17678.0782
| VAT calculation | [7 empty] | 1613.1036
4 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for toilet | 2 | 1.33 | 0.23 | 0.15 | 0.09177
| Sub-total |  |  |  |  | 0.09177 | m3 | 14362.76 | 1318.0705
| VAT calculation | [7 empty] | 123.0201
5 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -walls | 1 | 10.339 |  | 2.1335 | 22.0582
| -deduction for door | -2 | 0.76196 |  | 1.8287 | -2.7868
| -deduction for window | -2 | 0.76196 |  | 0.33008 | -0.50302
| Sub-total |  |  |  |  | 18.7684 | sqm | 405.86 | 7617.3404
| VAT calculation | [7 empty] | 272.4431
6 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd .
| -for toilet walls | 4 | 1.97 |  | 1.5 | 11.82
|  | 4 | 1.33 |  | 1.5 | 7.98
| -deduction for door | -2 | 0.76196 |  | 1.5 | -2.2859
| for floors | 2 | 1.33 | 1.97 |  | 5.2402
| -deduction for toilet pan | -2 | 0.45 | 0.6 |  | -0.54
| Sub-total |  |  |  |  | 22.2143 | sqm | 2807.39 | 62364.2361
| VAT calculation | [7 empty] | 2312.873
7 | Knfi6/ dfly @) dL=dL= afSnf] emNn/ jf kfgL k§L agfpg] sfd
| -For roof slab | 1 | 14.4773 |  |  | 14.4773
| Sub-total |  |  |  |  | 14.4773 | rm | 137.45 | 1989.904
| VAT calculation | [7 empty] | 183.7632
8 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -outer wall | 1 | 8.0464 |  | 2.1 | 16.8975
|  | 1 | 2.4383 |  | 1 | 2.4383
| -inner walls | 1 | 13.2 |  | 0.6 | 7.92
| -deduction for door | -4 | 0.76196 |  | 1.8287 | -5.5736
| -deduction for window | -2 | 0.91436 |  | 0.60957 | -1.1147
|  | -2 | 0.76196 |  | 0.33008 | -0.50302
| Sub-total |  |  |  |  | 20.0644 | sqm | 251.77 | 5051.6186
| VAT calculation | [7 empty] | 332.9851
9 | Ready made Teak wood Doors, ordinary (Seasoned and Poisoned treated) with all neccessary hardware all complete.
| -door | 2 | 0.6 |  | 1.7525 | 2.103 | sqm | 5513.08 | 11594.103
| VAT calculation | [7 empty] | 873.532
10 | Roof top PVC water tank
| -1000 lit capacity | 1 | 1000 |  |  | 1000 | lit | 10 | 10000
| VAT calculation | [7 empty] | 1300
11 | Provisional Sum for unforeseen works in toilet and its fittings and plumbing works | 1 |  |  |  | 1 | PS | 26000 | 26000
12 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 191179.5139
| Total Estimated | 191179.5139 |  | 100
| Budget allocated | 170000
| Municipal payment | 161500 |  | 84.4756
| User Contribution | 29679.5139 |  | 15.5244
| Contingencies | 5100 |  | 3
| Maintanince | 3400 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 191179.5139 |  |  |  |  | Total Valuated Amount : |  | 185938.239
Work Started : | [7 empty] | Work Finished:
Project:- कालिका भगवती मन्दिर परिसरमा विभिन्न भौतिक संरचना निर्माण (शौचालय निर्माण) | [7 empty] | F.Y:2081/2082
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2082/01/04
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd | m2 | 10.3792 | 915.42 | 9501.3436 | 10.326 | 915.42 | 9452.6618 | -48.6818 |  | 11876.6795
| VAT calculation |  |  |  | 631.8477 |  |  | 628.6103 | -3.2374
2 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | MT | 0.2053 | 131940 | 27086.9179 | 0.12679 | 131940 | 16728.8192 | -10358.0987
| VAT calculation |  |  |  | 2834.3337 |  |  | 1750.4781 | -1083.8556
3 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_ | m3 | 1.3028 | 13568.9 | 17678.0782 | 1.6219 | 13568.9 | 22007.3989 | 4329.3207
| VAT calculation |  |  |  | 1613.1036 |  |  | 2008.149 | 395.0454
4 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | m3 | 0.09177 | 14362.76 | 1318.0705 | 0.08832 | 14362.76 | 1268.519 | -49.5515
| VAT calculation |  |  |  | 123.0201 |  |  | 118.3953 | -4.6248
5 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/ | sqm | 18.7684 | 405.86 | 7617.3404 | 18.555 | 405.86 | 7530.7503 | -86.5901
| VAT calculation |  |  |  | 272.4431 |  |  | 269.3461 | -3.097
6 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd . | sqm | 22.2143 | 2807.39 | 62364.2361 | 22.172 | 2807.39 | 62245.4511 | -118.785 |  | 77955.2951
| VAT calculation |  |  |  | 2312.873 |  |  | 2308.4677 | -4.4053
7 | Knfi6/ dfly @) dL=dL= afSnf] emNn/ jf kfgL k§L agfpg] sfd | rm | 14.4773 | 137.45 | 1989.904 | 14.46 | 137.45 | 1987.527 | -2.377 |  | 2487.38
| VAT calculation |  |  |  | 183.7632 |  |  | 183.5437 | -0.21951
8 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd | sqm | 20.0644 | 251.77 | 5051.6186 | 25.3459 | 251.77 | 6381.3468 | 1329.7282
| VAT calculation |  |  |  | 332.9851 |  |  | 420.6361 | 87.651
9 | Ready made Teak wood Doors, ordinary (Seasoned and Poisoned treated) with all neccessary hardware all complete. | sqm | 2.103 | 5513.08 | 11594.103 | 2.1672 | 5513.08 | 11947.947 | 353.844
| VAT calculation |  |  |  | 873.532 |  |  | 900.1916 | 26.6596
10 | Roof top PVC water tank | lit | 1000 | 10 | 10000 | 1000 | 10 | 10000 | 0
| VAT calculation |  |  |  | 1300 |  |  | 1300 | 0
11 | Provisional Sum for unforeseen works in toilet and its fittings and plumbing works | PS | 1 | 26000 | 26000 | 1 | 26000 | 26000 | 0
12 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0
| Total |  |  |  | 191179.5139 |  |  | 185938.239 | -5241.2749

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- कालिका भगवती मन्दिर परिसरमा विभिन्न भौतिक संरचना निर्माण (शौचालय निर्माण) | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2082/02/17
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -For roof slab | 1 | 3.92 | 3.31 |  | 12.9752
|  | -1 | 10.5275 | 0.23 |  | -2.4213
|  | -1 | 1.9811 | 0.115 |  | -0.22783
| Sub-total |  |  |  |  | 10.326 | m2 | 915.42 | 9452.6618
| VAT calculation | [7 empty] | 628.6103
2 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit length (kg/m) | Weight (kg) | Weight (MT)
| -For roof slab | 42 | 3.82 | 0.39506 | 63.3837 | 0.063384
|  | 50 | 3.21 | 0.39506 | 63.4074 | 0.063407
| Sub-total |  |  |  |  | 0.12679 | MT | 131940 | 16728.8192
| VAT calculation | [7 empty] | 1750.4781
3 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -For roof slab | 1 | 3.92 | 3.31 | 0.125 | 1.6219
| Sub-total |  |  |  |  | 1.6219 | m3 | 13568.9 | 22007.3989
| VAT calculation | [7 empty] | 2008.149
4 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for toilet | 2 | 1.28 | 0.23 | 0.15 | 0.08832
| Sub-total |  |  |  |  | 0.08832 | m3 | 14362.76 | 1268.519
| VAT calculation | [7 empty] | 118.3953
5 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -walls | 1 | 10.239 |  | 2.1335 | 21.8449
| -deduction for door | -2 | 0.76196 |  | 1.8287 | -2.7868
| -deduction for window | -2 | 0.76196 |  | 0.33008 | -0.50302
| Sub-total |  |  |  |  | 18.555 | sqm | 405.86 | 7530.7503
| VAT calculation | [7 empty] | 269.3461
6 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd .
| -for toilet walls | 4 | 1.9 |  | 1.47 | 11.172
|  | 4 | 1.28 |  | 1.47 | 7.5264
|  | 2 | 0.45 |  | 0.6 | 0.54
| -deduction for door | -2 | 0.73 |  | 1.47 | -2.1462
| for floors | 2 | 1.28 | 1.9 |  | 4.864
| -deduction for toilet pan | -2 | 0.45 | 0.6 |  | -0.54
|  | 2 | 0.73 |  | 0.23 | 0.3358
|  | 2 | 0.75 | 0.28 |  | 0.42
| Sub-total |  |  |  |  | 22.172 | sqm | 2807.39 | 62245.4511
| VAT calculation | [7 empty] | 2308.4677
7 | Knfi6/ dfly @) dL=dL= afSnf] emNn/ jf kfgL k§L agfpg] sfd
| -For roof slab | 1 | 14.46 |  |  | 14.46
| Sub-total |  |  |  |  | 14.46 | rm | 137.45 | 1987.527
| VAT calculation | [7 empty] | 183.5437
8 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -outer wall | 2 | 2.47 |  | 2.13 | 10.5222
|  | 2 | 3.28 |  | 2.13 | 13.9728
| -inner walls | 1 | 12.8 |  | 0.6 | 7.68 |  |  |  |  | 0.66
| -deduction for door | -4 | 0.73 |  | 1.8287 | -5.3398
| -deduction for window | -2 | 0.91436 |  | 0.6 | -1.0972
|  | -2 | 0.7 |  | 0.28 | -0.392
| Sub-total |  |  |  |  | 25.3459 | sqm | 251.77 | 6381.3468
| VAT calculation | [7 empty] | 420.6361
9 | Ready made Teak wood Doors,ordinary (Seasoned and Poisoned treated) with all neccessary hardware all complete.
| -door | 2 | 0.63 |  | 1.72 | 2.1672 | sqm | 5513.08 | 11947.947
| VAT calculation | [7 empty] | 900.1916
10 | Roof top PVC water tank
| -1000 lit capacity | 1 | 1000 |  |  | 1000 | lit | 10 | 10000
| VAT calculation | [7 empty] | 1300
11 | Provisional Sum for unforeseen works in toilet and its fittings and plumbing works | 1 |  |  |  | 1 | PS | 26000 | 26000
12 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 185938.239
| Total Valuated | 185938.239 |  | 100
| Budget allocated | 170000
| Municipal payment | 161500 |  | 86.8568
| User Contribution | 24438.239 |  | 13.1432
| Contingencies | 5100 |  | 3
| Maintanince | 3400 |  | 2