## Estimate (3)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- सानागाउँ ढल व्यबस्थापन | [6 empty] | F.Y.: 2081/2082 |  |  |  |  | subservience
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks | 45m
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य) | [9 empty] | 13m | ht=3'9"
| -For wall | 0.5 | 13 | 1.375 | 2.75 | 24.5781
| -For drain clearance | 1 | 50 | 1.5 | 0.5 | 37.5
| Sub-total |  |  |  |  | 62.0781 | m3 | 64.63 | 4012.1092
| VAT calculation | [7 empty] | 432.2914
2 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance
| -for empty bag filling | 2 | 30 | 0.38 | 79 | 158 |  |  |  | labour cost only
| Sub-total |  |  |  |  | 158 | sack | 92 | 14536
3 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Road | 1 | 13 | 1.375 | 0.15 | 2.6812
| Sub-total |  |  |  |  | 2.6812 | m3 | 4561.53 | 12230.6023
| VAT calculation | [7 empty] | 1077.2394
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For wall | 1 | 13 | 1.375 | 0.075 | 1.3406
|  | 1 | 13 | 0.5 | 0.05 | 0.325
| Sub-total |  |  |  |  | 1.6656 | m3 | 10634.5 | 17713.0891
| VAT calculation | [7 empty] | 1747.3004
5 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -For wall | 1 | 13 | 0.90774 | 2.75 | 32.4517
| Sub-total |  |  |  |  | 32.4517 | m3 | 9709.43 | 315087.1936
| VAT calculation | [7 empty] | 22858.7793
6 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia.
| -450mm hume pipe | 4 | 2.5 |  |  | 10
| Sub-total |  |  |  |  | 10 | rm | 5144.96 | 51449.6
| VAT calculation | [7 empty] | 5965.9184
7 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
7.8744
| Grand Total | [7 empty] | 447610.123
| Total Estimated | 447610.123 |  | 100
| Budget allocated | 400000
| Municipal payment | 380000 |  | 84.8953
| User Contribution | 67610.123 |  | 15.1047
| Contingencies | 12000 |  | 3
| Maintanince | 8000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 447610.123 |  |  |  |  | Total Valuated Amount : |  | 448359.425
Work Started : | [7 empty] | Work Finished:
Project:- सानागाउँ ढल व्यबस्थापन | [7 empty] | F.Y:2079/80
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2079/06/13
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य) | m3 | 62.0781 | 64.63 | 4012.1092 | 70.3125 | 64.63 | 4544.2969 | 532.1877 |  | 5015.1365
| VAT calculation |  |  |  | 432.2914 |  |  | 489.6328 | 57.3414 |  | 540.3642
2 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance | sack | 158 | 92 | 14536 | 158 | 92 | 14536 | 0 |  | 18170
3 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | m3 | 2.6812 | 4561.53 | 12230.6023 | 2.8596 | 4561.53 | 13044.3631 | 813.7608 |  | 15288.2529
| VAT calculation |  |  |  | 1077.2394 |  |  | 1148.9133 | 71.6739 |  | 1346.5492
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 | m3 | 1.6656 | 10634.5 | 17713.0891 | 1.7673 | 10634.5 | 18794.5988 | 1081.5098 |  | 22141.3613
| VAT calculation |  |  |  | 1747.3004 |  |  | 1853.9855 | 106.6851 |  | 2184.1255
5 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications. | m3 | 32.4517 | 9709.43 | 315087.1936 | 32.2679 | 9709.43 | 313302.7908 | -1784.4028 |  | 393858.992
| VAT calculation |  |  |  | 22858.7793 |  |  | 22729.3254 | -129.4539 |  | 28573.4742
6 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia. | rm | 10 | 5144.96 | 51449.6 | 10 | 5144.96 | 51449.6 | 0
| VAT calculation |  |  |  | 5965.9184 |  |  | 5965.9184 | 0
7 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0 |  | 625
| Total |  |  |  | 447610.123 |  |  | 448359.425 | 749.3019

## Valuated
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- सानागाउँ ढल व्यबस्थापन | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य)
| -For wall | 0.5 | 15 | 1.25 | 1.5 | 14.0625
| -For drain clearance | 1 | 50 | 1.5 | 0.75 | 56.25
| Sub-total |  |  |  |  | 70.3125 | m3 | 64.63 | 4544.2969
| VAT calculation | [7 empty] | 489.6328
2 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance
| -for empty bag filling | 2 | 30 | 0.38 | 79 | 158 |  |  |  | labour cost only
| Sub-total |  |  |  |  | 158 | sack | 92 | 14536
3 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | [9 empty] | Description | Amount | VAT 13% | Total
| -Road | 1 | 15 | 1.271 | 0.15 | 2.8596 |  |  |  |  | jcb | 3766.4063 | 489.6328 | 4256.0391
| Sub-total |  |  |  |  | 2.8596 | m3 | 4561.53 | 13044.3631 |  | stone | 104407.4027 | 13572.9624 | 117980.3651
| VAT calculation | [7 empty] | 1148.9133 |  | cement | 41122.7308 | 5345.955 | 46468.6858
[11 empty] | sand | 45370.8939 | 5898.2162 | 51269.1101
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 | [9 empty] | aggregate | 5134.6183 | 667.5004 | 5802.1187
| -For wall | 1 | 15 | 1.271 | 0.075 | 1.4298 |  |  |  |  | formwork | 722.8705 | 93.9732 | 816.8437
|  | 1 | 15 | 0.45 | 0.05 | 0.3375 |  |  |  |  | water | 2073.6584 | 269.5756 | 2343.2339
| Sub-total |  |  |  |  | 1.7673 | m3 | 10634.5 | 18794.5988 |  | hume pipe | 45000 | 5850 | 50850
| VAT calculation | [7 empty] | 1853.9855
5 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -For wall | 1 | 15 | 0.86048 | 2.5 | 32.2679
| Sub-total |  |  |  |  | 32.2679 | m3 | 9709.43 | 313302.7908
| VAT calculation | [7 empty] | 22729.3254
6 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia.
| -450mm hume pipe | 4 | 2.5 |  |  | 10
| Sub-total |  |  |  |  | 10 | rm | 5144.96 | 51449.6
| VAT calculation | [7 empty] | 5965.9184
7 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 448359.425
| Total Valuated | 448359.425 |  | 100
| Budget allocated | 400000
| Municipal payment | 380000 |  | 84.7534
| User Contribution | 68359.425 |  | 15.2466
| Contingencies | 12000 |  | 3
| Maintanince | 8000 |  | 2

## M
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- सानागाउँ ढल व्यबस्थापन | [9 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [9 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य)
| -For wall | 0.5 | 15 | 1.25 | 1.5 | 14.0625
| -For drain clearance | 1 | 50 | 1.5 | 0.75 | 56.25
| Sub-total |  |  |  |  | 70.3125 | m3 | 64.63 | 4544.2969
| VAT calculation | [7 empty] | 489.6328
2 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance
| -for empty bag filling | 2 | 30 | 0.38 | 79 | 158 |  |  |  | labour cost only
| Sub-total |  |  |  |  | 158 | sack | 92 | 14536
3 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | [9 empty] | Description | Amount | VAT 13% | Total
| -Road | 1 | 15 | 1.271 | 0.15 | 2.8596 |  |  |  |  | jcb | 3766.4063 | 489.6328 | 4256.0391
| Sub-total |  |  |  |  | 2.8596 | m3 | 4561.53 | 13044.3631 |  | stone | 104407.4027 | 13572.9624 | 117980.3651
| VAT calculation | [7 empty] | 1148.9133 |  | cement | 41122.7308 | 5345.955 | 46468.6858
[11 empty] | sand | 45370.8939 | 5898.2162 | 51269.1101
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 | [9 empty] | aggregate | 5134.6183 | 667.5004 | 5802.1187
| -For wall | 1 | 15 | 1.271 | 0.075 | 1.4298 |  |  |  |  | formwork | 722.8705 | 93.9732 | 816.8437
|  | 1 | 15 | 0.45 | 0.05 | 0.3375 |  |  |  |  | water | 2073.6584 | 269.5756 | 2343.2339
| Sub-total |  |  |  |  | 1.7673 | m3 | 10634.5 | 18794.5988 |  | hume pipe | 45000 | 5850 | 50850
| VAT calculation | [7 empty] | 1853.9855
5 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -For wall | 1 | 15 | 0.86048 | 2.5 | 32.2679
| Sub-total |  |  |  |  | 32.2679 | m3 | 9709.43 | 313302.7908
| VAT calculation | [7 empty] | 22729.3254
6 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia.
| -450mm hume pipe | 4 | 2.5 |  |  | 10
| Sub-total |  |  |  |  | 10 | rm | 5144.96 | 51449.6
| VAT calculation | [7 empty] | 5965.9184
7 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 448359.425
| Total Valuated | 448359.425 |  | 100
| Budget allocated | 400000
| Municipal payment | 380000 |  | 84.7534
| User Contribution | 68359.425 |  | 15.2466
| Contingencies | 12000 |  | 3
| Maintanince | 8000 |  | 2

## V (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- सानागाउँ ढल व्यबस्थापन | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य)
| -For wall | 0.5 | 15 | 1.25 | 1 | 9.375
| Sub-total |  |  |  |  | 9.375 | m3 | 64.63 | 605.9062
| VAT calculation | [7 empty] | 65.2844
2 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance
| -for empty bag filling | 1 | 60 | 0.38 | 158 | 158 |  |  |  | labour cost only
| Sub-total |  |  |  |  | 158 | sack | 92 | 14536
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For wall | 1 | 15 | 1.3206 | 0.075 | 1.4857
|  | 1 | 15 | 0.45 | 0.05 | 0.3375
| Sub-total |  |  |  |  | 1.8232 | m3 | 10634.5 | 19388.9607
| VAT calculation | [7 empty] | 1912.616
5 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -For wall | 1 | 15 | 0.85 | 2.5 | 31.875 | [5 empty] | 1.25
| Sub-total |  |  |  |  | 31.875 | m3 | 9709.43 | 309488.0812
| VAT calculation | [7 empty] | 22452.5779 |  | 2.5907 | 8.33 | 2.5389 | 2.5398
6 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia.
| -450mm hume pipe | 4 | 2.5 |  |  | 10
| Sub-total |  |  |  |  | 10 | m3 | 5144.96 | 51449.6
| VAT calculation | [7 empty] | 5965.9184
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 426364.9449
| Total Valuated | 426364.9449 |  | 100
| Budget allocated | 400000
| Municipal payment | 380000 |  | 89.1255
| User Contribution | 46364.9449 |  | 10.8745
| Contingencies | 12000 |  | 3
| Maintanince | 8000 |  | 2