## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- वडा कार्यालय अगाडी ढलान गरि ब्लक बिछ्याउने कार्य | [6 empty] | F.Y.: 2081/2082 |  |  |  |  | subservience
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2082/02/19
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks | 45m
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य) | [9 empty] | 13m | ht=3'9"
| -For stone masonary | 0.15 | 4.2 | 2.7431 | 5.029 | 0.86405
|  | 0.15 | 5.029 | 2.2859 | 4.7242 | 0.8055
| -deduction for occupied area | -1 | 1.3207 | 0.55877 | 0.15 | -0.1107
|  | -1 | 0.83 | 0.37 | 0.15 | -0.046065
|  | -1 | 0.99055 | 0.60957 | 0.15 | -0.090572
| Sub-total |  |  |  |  | 1.4222 | m3 | 736.88 | 1048.0051
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | [10 empty] | 3fF; sf6\g] To;sf] h/f lemSg], l9:sf] k'm6fpg] / n]en u/L :yn ;kmf ug]{ ;a} jf]sgL ;d]t
| -For stone masonary | 0.15 | 4.2 | 2.7431 | 5.029 | 0.86405
|  | 0.15 | 5.029 | 2.2859 | 4.7242 | 0.8055
| -deduction for occupied area | -1 | 1.3207 | 0.55877 | 0.15 | -0.1107
|  | -1 | 0.83 | 0.37 | 0.15 | -0.046065
|  | -1 | 0.99055 | 0.60957 | 0.15 | -0.090572
| Sub-total |  |  |  |  | 1.4222 | m3 | 4434.52 | 6306.8608
| VAT calculation | [7 empty] | 547.9209
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For stone masonary | 0.05 | 4.2 | 2.7431 | 5.029 | 0.28802 |  |  |  | Area of scalene triangle
|  | 0.05 | 5.029 | 2.2859 | 4.7242 | 0.2685
| -deduction for occupied area | -1 | 1.3207 | 0.55877 | 0.05 | -0.0369
|  | -1 | 0.83 | 0.37 | 0.05 | -0.015355
|  | -1 | 0.99055 | 0.60957 | 0.05 | -0.030191
| Sub-total |  |  |  |  | 0.47407 | m3 | 10634.5 | 5041.531
| VAT calculation | [7 empty] | 497.3198
4 | dfn;fdfg pknAw u/L %) dL=dL= df]6f] x]eL 8o"6L OG6/nls+u s+lqm6Ans %) dL=dL=df]6fOsf] qm;/ 8:6 dfyL /fvL la5ofpg]] sfd k'/f |  |  |  |  | Area(m2)
| -For stone masonary | 1 | 4.2 | 2.7431 | 5.029 | 5.7604
|  | 1 | 5.029 | 2.2859 | 4.7242 | 5.37
| -deduction for occupied area | -1 | 1.3207 | 0.55877 |  | -0.73799
|  | -1 | 0.83 | 0.37 |  | -0.3071
|  | -1 | 0.99055 | 0.60957 |  | -0.60381
| Sub-total |  |  |  |  | 9.4815 | m2 | 1737.28 | 16471.9565
| VAT calculation | [7 empty] | 856.379
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
7.8744
| Grand Total | [7 empty] | 31269.973
| Total Estimated | 31269.973 |  | 100
| Budget allocated | 27500
| Municipal payment | 26125 |  | 83.5466
| User Contribution | 5144.973 |  | 16.4534
| Contingencies | 825 |  | 3
| Maintanince | 550 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | #REF! |  |  |  |  | Total Valuated Amount : |  | #REF!
Work Started : | [7 empty] | Work Finished:
Project:- वडा कार्यालय अगाडी ढलान गरि ब्लक बिछ्याउने कार्य | [7 empty] | F.Y:2081/82
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2082/01/12
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य) | m3 | 1.4222 | 736.88 | 1048.0051 | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  |  | #REF! |  |  | #REF! | #REF!
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | m3 | 1.4222 | 4434.52 | 6306.8608 | #REF! | #REF! | #REF! | #REF!
| VAT calculation |  |  |  | 547.9209 |  |  | #REF! | #REF!
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 | m3 | 0.47407 | 10634.5 | 5041.531 | #REF! | #REF! | #REF! | #REF!
| VAT calculation |  |  |  | 497.3198 |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  |  | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  |  | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  |  | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  |  | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  |  | #REF! |  |  | #REF! | #REF!
5 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | #REF! | #REF! | #REF! | #REF!
| Total |  |  |  | #REF! |  |  | #REF! | #REF!

## M
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- बद्री पुडासैनीको घर जाने बाटो ढलान | [6 empty] | F.Y.: 2081/2082 |  |  |  |  | subservience
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2082/01/11
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks | 45m
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य) | [9 empty] | 13m | ht=3'9"
| -for road | 1 | 6.5 | 5 | 0.15 | 27.9929
| -for geotextile laying | 1 | 3 | 1 | 1 | 3
| Sub-total |  |  |  |  | 30.9929 | m3 | 64.63 | 2003.074
| VAT calculation | [7 empty] | 215.8245
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | [10 empty] | 3fF; sf6\g] To;sf] h/f lemSg], l9:sf] k'm6fpg] / n]en u/L :yn ;kmf ug]{ ;a} jf]sgL ;d]t
| -as of RCC quantity | 1 | 6.5 | 5 | 0.15 | 27.9929
| Sub-total |  |  |  |  | 27.9929 | m3 | 4434.52 | 124135.2744
| VAT calculation | [7 empty] | 10784.4948
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For stone masonary | 1 | 1.75 | 0.5 | 0.05 | 0.04375
|  | 1 | 1 | 0.5 | 0.05 | 0.025
|  | 1 | 1 | 0.25 | 0.05 | 0.0125
|  | 1 | 2.98 | 0.5 | 0.05 | 0.0745
|  | 1 | 2.4 | 0.5 | 0.05 | 0.06
| Sub-total |  |  |  |  | 0.21575 | m3 | 10634.5 | 2294.3934
| VAT calculation | [7 empty] | 226.3295
4 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -For stone masonary | 1 | 1.75 | 0.5 | 0.525 | 0.45937
|  | 1 | 1 | 0.5 | 1.025 | 0.5125
|  | 1 | 1 | 0.25 | 0.875 | 0.21875
|  | 1 | 2.98 | 0.5 | 0.55 | 0.8195
|  | 1 | 2.4 | 0.5 | 0.675 | 0.81
| Sub-total |  |  |  |  | 2.8201 | m3 | 9709.43 | 27381.8063
| VAT calculation | [7 empty] | 1986.4808
5 | Providing and laying , fitting and placing HYSD bar reinforcement in sub-structure complete as per Drawing and Technical Specifications | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For road | 25 | 6.7815 | 0.61728 | 104.6523 | 0.10465
|  | 42 | 3.886 | 0.61728 | 100.7484 | 0.10075
| Sub-total |  |  |  |  | 0.2054 | MT | 124140 | 25498.445
| VAT calculation | [7 empty] | 2962.8643
6 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 20 |  |  |  |  | Area of scalene triangle
| -for road | 1 | 3.2 | 2.2 | 4.2 | 3.4613
|  | 1 | 4.2 | 4.5 | 4.17 | 7.9394
|  | 1 | 4.5 | 4.5 | 2.9 | 6.177
|  | 1 | 4.5 | 4.35 | 4.23 | 8.2155
|  | 1 | 4.35 | 1.42 | 2.95 | 0.42513
|  | 1 | 1.42 | 2.9 | 2.5 | 1.7746
| Sub-total |  |  |  |  | 27.9929 | m3 | 11588.17 | 324387.0053
| VAT calculation | [7 empty] | 32836.0996
7 | Gabion Structure for Retaining Earth,Providing and laying Gabion structure for retaining earth with diaphragm including rolling, cutting, weaving, placing, laying sides and diaphragms with binding wire and filling boulders all complete as per drawing and technical specification Mesh wire- 10 Swg(0.0615 kg/m), Selvedge Wire 8 Swg ( 0.1057 kg/m), binding wire 12 Swg (0.0409 kg/m) Hexagonal mesh Type 100 mm X 120 mm,, Box size 3 X 1 X 1 m ( 6 sqm)
| -gabion wall | 1 | 3 | 1 | 1 | 3
| Sub-total |  |  |  |  | 3 | m3 | 6152.23 | 18456.69
| VAT calculation | [7 empty] | 1741.8895
8 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications.
| -gabion wall | 1 | 3 |  | 2 | 6
|  | 1 | 3 |  | 1 | 3
| Sub-total |  |  |  |  | 9 | sqm | 161.42 | 1452.78
| VAT calculation | [7 empty] | 176.904
9 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
7.8744
| Grand Total | [7 empty] | 577040.3554
| Total Estimated | 577040.3554 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 32.9266
| User Contribution | 387040.3554 |  | 67.0734 | [8 empty] | 3.2 | 10.4987
| Contingencies | 6000 |  | 3 | [8 empty] | 2.2 | 7.2178
| Maintanince | 4000 |  | 2 | [8 empty] | 4.2 | 13.7795
[13 empty] | 4.2 | 13.7795
[13 empty] | 4.5 | 14.7638
[13 empty] | 4.17 | 13.6811
[13 empty] | 4.5 | 14.7638
[13 empty] | 4.5 | 14.7638
[13 empty] | 2.9 | 9.5144
[13 empty] | 4.5 | 14.7638
[13 empty] | 4.35 | 14.2717
[13 empty] | 4.23 | 13.878
[13 empty] | 4.35 | 14.2717
[13 empty] | 1.42 | 4.6588
[13 empty] | 2.95 | 9.6785
[13 empty] | 1.42 | 4.6588
[13 empty] | 2.9 | 9.5144
[13 empty] | 2.5 | 8.2021