## field (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- फ्रेंश कृषि तथा पशुपालन | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date: 2082/02/05
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness | 3 | 2.53 | 1.83 | 13.8897 | 13.8897
|  | 1 | 0.55877 | 1.83 | 1.0226 | 1.0226
|  | 3 | 0.6619 | 1.83 | 3.6338 | 3.6338
|  | 3 | 3.0479 | 1.83 | 16.7327 | 16.7327
|  | 3 | 2.2859 | 1.83 | 12.5495 | 12.5495
|  | 3 | 2.1335 | 1.83 | 11.7129 | 11.7129
|  | 2 | 4.5 | 1.83 | 16.47 | 16.47
| sub-total |  |  |  |  | 76.0112 | Kg | 181.17 | 13770.9525
| -VAT 13% for materials | [7 empty] | 976.3653
2 | )=@$ dL=dL= afSnf] ;L=hL=cfO{= 5fgf 5fpg] sfd
|  | 1 | 4 | 2.1335 |  | 8.534 | [5 empty] | 20 | 4.5
| sub-total |  |  |  |  | 8.534 | sqm | 249.75 | 2131.3624
| -VAT 13% for materials | [7 empty] | 0
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -for passage flooring | 1 | 4.8766 | 3.0479 | 0.15 | 2.2295
| sub-total |  |  |  |  | 2.2295 | cum | 663.31 | 1478.82
4 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf
| -for passage flooring | 1 | 4 | 1.5 | 0.15 | 0.9
| sub-total |  |  |  |  | 0.9 | sqm | 4473.15 | 4025.835
| -VAT 13% for materials | [7 empty] | 361.8986 |  | 4434 | #REF! | #REF!
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| ;-for footing | 1 | 3.3526 | 2.5145 | 0.05 | 0.42151
|  | 1 | 4.7 | 2.58 | 0.1 | 1.2126
|  | 1 | 4.8766 | 2.5 | 0.1 | 1.2191
| sub-total |  |  |  |  | 2.8532 | cum | 12983.1 | 37043.99
| -VAT 13% for materials | [7 empty] | 2996.3495
6 | Information board | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 63285.5733
| Total Estimated | 63285.5733 |  | 100
| Budget allocated | 60000
| Municipal payment | 30000 |  | 47.4042
| User Contribution | 33285.5733 |  | 52.5958
| Contingencies | 1800 |  | 3
| Maintanince | 1200 |  | 2

## as per mistry (2)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- इन्द्रायणी एग्रो फर्म प्रा. लि . | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness | 3 | 2.53 | 1.83 | 13.8897 | 13.8897
|  | 1 | 0.55877 | 1.83 | 1.0226 | 1.0226
|  | 3 | 0.6619 | 1.83 | 3.6338 | 3.6338
|  | 3 | 3.0479 | 1.83 | 16.7327 | 16.7327
|  | 3 | 2.2859 | 1.83 | 12.5495 | 12.5495
|  | 3 | 2.1335 | 1.83 | 11.7129 | 11.7129
|  | 2 | 4.5 | 1.83 | 16.47 | 16.47
| sub-total |  |  |  |  | 76.0112 | Kg | 181.17 | 13770.9525
| -VAT 13% for materials | [7 empty] | 976.3653
2 | ;L=hL=cfO{= 5fgf 5fpg] sfd
|  | 1 | 4 | 2.2859 |  | 9.1436 | [5 empty] | 20 | 4.5
| sub-total |  |  |  |  | 9.1436 | sqm | 249.75 | 2283.6026
| -VAT 13% for materials | [7 empty] | 0
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -for passage flooring | 1 | 4.5 | 3.0479 | 0.15 | 2.0573
| sub-total |  |  |  |  | 2.0573 | cum | 663.31 | 1364.6274
4 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf
| -for passage flooring | 1 | 4 | 1.5 | 0.15 | 0.9
| sub-total |  |  |  |  | 0.9 | sqm | 4473.15 | 4025.835
| -VAT 13% for materials | [7 empty] | 361.8986 |  | 4434 | #REF! | #REF!
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| ;-for footing | 1 | 3 | 2.5 | 0.05 | 0.375
|  | 1 | 4.5 | 2.5 | 0.1 | 1.125
|  | 1 | 4.5 | 2.5 | 0.1 | 1.125
| sub-total |  |  |  |  | 2.625 | cum | 12983.1 | 34080.6375
| -VAT 13% for materials | [7 empty] | 2756.655
6 | Information board | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 60120.5739
| Total Estimated | 60120.5739
| Total Estimated | 60120.5739 |  | 100
| Budget allocated | 60000
| Municipal payment | 30000 |  | 49.8997
| User Contribution | 30120.5739 |  | 50.1003
| Contingencies | 1800 |  | 3
| Maintanince | 1200 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 60120.5739 |  |  |  |  | Total Valuated Amount : |  | 63359.6049
Work Started : | [7 empty] | Work Finished:
Project:- इन्द्रायणी एग्रो फर्म प्रा. लि . | [7 empty] | F.Y:2081/2082
Location:- Shankharapur Municipality 9 | [7 empty] | Date:
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | Kg | 76.0112 | 181.17 | 13770.9525 | 91.2737 | 181.17 | 16536.064 | 2765.1115 |  |  | 17213.6906
| -VAT 13% for materials |  |  |  | 976.3653 |  |  | 1172.4127 | 196.0474 |  |  | 1220.4566
2 | ;L=hL=cfO{= 5fgf 5fpg] sfd | sqm | 9.1436 | 249.75 | 2283.6026 | 18.1143 | 249.75 | 4524.0526 | 2240.4501 |  |  | 2854.5032
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | cum | 2.0573 | 663.31 | 1364.6274 | 2.0573 | 663.31 | 1364.6274 | 0 |  |  | 1705.7843
4 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf | sqm | 0.9 | 4473.15 | 4025.835 | 0.6 | 4473.15 | 2683.89 | -1341.945 |  |  | 5032.2937
| -VAT 13% for materials |  |  |  | 361.8986 |  |  | 241.2657 | -120.6328 |  |  | 452.3732
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_ | cum | 2.625 | 12983.1 | 34080.6375 | 2.625 | 12983.1 | 34080.6375 | 0 |  |  | 42600.7969
| -VAT 13% for materials |  |  |  | 2756.655 |  |  | 2756.655 | 0 |  |  | 3445.8188
6 | Information board | no. | 1 | 500 | 500 | 0 | 500 | 0 | -500 |  |  | 625
| Total |  |  |  | 60120.5739 |  |  | 63359.6049 | 3239.0311
[10 empty] | 1070 | 70.2278 | 75143.7929

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- इन्द्रायणी एग्रो फर्म प्रा. लि . | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness | 3 | 2.53 | 1.83 | 13.8897 | 13.8897
|  | 1 | 0.55877 | 1.83 | 1.0226 | 1.0226
|  | 3 | 0.63 | 1.83 | 3.4587 | 3.4587
|  | 3 | 3.0479 | 1.83 | 16.7327 | 16.7327
|  | 3 | 2.2859 | 1.83 | 12.5495 | 12.5495
|  | 3 | 5.029 | 1.83 | 27.609 | 27.609
|  | 2 | 2.4892 | 1.83 | 9.1104 | 9.1104
| -inclined member | 3 | 0.81286 | 2.83 | 6.9012 | 6.9012
| sub-total |  |  |  |  | 91.2737 | Kg | 181.17 | 16536.064
| -VAT 13% for materials | [7 empty] | 1172.4127
2 | ;L=hL=cfO{= 5fgf 5fpg] sfd
|  | 1 | 4.9528 | 3.6574 |  | 18.1143 | [5 empty] | 24.7638 | 4.5
| sub-total |  |  |  |  | 18.1143 | sqm | 249.75 | 4524.0526
| -VAT 13% for materials | [7 empty] | 0
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -for passage flooring | 1 | 4.5 | 3.0479 | 0.15 | 2.0573
| sub-total |  |  |  |  | 2.0573 | cum | 663.31 | 1364.6274
4 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf
| -for passage flooring | 1 | 4 | 1.5 | 0.1 | 0.6
| sub-total |  |  |  |  | 0.6 | cum | 4473.15 | 2683.89
| -VAT 13% for materials | [7 empty] | 241.2657 |  | 4434 | #REF! | #REF!
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| ;-for footing | 1 | 3 | 2.5 | 0.05 | 0.375
|  | 1 | 4.5 | 2.5 | 0.1 | 1.125 |  |  |  |  | 4.8766 | 8.4585
|  | 1 | 4.5 | 2.5 | 0.1 | 1.125 |  |  |  |  | 4.7242 | 2.5907
| sub-total |  |  |  |  | 2.625 | cum | 12983.1 | 34080.6375
| -VAT 13% for materials | [7 empty] | 2756.655
6 | Information board | 0 |  |  |  | 0 | no. | 500 | 0
| Grand Total | [7 empty] | 63359.6049
| Total Valuated | 63359.6049
| Total Estimated | 63359.6049 |  | 100
| Budget allocated | 60000
| Municipal payment | 30000 |  | 47.3488
| User Contribution | 33359.6049 |  | 52.6512
| Contingencies | 1800 |  | 3
| Maintanince | 1200 |  | 2

## M
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- इन्द्रायणी एग्रो फर्म प्रा. लि . | [9 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [9 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness | 3 | 2.53 | 1.83 | 13.8897 | 13.8897
|  | 1 | 0.55877 | 1.83 | 1.0226 | 1.0226
|  | 3 | 0.63 | 1.83 | 3.4587 | 3.4587
|  | 3 | 3.0479 | 1.83 | 16.7327 | 16.7327
|  | 3 | 2.2859 | 1.83 | 12.5495 | 12.5495
|  | 3 | 5.029 | 1.83 | 27.609 | 27.609
|  | 2 | 2.4892 | 1.83 | 9.1104 | 9.1104
| -inclined member | 3 | 0.81286 | 2.83 | 6.9012 | 6.9012
| sub-total |  |  |  |  | 91.2737 | Kg | 181.17 | 16536.064
| -VAT 13% for materials | [7 empty] | 1172.4127
2 | ;L=hL=cfO{= 5fgf 5fpg] sfd
|  | 1 | 4.9528 | 3.6574 |  | 18.1143 | [5 empty] | 24.7638 | 4.5
| sub-total |  |  |  |  | 18.1143 | sqm | 249.75 | 4524.0526
| -VAT 13% for materials | [7 empty] | 0
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -for passage flooring | 1 | 4.5 | 3.0479 | 0.15 | 2.0573
| sub-total |  |  |  |  | 2.0573 | cum | 663.31 | 1364.6274
4 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf
| -for passage flooring | 1 | 4 | 1.5 | 0.1 | 0.6
| sub-total |  |  |  |  | 0.6 | cum | 4473.15 | 2683.89
| -VAT 13% for materials | [7 empty] | 241.2657 |  | 4434 | #REF! | #REF!
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| ;-for footing | 1 | 3 | 2.5 | 0.05 | 0.375
|  | 1 | 4.5 | 2.5 | 0.1 | 1.125 |  |  |  |  | 4.8766 | 8.4585
|  | 1 | 4.5 | 2.5 | 0.1 | 1.125 |  |  |  |  | 4.7242 | 2.5907
| sub-total |  |  |  |  | 2.625 | cum | 12983.1 | 34080.6375
| -VAT 13% for materials | [7 empty] | 2756.655
6 | Information board | 0 |  |  |  | 0 | no. | 500 | 0
| Grand Total | [7 empty] | 63359.6049
| Total Valuated | 63359.6049
| Total Estimated | 63359.6049 |  | 100
| Budget allocated | 60000
| Municipal payment | 30000 |  | 47.3488
| User Contribution | 33359.6049 |  | 52.6512
| Contingencies | 1800 |  | 3
| Maintanince | 1200 |  | 2

## Sheet1
#REF! | dfn;fdfg pknAw u/L )=१७ dL=dL= afSnf] ;L=hL=cfO{= zL6 -h:tf kftfsf]_ 5fgf 5fpg] sfd k'/f .
F1 | b/ ljZn]if0fsf] nflu !) j=ld= lnOPsf]
| ;¦f]t ;fwg | tx÷lsl;d | kl/df0f | PsfO{ | b/ k¦lt PsfO{ | /sd | k¦To]s ;¦f]t ;fwgsf] hDdf
| >lds | s_ l;kfn' | 1.1 | hjfg | 1225 | 1347.5
|  | v_ HofdL | 1.25 | hjfg | 920 | 1150 | 2497.5
| lgdf{0f ;fdu¦L | CGI kftf #) u]h (0.१७mm) | 12 | j=dL= | 313.4529 | 3761.43
|  | * dL=dL= jf]N6 g6 | 30 | uf]6f | 34.13 | 1023.9
|  | h] x's | 25 | uf]6f | 13.9286 | 348.21
|  | lj6'ldg jfz/ | 55 | uf]6f | 3 | 165 | 0
[5 empty] | jf:tljs b//]6 |  | 2497.5
| b/ k¦lt j=dL=sf] |  |  |  | !%Ü 7]s]bf/ cf]e/x]8 |  | 374.62
| 2872.12 | ?= | 287.21 | k}= | hDdf b/ /]6 |  | 2872.12
10
gf]6 M !=)) j08n h:tf nDafO{{ &@Ú–)Æ / rf}8fO{ @Ú–&=%Æ dfg]sf] . -&@Ú x @Ú–&=%=+ !&=%^ j=dL=_
=