## new (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- कुर्थली सामुदायिक ट्रस्ट निर्माण | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 1.8mm thickness for vertical post | 12 | 4.5718 | 3.97 | 217.7995 | 217.7995
| -MS square pipe of 2"*2" of 1.8mm thickness for horizontal member | 4 | 10.0579 | 2.72 | 109.4301 | 109.4301
|  | 2 | 12.1914 | 2.72 | 66.3212 | 66.3212
| -MS square pipe of 2"*2" of 1.8mm thickness for inclined member | 8 | 4.8766 | 2.72 | 106.114 | 106.114
| -MS square pipe of 2"*2" of 1.6mm thickness for king post member | 4 | 1.0667 | 2.43 | 10.3688 | 10.3688
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for diagnol member | 2 | 1.1938 | 1.83 | 4.3695 | 4.3695
|  | 2 | 1.0667 | 1.83 | 3.9043 | 3.9043
|  | 2 | 0.96617 | 1.83 | 3.5362 | 3.5362
|  | 2 | 0.91436 | 1.83 | 3.3465 | 3.3465
| -MS square pipe of 50mm * 50mm of 2.6mm thickness for vertical member | 2 | 0.81286 | 1.83 | 2.9751 | 2.9751
|  | 2 | 0.60957 | 1.83 | 2.231 | 2.231
|  | 2 | 0.40628 | 1.83 | 1.487 | 1.487
|  | 2 | 0.20319 | 1.83 | 0.74368 | 0.74368
| -MS square pipe of 2"*2" of 1.8mm thickness for purlins | 10 | 9.6007 | 2.72 | 261.1399 | 261.1399
| sub-total |  |  |  |  | 793.7667 | Kg | 181.17 | 143806.7063
| -VAT 13% for materials | [7 empty] | 10195.9454
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
|  | 2 | 4.8766 | 9.6007 |  | 93.6371
| sub-total |  |  |  |  | 93.6371 | sqm | 1070.9 | 100275.9973
| -VAT 13% for materials | [7 empty] | 10453.5728
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| ;-for footing | 12 | 0.9 | 0.9 | 0.91436 | 8.8875
| sub-total |  |  |  |  | 8.8875 | cum | 663.31 | 5895.1904
3 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf
| ;-for footing | 12 | 0.75 | 0.75 | 0.15 | 1.0125
| sub-total |  |  |  |  | 1.0125 | cum | 4473.15 | 4529.0644
| -VAT 13% for materials | [7 empty] | 407.1359
3 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| ;-for footing | 12 | 0.75 | 0.75 | 0.05 | 0.3375
| sub-total |  |  |  |  | 0.3375 | cum | 12983.1 | 4381.7963
| -VAT 13% for materials | [7 empty] | 354.4271
3 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| ;-for footing | 12 | 0.6 | 0.6 | 0.6 | 2.592
| sub-total |  |  |  |  | 2.592 | cum | 13568.9 | 35170.5888
| -VAT 13% for materials | [7 empty] | 3209.2744
3 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
4 | Information board | 1 |  |  |  | 1 | PS | 500 | 500
| Grand Total | [7 empty] | 324179.6989
| Total Estimated | 324179.6989 |  | 100
| Budget allocated | 400000
| Municipal payment | 380000 |  | 117.2189
| User Contribution | -55820.3011 |  | -17.2189
| Contingencies | 12000 |  | 3
| Maintanince | 8000 |  | 2

## as per mistry (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- कुर्थली सामुदायिक ट्रस्ट निर्माण | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 1.8mm thickness for vertical post | 15 | 5.1813 | 3.97 | 308.5492 | 308.5492
| -MS square pipe of 2"*2" of 1.8mm thickness for horizontal member | 5 | 10.0579 | 2.72 | 136.7876 | 136.7876
| -MS square pipe of 2"*2" of 1.8mm thickness for inclined member | 10 | 4.9781 | 2.72 | 135.4031 | 135.4031
| -MS square pipe of 2"*2" of 1.6mm thickness for king post member | 5 | 1.0667 | 2.43 | 12.961 | 12.961
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for diagnol member | 10 | 1.2191 | 1.83 | 22.3103 | 22.3103
|  | 10 | 1.092 | 1.83 | 19.9844 | 19.9844
|  | 10 | 0.99055 | 1.83 | 18.1271 | 18.1271
|  | 10 | 0.93965 | 1.83 | 17.1956 | 17.1956
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for vertical member | 10 | 0.81286 | 1.83 | 14.8754 | 14.8754
|  | 10 | 0.60957 | 1.83 | 11.1551 | 11.1551
|  | 10 | 0.40628 | 1.83 | 7.4349 | 7.4349
|  | 10 | 0.20319 | 1.83 | 3.7184 | 3.7184
| -MS square pipe of 2"*2" of 1.8mm thickness for purlins | 12 | 13.4105 | 2.72 | 437.7202 | 437.7202
| sub-total |  |  |  |  | 1146.2223 | Kg | 181.17 | 207661.096
| -VAT 13% for materials | [7 empty] | 14723.2437
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
|  | 2 | 4.9781 | 13.4105 |  | 133.5169
| sub-total |  |  |  |  | 133.5169 | sqm | 1070.9 | 142983.2262
| -VAT 13% for materials | [7 empty] | 14905.7163
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| ;-for footing | 15 | 0.45 | 0.45 | 0.88997 | 2.7033
| sub-total |  |  |  |  | 2.7033 | cum | 663.31 | 1793.1204
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| ;-for footing | 15 | 0.45 | 0.45 |  | 3.0375
| -for flooring | 1 | 12.1914 | 9.1436 |  | 111.4728
| sub-total |  |  |  |  | 114.5103 | sqm | 1014.97 | 116224.4867
| -VAT 13% for materials | [7 empty] | 12827.8525
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| ;-for footing | 15 | 0.45 | 0.45 | 0.075 | 0.22781
| sub-total |  |  |  |  | 0.22781 | cum | 12983.1 | 2957.7125
| -VAT 13% for materials | [7 empty] | 239.2383
6 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -for footing | 15 | 0.45 | 0.45 | 0.75 | 2.2781
|  | 15 | 0.3 | 0.3 | 0.45 | 0.6075
| -for flooring | 1 | 12.1914 | 9.1436 | 0.075 | 8.3605
| sub-total |  |  |  |  | 11.2461 | cum | 13568.9 | 152596.9702
| -VAT 13% for materials | [7 empty] | 13924.2922
7 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for footing | 8 | 4.2417 | 0.23 | 0.3 | 2.3414
|  | 4 | 2.7178 | 0.23 | 0.3 | 0.7501
| -wall | 2 | 9.1436 | 0.23 | 0.9 | 3.7854
|  | 2 | 11.7342 | 0.23 | 0.9 | 4.858
| sub-total |  |  |  |  | 11.7349 | cum | 14362.76 | 168545.8548
| -VAT 13% for materials | [7 empty] | 15730.9691
8 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 4 | 9.1436 |  | 0.9 | 32.9168
|  | 4 | 11.7342 |  | 0.9 | 42.2432
| sub-total |  |  |  |  | 75.16 | sqm | 405.86 | 30504.4425
| -VAT 13% for materials | [7 empty] | 1091.0272
9 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
10 | Information board | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 902209.2486
| Total Estimated | 902209.2486 |  | 100
| Budget allocated | 400000
| Municipal payment | 380000 |  | 42.1188
| User Contribution | 522209.2486 |  | 57.8812
| Contingencies | 12000 |  | 3
| Maintanince | 8000 |  | 2

## final (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- कुर्थली सामुदायिक ट्रस्ट निर्माण | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 1.8mm thickness for vertical post | 12 | 5.1813 | 3.97 | 246.8394 | 246.8394
| -MS square pipe of 2"*2" of 1.8mm thickness for horizontal member | 4 | 10.0579 | 2.72 | 109.4301 | 109.4301
| -MS square pipe of 2"*2" of 1.8mm thickness for inclined member | 8 | 4.9781 | 2.72 | 108.3225 | 108.3225
| -MS square pipe of 2"*2" of 1.6mm thickness for king post member | 4 | 1.0667 | 2.43 | 10.3688 | 10.3688
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for diagnol member | 8 | 1.2191 | 1.83 | 17.8482 | 17.8482
|  | 8 | 1.092 | 1.83 | 15.9875 | 15.9875
|  | 8 | 0.99055 | 1.83 | 14.5017 | 14.5017
|  | 8 | 0.93965 | 1.83 | 13.7565 | 13.7565
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for vertical member | 8 | 0.81286 | 1.83 | 11.9003 | 11.9003
|  | 8 | 0.60957 | 1.83 | 8.9241 | 8.9241
|  | 8 | 0.40628 | 1.83 | 5.9479 | 5.9479
|  | 8 | 0.20319 | 1.83 | 2.9747 | 2.9747
| -MS square pipe of 2"*2" of 1.6mm thickness for purlins | 12 | 13.4105 | 2.43 | 391.0515 | 391.0515
| sub-total |  |  |  |  | 957.8532 | Kg | 181.17 | 173534.2626
| -VAT 13% for materials | [7 empty] | 12303.6394
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
|  | 2 | 4.9284 | 12.6486 |  | 124.6739
| sub-total |  |  |  |  | 124.6739 | sqm | 1070.9 | 133513.3122
| -VAT 13% for materials | [7 empty] | 13918.4966
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -for footing | 12 | 0.45 | 0.45 | 0.88997 | 2.1626
| sub-total |  |  |  |  | 2.1626 | cum | 663.31 | 1434.4963
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing | 12 | 0.45 | 0.45 |  | 2.43
| -for tie beam | 0 | 3.4044 | 0.23 |  | 0
|  | 0 | 3.5812 | 0.23 |  | 0
| sub-total |  |  |  |  | 2.43 | sqm | 1014.97 | 2466.3771
| -VAT 13% for materials | [7 empty] | 272.2173
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for footing | 12 | 0.45 | 0.45 | 0.075 | 0.18225
| -for tie beam | 0 | 3.4044 | 0.23 | 0.05 | 0
|  | 0 | 3.5812 | 0.23 | 0.05 | 0
| sub-total |  |  |  |  | 0.18225 | cum | 12983.1 | 2366.17
| -VAT 13% for materials | [7 empty] | 191.3906
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | Nos. | Length (m) | Unit length (Kg/m) | Total Weight (Kg) | Total Weight (MT)
| -for tie beam | 4 | 40.833 | 0.88889 | 145.184 | 0.14518
| -stirrups | 143 | 0.81439 | 0.39506 | 46.0078 | 0.046008
| -for tie beam | 4 | 30.833 | 0.88889 | 109.6284 | 0.10963
| -stirrups | 95 | 0.81439 | 0.39506 | 30.5646 | 0.030565
| sub-total |  |  |  |  | 0 | MT | 131940 | 0
| -VAT 13% for materials | [7 empty] | 0
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for footing | 12 | 1.8 |  | 0.45 | 9.72
| -for column | 12 | 1.2 |  | 0.3 | 4.32
| -for tie beam | 0 | 3.8098 |  | 0.46 | 0
|  | 0 | 3.6321 |  | 0.46 | 0
|  | 0 | 3.7336 |  | 0.46 | 0
| sub-total |  |  |  |  | 14.04 | sqm | 915.42 | 12852.4968
| -VAT 13% for materials | [7 empty] | 854.7023
8 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -for footing | 12 | 0.45 | 0.45 | 0.45 | 1.0935
| -for column | 12 | 0.3 | 0.3 | 0.75 | 0.81
| -tie beam | 0 | 12.1914 | 0.23 | 0.23 | 0
|  | 0 | 9.1436 | 0.23 | 0.23 | 0
| -deduction for overlap part | 0 | 0.076196 | 0.23 | 0.23 | 0
| sub-total |  |  |  |  | 1.9035 | cum | 13568.9 | 25828.4011
| -VAT 13% for materials | [7 empty] | 2356.8109
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for footing | 4 | 3.8098 | 0.23 | 0.45 | 1.5773
|  | 4 | 3.6321 | 0.23 | 0.45 | 1.5037
|  | 2 | 3.7336 | 0.23 | 0.45 | 0.77286
| sub-total |  |  |  |  | 3.8538 | cum | 14362.76 | 55351.5118
| -VAT 13% for materials | [7 empty] | 5166.1486
10 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
11 | Information board | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 448410.4337
| Total Estimated | 448410.4337 |  | 100
| Budget allocated | 400000
| Municipal payment | 380000 |  | 84.7438
| User Contribution | 68410.4337 |  | 15.2562
| Contingencies | 12000 |  | 3
| Maintanince | 8000 |  | 2

## 400000 final (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- कुर्थली सामुदायिक ट्रस्ट निर्माण | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 1.8mm thickness for vertical post | 9 | 5.1813 | 3.97 | 185.1295 | 185.1295
| -MS square pipe of 2"*2" of 1.8mm thickness for horizontal member | 3 | 10.0579 | 2.72 | 82.0725 | 82.0725
| -MS square pipe of 2"*2" of 1.8mm thickness for inclined member | 6 | 4.9781 | 2.72 | 81.2419 | 81.2419
| -MS square pipe of 2"*2" of 1.6mm thickness for king post member | 3 | 1.0667 | 2.43 | 7.7766 | 7.7766
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for diagnol member | 6 | 1.2191 | 1.83 | 13.3862 | 13.3862
|  | 6 | 1.092 | 1.83 | 11.9907 | 11.9907
|  | 6 | 0.99055 | 1.83 | 10.8763 | 10.8763
|  | 6 | 0.93965 | 1.83 | 10.3174 | 10.3174
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for vertical member | 6 | 0.81286 | 1.83 | 8.9252 | 8.9252
|  | 6 | 0.60957 | 1.83 | 6.6931 | 6.6931
|  | 6 | 0.40628 | 1.83 | 4.4609 | 4.4609
|  | 6 | 0.20319 | 1.83 | 2.231 | 2.231
| -MS square pipe of 2"*2" of 1.6mm thickness for purlins | 12 | 13.4105 | 2.43 | 391.0515 | 391.0515
| sub-total |  |  |  |  | 816.1528 | Kg | 181.17 | 147862.3974
| -VAT 13% for materials | [7 empty] | 10483.4953
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
|  | 2 | 4.9284 | 9.6007 |  | 94.632
| sub-total |  |  |  |  | 94.632 | sqm | 1070.9 | 101341.4298
| -VAT 13% for materials | [7 empty] | 10564.642
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -for footing | 12 | 0.45 | 0.45 | 0.88997 | 2.1626
| sub-total |  |  |  |  | 2.1626 | cum | 663.31 | 1434.4963
4 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -for flooring | 1 | 8.6611 | 7.1372 | 0.15 | 9.2723
| -for tie beam | 0 | 3.4044 | 0.23 |  | 0
|  | 0 | 3.5812 | 0.23 |  | 0
| sub-total |  |  |  |  | 9.2723 | sqm | 4434.52 | 41118.2762
| -VAT 13% for materials | [7 empty] | 3572.2307
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for footing | 1 | 8.6611 | 7.1372 | 0.075 | 4.6362
| -for tie beam | 0 | 3.4044 | 0.23 | 0.05 | 0
|  | 0 | 3.5812 | 0.23 | 0.05 | 0
| sub-total |  |  |  |  | 4.6362 | cum | 12983.1 | 60191.7109
| -VAT 13% for materials | [7 empty] | 4868.6819
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | Nos. | Length (m) | Unit length (Kg/m) | Total Weight (Kg) | Total Weight (MT)
| -for tie beam | 4 | 40.833 | 0.88889 | 145.184 | 0.14518
| -stirrups | 143 | 0.81439 | 0.39506 | 46.0078 | 0.046008
| -for tie beam | 4 | 30.833 | 0.88889 | 109.6284 | 0.10963
| -stirrups | 95 | 0.81439 | 0.39506 | 30.5646 | 0.030565
| sub-total |  |  |  |  | 0 | MT | 131940 | 0
| -VAT 13% for materials | [7 empty] | 0
6 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for footing | 12 | 1.8 |  | 0.45 | 9.72
| -for column | 12 | 1.2 |  | 0.3 | 4.32
| -for tie beam | 0 | 3.8098 |  | 0.46 | 0
|  | 0 | 3.6321 |  | 0.46 | 0
|  | 0 | 3.7336 |  | 0.46 | 0
| sub-total |  |  |  |  | 14.04 | sqm | 915.42 | 12852.4968
| -VAT 13% for materials | [7 empty] | 854.7023
7 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -for footing | 1 | 8.6611 | 7.1372 | 0.45 | 27.817
| -for column | 1 | 0.3 | 0.3 | 0.75 | 0.0675
| -tie beam | 0 | 12.1914 | 0.23 | 0.23 | 0
|  | 0 | 9.1436 | 0.23 | 0.23 | 0
| -deduction for overlap part | 0 | 0.076196 | 0.23 | 0.23 | 0
| sub-total |  |  |  |  | 27.8845 | cum | 13568.9 | 378361.3365
| -VAT 13% for materials | [7 empty] | 34525.0223
8 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for footing | 4 | 3.8098 | 0.23 | 0.5 | 1.7525
|  | 4 | 3.6321 | 0.23 | 0.5 | 1.6708
|  | 2 | 3.7336 | 0.23 | 0.5 | 0.85873
| sub-total |  |  |  |  | 4.282 | cum | 14362.76 | 61501.6798
| -VAT 13% for materials | [7 empty] | 5740.1651
9 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
10 | Information board | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 881272.7632
| Total Estimated | 881272.7632 |  | 100
| Budget allocated | 400000
| Municipal payment | 380000 |  | 43.1195
| User Contribution | 501272.7632 |  | 56.8805
| Contingencies | 12000 |  | 3
| Maintanince | 8000 |  | 2

## change estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- कुर्थली सामुदायिक ट्रस्ट निर्माण | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 1.6mm thickness for vertical post | 8 | 5.029 | 3.54 | 142.42 | 142.42
| -MS square pipe of 2"*2" of 1.6mm thickness for horizontal member | 3 | 9.1436 | 2.43 | 66.6565 | 66.6565
| -MS square pipe of 2"*2" of 1.6mm thickness for inclined member | 6 | 4.9528 | 2.43 | 72.2112 | 72.2112
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for diagnol member | 6 | 1.3968 | 1.83 | 15.3372 | 15.3372
|  | 6 | 1.271 | 1.83 | 13.9551 | 13.9551
|  | 6 | 1.1682 | 1.83 | 12.8273 | 12.8273
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for vertical member | 3 | 1.0667 | 1.83 | 5.8564 | 5.8564
|  | 6 | 0.81286 | 1.83 | 8.9252 | 8.9252
|  | 6 | 0.53337 | 1.83 | 5.8564 | 5.8564
|  | 6 | 0.33018 | 1.83 | 3.6254 | 3.6254
| -MS square pipe of 2"*2" of 1.6mm thickness for purlins | 14 | 8.6864 | 2.43 | 295.5105 | 295.5105 |  |  |  |  | 23.9167 |  | 28.9167
| sub-total |  |  |  |  | 643.1813 | Kg | 181.17 | 116525.1614
| -VAT 13% for materials | [7 empty] | 8261.6744
174
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
|  | 2 | 5.1813 | 8.6864 |  | 90.0143 | [5 empty] | 8.8896 | 7.5943
| sub-total |  |  |  |  | 90.0143 | sqm | 1070.9 | 96396.2712 |  |  | 8.8896
| -VAT 13% for materials | [7 empty] | 10049.1191
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] k'g]{ sfd
| -for footing | 8 | 0.45 | 0.45 | 0.9 | 1.458
| -for wall below plinth level | 2 | 7.6196 | 0.3 | 0.45 | 2.0573
|  | 2 | 8.6864 | 0.3 | 0.45 | 2.3453
| -deduction for footing | -8 | 0.45 | 0.45 | 0.45 | -0.729
| sub-total |  |  |  |  | 5.1316 | cum | 663.31 | 3403.8556
4 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod(without watering)
| -for earth filling work in flooring | 0.5 | 8.6864 | 7.1625 | 0.45 | 13.9985
| sub-total |  |  |  |  | 19.1302 | cum | 404.28 | 7733.942
5 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing | 8 | 0.45 | 0.45 |  | 1.62
| -for tie beam | 2 | 7.6196 | 0.23 |  | 3.505
|  | 2 | 8.6864 | 0.23 |  | 3.9957
| -deduction for footing | -8 | 0.45 | 0.23 |  | -0.828
| sub-total |  |  |  |  | 8.2928 | sqm | 1014.97 | 8416.9046
| -VAT 13% for materials | [7 empty] | 928.985
6 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -for flooring | 1 | 8.6864 | 7.1625 | 0.15 | 9.3324
| sub-total |  |  |  |  | 9.3324 | cum | 4434.52 | 41384.5406
| -VAT 13% for materials | [7 empty] | 3595.3629
7 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for footing | 8 | 0.45 | 0.45 | 0.05 | 0.081
| -flooring | 1 | 8.6864 | 7.1625 | 0.075 | 4.6662
| sub-total |  |  |  |  | 4.7472 | cum | 12983.1 | 61633.1178
| -VAT 13% for materials | [7 empty] | 4985.2719
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | Nos. | Length (m) | Unit length (Kg/m) | Total Weight (Kg) | Total Weight (MT)
| -for tie beam | 2 | 7.5181 | 0.39506 | 5.9403 | 0.0059403
| -stirrups | 48 | 0.2295 | 0.39506 | 4.3521 | 0.0043521
| -for tie beam | 2 | 9.0421 | 0.39506 | 7.1443 | 0.0071443
| -stirrups | 58 | 0.2295 | 0.39506 | 5.2587 | 0.0052587
| sub-total |  |  |  |  | 0.022695 | MT | 131940 | 2994.431
| -VAT 13% for materials | [7 empty] | 313.3327
9 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for column | 2 | 0.92 |  | 0.89515 | 1.6471
| sub-total |  |  |  |  | 1.6471 | sqm | 915.42 | 1507.7712
| -VAT 13% for materials | [7 empty] | 100.2681
10 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -for column | 2 | 0.23 | 0.23 | 0.45 | 0.04761
| -tie beam | 2 | 7.6196 | 0.23 | 0.1 | 0.3505
|  | 2 | 8.6864 | 0.23 | 0.1 | 0.39957
| sub-total |  |  |  |  | 0.79769 | cum | 13568.9 | 10823.7242
| -VAT 13% for materials | [7 empty] | 987.652
11 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -upto tie beam | 2 | 8.4325 | 0.23 | 0.75 | 2.9092
|  | 2 | 7.3657 | 0.23 | 0.75 | 2.5412
| deduction for post | -8 | 0.23 | 0.23 | 0.75 | -0.3174
| sub-total |  |  |  |  | 5.133 | cum | 14362.76 | 73723.9052 |  |  | 2874.4745
| -VAT 13% for materials | [7 empty] | 6880.9077
12 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 10000 | 10000
13 | Information board | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 471146.1987
| Total Valuated | 471146.1987 |  | 100
| Budget allocated | 400000
| Municipal payment | 380000 |  | 80.6544
| User Contribution | 91146.1987 |  | 19.3456
| Contingencies | 12000 |  | 3
| Maintanince | 8000 |  | 2
Note on F80: DELL: for taking ht of 3 ft there is deduction of 45"-36"

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 471146.1987 |  |  |  |  | Total Valuated Amount : |  | 481578.6451
Work Started : | [7 empty] | Work Finished:
Project:- राष्ट्रिय मा. बि. वाल निर्माण | [7 empty] | F.Y:2081/2082
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2082/02/03
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | Kg | 643.1813 | 181.17 | 116525.1614 | 599.3303 | 181.17 | 108580.6619 | -7944.4994 |  | 145656.4517
| -VAT 13% for materials |  |  |  | 8261.6744 |  |  | 7698.4066 | -563.2678 |  | 10327.0929
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd | sqm | 90.0143 | 1070.9 | 96396.2712 | 84.0458 | 1070.9 | 90004.6712 | -6391.6 |  | 120495.339
| -VAT 13% for materials |  |  |  | 10049.1191 |  |  | 9382.8075 | -666.3116 |  | 12561.3989
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] k'g]{ sfd | cum | 5.1316 | 663.31 | 3403.8556 | 3.655 | 663.31 | 2424.3807 | -979.475 |  | 4254.8195
4 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod(without watering) | cum | 19.1302 | 404.28 | 7733.942 | 13.9085 | 404.28 | 5622.9186 | -2111.0234 |  | 9667.4275
5 | ;'Vvf O{6f RofK6f] 5fKg] sfd | sqm | 8.2928 | 1014.97 | 8416.9046 | 8.2695 | 1014.97 | 8393.2828 | -23.6218 |  | 10521.1308
| -VAT 13% for materials |  |  |  | 928.985 |  |  | 926.3779 | -2.6072 |  | 1161.2313
6 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | cum | 9.3324 | 4434.52 | 41384.5406 | 9.2723 | 4434.52 | 41118.2762 | -266.2644 |  | 51730.6757
| -VAT 13% for materials |  |  |  | 3595.3629 |  |  | 3572.2307 | -23.1322 |  | 4494.2037
7 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_ | cum | 4.7472 | 12983.1 | 61633.1178 | 5.2295 | 12983.1 | 67895.5034 | 6262.3856 |  | 77041.3973
| -VAT 13% for materials |  |  |  | 4985.2719 |  |  | 5491.8128 | 506.5409 |  | 6231.5899
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | MT | 0.022695 | 131940 | 2994.431 | 0.028221 | 131940 | 3723.5404 | 729.1094 |  | 3743.0387
| -VAT 13% for materials |  |  |  | 313.3327 |  |  | 389.6256 | 76.2929 |  | 391.6659
9 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd | sqm | 1.6471 | 915.42 | 1507.7712 | 1.6471 | 915.42 | 1507.7712 | 0 |  | 1884.714
| -VAT 13% for materials |  |  |  | 100.2681 |  |  | 100.2681 | 0 |  | 125.3351
10 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_ | cum | 0.79769 | 13568.9 | 10823.7242 | 0.9823 | 13568.9 | 13328.6772 | 2504.9529 |  | 13529.6553
| -VAT 13% for materials |  |  |  | 987.652 |  |  | 1216.226 | 228.574 |  | 1234.565
11 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | cum | 5.133 | 14362.76 | 73723.9052 | 6.3491 | 14362.76 | 91190.1166 | 17466.2113 |  | 92154.8816
| -VAT 13% for materials |  |  |  | 6880.9077 |  |  | 8511.0898 | 1630.1821 |  | 8601.1347
12 | Provisional sum for unforseen works | PS | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 0 |  | 12500
13 | Information board | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0 |  | 625
| Total |  |  |  | 471146.1987 |  |  | 481578.6451 | 10432.4464

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- कुर्थली सामुदायिक ट्रस्ट निर्माण | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 1.6mm thickness for vertical post | 3 | 3.7559 | 3.54 | 39.8873 | 39.8873
|  | 2 | 3.9337 | 3.54 | 27.8507 | 27.8507
|  | 3 | 4.1116 | 3.54 | 43.6647 | 43.6647
| -MS square pipe of 2"*2" of 1.6mm thickness for horizontal member | 3 | 8.8896 | 2.43 | 64.8049 | 64.8049
| -MS square pipe of 2"*2" of 1.6mm thickness for inclined member | 6 | 4.7751 | 2.43 | 69.6205 | 69.6205
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for diagnol member | 6 | 1.2953 | 1.83 | 14.2228 | 14.2228
|  | 6 | 1.3472 | 1.83 | 14.7917 | 14.7917
|  | 6 | 1.473 | 1.83 | 16.1738 | 16.1738
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for vertical member | 6 | 0.86346 | 1.83 | 9.4807 | 9.4807
|  | 6 | 0.60957 | 1.83 | 6.6931 | 6.6931
|  | 6 | 0.40628 | 1.83 | 4.4609 | 4.4609
|  | 6 | 0.15239 | 1.83 | 1.6733 | 1.6733
| -MS square pipe of 2"*2" of 1.6mm thickness for purlins | 14 | 8.407 | 2.43 | 286.0058 | 286.0058 |  |  |  |  | 23.9167 |  | 28.9167
| sub-total |  |  |  |  | 599.3303 | Kg | 181.17 | 108580.6619
| -VAT 13% for materials | [7 empty] | 7698.4066
174
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
|  | 2 | 5.029 | 8.3562 |  | 84.0458 | [5 empty] | 8.8896 | 7.5943
| sub-total |  |  |  |  | 84.0458 | sqm | 1070.9 | 90004.6712 |  |  | 8.8896
| -VAT 13% for materials | [7 empty] | 9382.8075
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] k'g]{ sfd
| -for footing | 8 | 0.45 | 0.45 | 0.75 | 1.215
| -for wall below plinth level | 2 | 7.5943 | 0.3 | 0.3 | 1.367
|  | 2 | 8.6611 | 0.3 | 0.3 | 1.559
| -deduction for footing | -8 | 0.45 | 0.45 | 0.3 | -0.486
| sub-total |  |  |  |  | 3.655 | cum | 663.31 | 2424.3807
4 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod(without watering)
| -for earth filling work in flooring | 0.5 | 8.6611 | 7.1372 | 0.45 | 13.9085
| sub-total |  |  |  |  | 13.9085 | cum | 404.28 | 5622.9186
5 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing | 8 | 0.45 | 0.45 |  | 1.62
| -for tie beam | 2 | 8.6611 | 0.23 |  | 3.9841
|  | 2 | 7.5943 | 0.23 |  | 3.4934
| -deduction for footing | -8 | 0.45 | 0.23 |  | -0.828
| sub-total |  |  |  |  | 8.2695 | sqm | 1014.97 | 8393.2828
| -VAT 13% for materials | [7 empty] | 926.3779
7 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -for flooring | 1 | 8.6611 | 7.1372 | 0.15 | 9.2723
| sub-total |  |  |  |  | 9.2723 | cum | 4434.52 | 41118.2762
| -VAT 13% for materials | [7 empty] | 3572.2307
8 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for footing | 8 | 0.3 | 0.3 | 0.05 | 0.036
| -flooring | 1 | 9.1183 | 7.5943 | 0.075 | 5.1935
| sub-total |  |  |  |  | 5.2295 | cum | 12983.1 | 67895.5034
| -VAT 13% for materials | [7 empty] | 5491.8128
9 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | Nos. | Length (m) | Unit length (Kg/m) | Total Weight (Kg) | Total Weight (MT)
| -for tie beam | 2 | 7.2894 | 0.61728 | 8.9993 | 0.0089993
| -stirrups | 41 | 0.2295 | 0.39506 | 3.7174 | 0.0037174
| -for tie beam | 2 | 8.8134 | 0.61728 | 10.8807 | 0.010881
| -stirrups | 51 | 0.2295 | 0.39506 | 4.6241 | 0.0046241
| sub-total |  |  |  |  | 0.028221 | MT | 131940 | 3723.5404
| -VAT 13% for materials | [7 empty] | 389.6256
10 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for column | 2 | 0.92 |  | 0.89515 | 1.6471
| sub-total |  |  |  |  | 1.6471 | sqm | 915.42 | 1507.7712
| -VAT 13% for materials | [7 empty] | 100.2681
11 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -for column | 2 | 0.23 | 0.23 | 0.45 | 0.04761
| -tie beam | 2 | 8.6611 | 0.23 | 0.125 | 0.49801
|  | 2 | 7.5943 | 0.23 | 0.125 | 0.43667
| sub-total |  |  |  |  | 0.9823 | cum | 13568.9 | 13328.6772
| -VAT 13% for materials | [7 empty] | 1216.226
12 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for footing | 6 | 0.45 | 0.45 | 0.075 | 0.091125
| -upto tie beam | 2 | 8.4325 | 0.23 | 0.91436 | 3.5467
|  | 2 | 7.3657 | 0.23 | 0.81164 | 2.75
| deduction for post | -8 | 0.075 | 0.075 | 0.863 | -0.038835
| sub-total |  |  |  |  | 6.3491 | cum | 14362.76 | 91190.1166 |  |  | 3555.4772
| -VAT 13% for materials | [7 empty] | 8511.0898
13 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 10000 | 10000
14 | Information board | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 481578.6451
| Total Valuated | 481578.6451 |  | 100
| Budget allocated | 400000
| Municipal payment | 380000 |  | 78.9072
| User Contribution | 101578.6451 |  | 21.0928
| Contingencies | 12000 |  | 3
| Maintanince | 8000 |  | 2
Note on F83: DELL: for taking ht of 3 ft there is deduction of 45"-36"