## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- ६. नं. कृषि सडक | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2082/03/01
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -for road | 1 | 200 | 4 | 0.9 | 720
| Sub-total |  |  |  |  | 720 | sqm | 64.63 | 46533.6
| VAT calculation | [7 empty] | 5013.84
2 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 52047.44
| Total Estimated | 52047.44
| Budget allocated | 40000
| Municipal payment | 38000 |  | 73.0103
| User Contribution | 14047.44 |  | 26.9897
| Contingencies | 1200 |  | 3
| Maintanince | 800 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 52047.44 |  |  |  |  | Total Valuated Amount : |  | 45495.7689
Work Started : | [7 empty] | Work Finished:
Project:- ६. नं. कृषि सडक | [7 empty] | F.Y:2081/2082
Location:- Shankharapur Municipality 9 | [7 empty] | Date:
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | sqm | 720 | 64.63 | 46533.6 | 635.472 | 64.63 | 41070.5539 | -5463.0461
| VAT calculation |  |  |  | 5013.84 |  |  | 4425.215
2 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 0 | 500 | 0 | -500
| Total |  |  |  | 52047.44 |  |  | 45495.7689 | -6551.6711

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- ६. नं. कृषि सडक | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | [9 empty] | 0 | 4 | 0.15
| -for road | 0.5 | 7 | 4.5 | 0.825 | 12.9937 |  |  |  |  | 7 | 5 | 1.5
|  | 0.5 | 7 | 5.5 | 1.85 | 35.6125 |  |  |  |  | 7 | 6 | 2.2
|  | 0.5 | 7 | 4.8287 | 1.85 | 31.2659 |  |  |  |  | 7 | 3.6574 | 1.5
|  | 0.5 | 7 | 3.6574 | 1.5 | 19.2015 |  |  |  |  | 7 | 3.6574 | 1.5
|  | 0.5 | 7 | 4.1146 | 2 | 28.8022 |  |  |  |  | 7 | 4.5718 | 2.5
|  | 0.5 | 7 | 4.5718 | 2.25 | 36.0027 |  |  |  |  | 7 | 4.5718 | 2
|  | 0.5 | 7 | 4.5718 | 2 | 32.0024 |  |  |  |  | 7 | 4.5718 | 2
|  | 0.5 | 7 | 4.5718 | 2 | 32.0024 |  |  |  |  | 7 | 4.5718 | 2
|  | 0.5 | 7 | 4.5718 | 2 | 32.0024 |  |  |  |  | 7 | 4.5718 | 2
|  | 0.5 | 7 | 4.5718 | 2 | 32.0024 |  |  |  |  | 7 | 4.5718 | 2
|  | 0.5 | 7 | 4.5718 | 2 | 32.0024 |  |  |  |  | 7 | 4.5718 | 2
|  | 0.5 | 7 | 4.5718 | 2 | 32.0024 |  |  |  |  | 7 | 4.5718 | 2
|  | 0.5 | 7 | 4.5718 | 2 | 32.0024 |  |  |  |  | 7 | 4.5718 | 2
|  | 0.5 | 7 | 4.5718 | 2 | 32.0024 |  |  |  |  | 7 | 4.5718 | 2
|  | 0.5 | 7 | 4.5718 | 2 | 32.0024 |  |  |  |  | 7 | 4.5718 | 2
|  | 0.5 | 7 | 4.5718 | 2 | 32.0024 |  |  |  |  | 7 | 4.5718 | 2
|  | 0.5 | 7 | 5.3337 | 2 | 37.3362 |  |  |  |  | 7 | 6.0957 | 2
|  | 0.5 | 7 | 6.0957 | 2 | 42.6699 |  |  |  |  | 7 | 6.0957 | 2
|  | 0.5 | 7 | 5.3337 | 2 | 37.3362 |  |  |  |  | 7 | 4.5718 | 2
|  | 0.5 | 7 | 4.5718 | 1.15 | 18.4014 |  |  |  |  | 7 | 4.5718 | 0.3
|  | 0.5 | 7 | 4.5718 | 0.3 | 4.8004 |  |  |  |  | 7 | 4.5718 | 0.3
| -drain | 0.5 | 147 | 1 | 0.15 | 11.025
| Sub-total |  |  |  |  | 635.472 | sqm | 64.63 | 41070.5539
| VAT calculation | [7 empty] | 4425.215
2 | Information board (सुचना पाटि) | 0 |  |  |  | 0 | no. | 500 | 0
| Grand Total | [7 empty] | 45495.7689
| Total Valuated | 45495.7689
| Budget allocated | 40000
| Municipal payment | 38000 |  | 83.5243
| User Contribution | 7495.7689 |  | 16.4757
| Contingencies | 1200 |  | 3
| Maintanince | 800 |  | 2