## measurement sheet (2)
Shankharapur Municipality
Office of Municipal Executive
Bagmati Pradesh
Sankhu, Kathmandu
Detail Measurement Sheet
Project: | nai khola corridor marmat | [6 empty] | Fiscal Year:080/81
Location: Shankharapur 6 | [7 empty] | Date:2080/10/23
S.No. | Description of works | Nos | Length | Breadth | Height | Quantity | Unit | Remarks
1 | Site clearance work as per instruction of engineer all complete | 1 |  |  |  | 1 | ls
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| embankment | 1 | 41.5 | 0.82054 | 1.8 | 61.2943
[6 empty] | 61.2943 | m3 | [5 empty] | #REF! | #REF!
3 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance
|  | 4 | 40 | 0.38 | 106 | 424 | sack |  | 0.05 | 21.2 | m3
[6 empty] | 424 | sack | labour cost only
4 | Providing and laying Bamboo for the protection all complete | [10 empty] | 0.45718
| vertical post | 60 | 6 |  |  | 360 | ft
| horizontal post | 3 | 114.835 |  |  | 344.505 | ft
[6 empty] | 704.505 | ft
[6 empty] | 39.1392 | no
5 | Information Board | 1 |  |  |  | 1 | ls |  |  |  | 5.4861
6 | Miscellaneous | 1 |  |  |  | 1 | PS

## estimate
Shankharapur Municipality
Office of Municipal Executive
Bagmati Pradesh
Sankhu, Kathmandu
Detail Estimated Sheet
Project: | nai khola corridor marmat |  |  |  |  | Fiscal Year:080/81
Location: Shankharapur 6 | [5 empty] | Date:2080/10/23
S.No. | Description of works | Quantity | Unit | Rate | Amount | Remarks
1 | Site clearance work as per instruction of engineer all complete | 1 | ls
|  |  |  | 1000 | 1000
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
|  | 61.2943 | m3 | 62.02 | 3801.4697 |  |  | #REF! | #REF!
| VAT |  |  |  | 407.8418
3 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance
|  | 424 | sack | 90 | 38160 | labour cost only
4 | Providing and laying Bamboo for the protection all complete
|  | 39.1392 | no | 240 | 9393.4
| VAT |  |  |  | 1221.142
5 | Information Board | 1 | ls | 500 | 500
6 | Miscellaneous | 1 | PS | 2500 | 2500
| Total |  |  |  | 56983.8535 |  | 56983.854
| Total Estimated | 56983.8535 |  | 100
| Budget allocated | 50000
| Municipal Payment | 47500 |  | 83.3569
| User Contribution | 9483.8535 |  | 16.6431
| Contingencies 3% | 1500
| Maintenance 2% | 1000

## Sheet1
rate analysis
Analysis : | 100sack
Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance
Labour | unit | qty | rate | amount
unskilled | m/day | 10 | 900 | 9000
Materials
Empty sacks | No | 1 | 0 | 0
sewing thread | No | 0.75 | 0 | 0
|  |  | total | 9000
|  |  | Per sack | 90

## wcr1
Government of Nepal
Shankharapur Municipality Office
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 56983.8535 | [5 empty] | Total Valuated Amount : | 58896.2415
Work Started : | [7 empty] | Work Finished:
Project: | nai khola corridor marmat | [6 empty] | Fiscal Year:08/81
Location: Shankharapur 6 | [7 empty] | Date:2081/02/29
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Site clearance work as per instruction of engineer all complete | ls | 1 | 1000 | 1000 | 1 | 1000 | 1000 | 0
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | m3 | 61.2943 | 62.02 | 3801.4697 | 66.0622 | 62.02 | 4097.1762 | 295.7064
[5 empty] | 407.8418 |  |  | 439.5667
3 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance | sack | 424 | 90 | 38160 | 432 | 90 | 38880 | 720
4 | Providing and laying Bamboo for the protection all complete | no | 39.1392 | 240 | 9393.4 | 43.5822 | 240 | 10459.7333 | 1066.3333
[5 empty] | 1221.142 |  |  | 1359.7653 | 138.6233
5 | Information Board | ls | 1 | 500 | 500 | 1 | 500 | 500 | 0
6 | Miscellaneous | PS | 1 | 2500 | 2500 | 1 | 2160 | 2160 | -340
|  |  |  | Grand Total | 56983.8535 |  | Grand Total | 58896.2415 | 1880.6631
|  |  |  | Allocated Budget | 50000 |  | Allocated Budget | 50000 | 0
|  |  |  | Municipal Payment | 47500 |  | Municipal Payment | 47500 | 0

## valuation (2)
Shankharapur Municipality
Office of Municipal Executive
Bagmati Pradesh
Sankhu, Kathmandu
Detail Valuated Sheet
Project: | nai khola corridor marmat |  |  |  |  | Fiscal Year:08/81
Location: Shankharapur 6 | [5 empty] | Date:2081/02/29
S.No. | Description of works | Quantity | Unit | Rate | Amount | Remarks
1 | Site clearance work as per instruction of engineer all complete | 1 | ls | 1000 | 1000
0
0
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. |  |  |  | 0 |  |  | 52800 | 19500
|  | 66.0622 | m3 | 62.02 | 4097.1762
439.5667
3 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance |  |  |  | 0
|  | 432 | sack | 90 | 38880
4 | Providing and laying Bamboo for the protection all complete |  |  |  | 0 |  |  | 6096.2415
|  | 43.5822 | no | 240 | 10459.7333 |  | 0
1359.7653
5 | Information Board | 1 | ls | 500 | 500
6 | Miscellaneous | 1 | PS | 2160 | 2160
| Total |  |  |  | 58896.2415
| Total Valuated | 58896.2415 |  | 100
| Budget allocated | 50000
| Municipal Payment | 47500 |  | 80.6503
| User Contribution | 11396.2415 |  | 19.3497
| Contingencies 3% | 1500
| Maintenance 2% | 1000

## MB
Shankharapur Municipality
Office of Municipal Executive
Bagmati Pradesh
Sankhu, Kathmandu
Detail Measurement Sheet
Project: | nai khola corridor marmat | [6 empty] | Fiscal Year:08/81
Location: Shankharapur 6 | [7 empty] | Date:2081/02/29
S.No. | Description of works | Nos | Length | Breadth | Height | Quantity | Unit | Remarks
1 | Site clearance work as per instruction of engineer all complete | 1 |  |  |  | 1 | ls
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | [8 empty] | 52800
embankment
|  | 1 | 42.5 | 0.85 | 1.8287 | 66.0622
[6 empty] | 66.0622 | m3
3 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance |  | L |  | no
|  | 4 | 41 | 0.38 | 108 | 432 | sack |  | 11.2
[6 empty] | 432 | sack
4 | Providing and laying Bamboo for the protection all complete | [8 empty] | #REF!
| vertical post | 87 | 1.8287 |  |  | 159.0978 | m
| horizontal post | 2 | 40 |  |  | 80 | m |  |  | #REF!
[6 empty] | 239.0978 | m
[6 empty] | 43.5822 | no
5 | Information Board | 1 |  |  |  | 1 | ls
6 | Miscellaneous | 1 |  |  |  | 1 | PS