## Estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- कालिका मन्दिरमा भएको सार्वजनिक भवन मर्मत सम्भार | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/08/24
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -Plinth area | 1 | 4.5844 | 3.4288 | 0.15 | 2.3579 |  |  |  |  | 169.2004
|  | 1 | 4.5844 | 3.2891 | 0.15 | 2.2618 |  |  |  |  | 162.3045
|  | 1 | 3.5305 | 3.886 | 0.15 | 2.0579 |  |  |  |  | 147.6752
|  | 1 | 3.124 | 3.6574 | 0.15 | 1.7139 |  |  |  |  | 122.988
| Sub-total |  |  |  |  | 8.3915 | m3 | 663.31 | 5566.157
2 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf
| -Plinth area | 1 | 4.5844 | 3.4288 | 0.15 | 2.3579
|  | 1 | 4.5844 | 3.2891 | 0.15 | 2.2618
|  | 1 | 3.5305 | 3.886 | 0.15 | 2.0579
|  | 1 | 3.124 | 3.6574 | 0.15 | 1.7139
| Sub-total |  |  |  |  | 8.3915 | m3 | 4473.15 | 37536.3787
| VAT calculation | [7 empty] | 3374.2965
3 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -Plinth area | 1 | 4.5844 | 3.4288 | 0.075 | 1.1789
|  | 1 | 4.5844 | 3.2891 | 0.075 | 1.1309
|  | 1 | 3.5305 | 3.886 | 0.075 | 1.029
|  | 1 | 3.124 | 3.6574 | 0.075 | 0.85695
| Sub-total |  |  |  |  | 4.1957 | m3 | 12983.1 | 54473.7555
| VAT calculation | [7 empty] | 4406.1779
4 | #*X&% dL=dL=lr/fg ;fn sf7sf] k¦m]d $ dL=dL= P]gf vfkf agfO
| -window | 12 | 0.54607 | 1.2572 |  | 8.2385
| Sub-total |  |  |  |  | 8.2385 | sqm | 10576.85 | 87137.7411
| VAT calculation | [7 empty] | 5635.2339
5 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -Outer walls | 1 | 23.7489 |  | 2.4383 | 57.9064
| -column | 0 | 0.3 |  | 2.4383 | 0
|  | 0 | 0.23 |  | 2.4383 | 0
| -beam | 0 | 4.5718 | 0.69 |  | 0
| -Inner walls | 1 | 14.1237 |  | 2.4383 | 34.4377
| -window | -8 | 1.8287 |  | 1.3715 | -20.0651
| -door | -4 | 0.91436 |  | 2.1335 | -7.8031
| Sub-total |  |  |  |  | 64.4758 | sqm | 405.86 | 26168.1681
| VAT calculation | [7 empty] | 935.9353
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 225733.8441
| Total Estimated | 225733.8441 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 84.1699
| User Contribution | 35733.8441 |  | 15.8301
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 225733.8441 |  |  |  |  | Total Valuated Amount : |  | 228229.2891
Work Started : | [7 empty] | Work Finished:
Project:- कालिका मन्दिरमा भएको सार्वजनिक भवन मर्मत सम्भार | [7 empty] | F.Y:2081/2082
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2081/10/20
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | m3 | 8.3915 | 663.31 | 5566.157 | 8.5378 | 663.31 | 5663.2164 | 97.0594 |  |  | 6957.6963
2 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf | m3 | 8.3915 | 4473.15 | 37536.3787 | 8.5378 | 4473.15 | 38190.916 | 654.5372 |  |  | 46920.4734
| VAT calculation |  |  |  | 3374.2965 |  |  | 3433.1355 | 58.839 |  |  | 4217.8707
3 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_ | m3 | 4.1957 | 12983.1 | 54473.7555 | 4.2689 | 12983.1 | 55423.6367 | 949.8812 |  |  | 68092.1944
| VAT calculation |  |  |  | 4406.1779 |  |  | 4483.0103 | 76.8323 |  |  | 5507.7224
4 | #*X&% dL=dL=lr/fg ;fn sf7sf] k¦m]d $ dL=dL= P]gf vfkf agfO | sqm | 8.2385 | 10576.85 | 87137.7411 | 7.9657 | 10576.85 | 84251.5721 | -2886.169 |  |  | 108922.1764
| VAT calculation |  |  |  | 5635.2339 |  |  | 5448.5842 | -186.6497 |  |  | 7044.0424
5 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/ | sqm | 64.4758 | 405.86 | 26168.1681 | 73.3515 | 405.86 | 29770.443 | 3602.275 |  |  | 32710.2101
| VAT calculation |  |  |  | 935.9353 |  |  | 1064.7749 | 128.8396 |  |  | 1169.9191
6 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0 |  |  | 625
| Total |  |  |  | 225733.8441 |  |  | 228229.2891 | 2495.445
[10 empty] | 1070 | 70.2278 | 75143.7929

## Valuation
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- कालिका मन्दिरमा भएको सार्वजनिक भवन मर्मत सम्भार | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/10/20 |  |  |  | area of parallelogram
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -Plinth area | 1 | 7.21 | 4.3 | 0.15 | 4.6505 |  |  |  |  | 333.7135
| -deduction for tie beam area | 1 | 4.3 | 0.23 | 0.15 | 0.14835 |  |  |  |  | 10.6455
| -Inner rooms | 1 | 3.125 | 3.69 | 0.15 | 1.7297 |  |  |  |  | 124.1213
|  | 1 | 3.65 | 3.67 | 0.15 | 2.0093 |  |  |  |  | 144.188
| Sub-total |  |  |  |  | 8.5378 | m3 | 663.31 | 5663.2164
2 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf
| -Plinth area | 1 | 7.21 | 4.3 | 0.15 | 4.6505
| -deduction for tie beam area | 1 | 4.3 | 0.23 | 0.15 | 0.14835
| -Inner rooms | 1 | 3.125 | 3.69 | 0.15 | 1.7297
|  | 1 | 3.65 | 3.67 | 0.15 | 2.0093
| Sub-total |  |  |  |  | 8.5378 | m3 | 4473.15 | 38190.916
| VAT calculation | [7 empty] | 3433.1355
3 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -Plinth area | 1 | 7.21 | 4.3 | 0.075 | 2.3252
|  | 1 | 4.3 | 0.23 | 0.075 | 0.074175
|  | 1 | 3.125 | 3.69 | 0.075 | 0.86484
|  | 1 | 3.65 | 3.67 | 0.075 | 1.0047
| Sub-total |  |  |  |  | 4.2689 | m3 | 12983.1 | 55423.6367
| VAT calculation | [7 empty] | 4483.0103
4 | #*X&% dL=dL=lr/fg ;fn sf7sf] k¦m]d $ dL=dL= P]gf vfkf agfO
| -window | 12 | 0.53337 | 1.2445 |  | 7.9657
| Sub-total |  |  |  |  | 7.9657 | sqm | 10576.85 | 84251.5721
| VAT calculation | [7 empty] | 5448.5842
5 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -Outer walls | 1 | 23.54 |  | 2.67 | 62.8518
| -column | 0 | 0.3 |  | 2.67 | 0
|  | 0 | 0.23 |  | 2.67 | 0
| -beam | 0 | 4.5718 | 0.69 | 2.67 | 0
| -Inner walls | 1 | 14.37 |  | 2.67 | 38.3679
| -window | -8 | 1.8287 |  | 1.3715 | -20.0651
| -door | -4 | 0.91436 |  | 2.1335 | -7.8031
| Sub-total |  |  |  |  | 73.3515 | sqm | 405.86 | 29770.443
| VAT calculation | [7 empty] | 1064.7749
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 228229.2891
| Total Valuated | 228229.2891 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 83.2496
| User Contribution | 38229.2891 |  | 16.7504
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2

## Measure
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- कालिका मन्दिरमा भएको सार्वजनिक भवन मर्मत सम्भार | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/10/20
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -Plinth area | 1 | 7.21 | 4.3 | 0.15 | 4.6505 |  |  |  |  | 333.7135
| -deduction for tie beam area | 1 | 4.3 | 0.23 | 0.15 | 0.14835 |  |  |  |  | 10.6455
| -Inner rooms | 1 | 3.125 | 3.69 | 0.15 | 1.7297 |  |  |  |  | 124.1213
|  | 1 | 3.65 | 3.67 | 0.15 | 2.0093 |  |  |  |  | 144.188
| Sub-total |  |  |  |  | 8.5378 | m3 | 663.31 | 5663.2164
2 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf
| -Plinth area | 1 | 7.21 | 4.3 | 0.15 | 4.6505
| -deduction for tie beam area | 1 | 4.3 | 0.23 | 0.15 | 0.14835
| -Inner rooms | 1 | 3.125 | 3.69 | 0.15 | 1.7297
|  | 1 | 3.65 | 3.67 | 0.15 | 2.0093
| Sub-total |  |  |  |  | 8.5378 | m3 | 4473.15 | 38190.916
| VAT calculation | [7 empty] | 3433.1355
3 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -Plinth area | 1 | 7.21 | 4.3 | 0.075 | 2.3252
| -deduction for tie beam area | 1 | 4.3 | 0.23 | 0.075 | 0.074175
| -Inner rooms | 1 | 3.125 | 3.69 | 0.075 | 0.86484
|  | 1 | 3.65 | 3.67 | 0.075 | 1.0047
| Sub-total |  |  |  |  | 4.2689 | m3 | 12983.1 | 55423.6367
| VAT calculation | [7 empty] | 4483.0103
4 | #*X&% dL=dL=lr/fg ;fn sf7sf] k¦m]d $ dL=dL= P]gf vfkf agfO
| -window | 12 | 0.53337 | 1.2445 |  | 7.9657
| Sub-total |  |  |  |  | 7.9657 | sqm | 10576.85 | 84251.5721
| VAT calculation | [7 empty] | 5448.5842
5 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -Outer walls | 1 | 23.54 |  | 2.67 | 62.8518
| -column | 0 | 0.3 |  | 2.67 | 0
|  | 0 | 0.23 |  | 2.67 | 0
| -beam | 0 | 4.5718 | 0.69 | 2.67 | 0
| -Inner walls | 1 | 14.37 |  | 2.67 | 38.3679
| -deduction for window | -8 | 1.8287 |  | 1.3715 | -20.0651
| -deduction for door | -4 | 0.91436 |  | 2.1335 | -7.8031
| Sub-total |  |  |  |  | 73.3515 | sqm | 405.86 | 29770.443
| VAT calculation | [7 empty] | 1064.7749
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 228229.2891
| Total Estimated | 228229.2891 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 83.2496
| User Contribution | 38229.2891 |  | 16.7504
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2