## Estimate (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- बेन्डोल हाईट सडक निर्माण | [6 empty] | F.Y.: 2079/80
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -Road | 1 | 25 | 3.253 | 0.2 | 16.2652
| -Manhole | 5 | 1.0671 | 1.0671 | 1.35 | 7.6859
| -Drain | 1 | 25 | 1.0152 | 0.5 | 12.6905 | [5 empty] | 1.0152
| Sub-total |  |  |  |  | 36.6416 | cum | 67.51 | 2473.6776
| VAT calculation | [7 empty] | 269.9268
2 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Road | 1 | 25 | 3.253 | 0.15 | 12.1989
| -Manhole | 5 | 1.0671 | 1.0671 | 0.15 | 0.85398
| -Drain | 1 | 25 | 1.0152 | 0.15 | 3.8072
| Sub-total |  |  |  |  | 16.8601 | m3 | 4370.52 | 73687.3231
| VAT calculation | [7 empty] | 6495.4745
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -Drain | 1 | 25 | 1.0152 | 0.075 | 1.9036
| -Top cover/cap | 1 | 25 | 0.35 | 0.05 | 0.4375
| -Manhole | 5 | 1.0671 | 1.0671 | 0.075 | 0.42699
| Sub-total |  |  |  |  | 2.7681 | m3 | 4370.52 | 12097.9239
| VAT calculation | [7 empty] | 1066.4216
4 | Providing and laying Brick Masonry Work in Cement mortar in Foundation / structure complete excluding Pointing and Plastering, as per Drawing and Technical Specifications., Cement sand mortar (1:6)
| -Manhole | 5 | 3.3537 | 0.23 | 1.35 | 5.2066
| -Deduction for manhole | -10 | 0.6 | 0.6 | 0.23 | -0.828
| Sub-total |  |  |  |  | 4.3786 | cum | 14197.17 | 62163.088
| VAT calculation | [7 empty] | 6083.2725
5 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -Drain | 2 | 25 | 0.35 | 0.5 | 8.75
| Sub-total |  |  |  |  | 8.75 | cum | 9882.71 | 86473.7125
| VAT calculation | [7 empty] | 6583.5315
6 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 20
| -Road | 1 | 25 | 3.6067 | 0.15 | 13.5252
| Sub-total |  |  |  |  | 13.5252 | cum | 12442.52 | 168286.9797
| VAT calculation | [7 empty] | 18401.2197
7 | Providing and laying , fitting and placing HYSD bar reinforcement in sub-structure complete as per Drawing and Technical Specifications |  | length(m) | Unit Wt. (Kg/m) | Total weight (kg)
| -Along road width | 21 | 24.9 | 0.61728 | 322.7778 | 0.32278
| -Along road length | 166 | 3.153 | 0.39506 | 206.7777 | 0.20678
| Sub-total |  |  |  |  | 0.52956 | tonne | 121218 | 64191.658
| VAT calculation | [7 empty] | 7479.5689
8 | Hume Pipes
8.1 | -Earthwork in excavation for laying hume pipe
| 450 dia hume pipe | 1 | 105.5 | 0.6 | 0.6 | 37.98
| Sub-total |  |  |  |  | 37.98 | m3 | 67.21 | 2552.6358
| VAT calculation | [7 empty] | 279.786
8.2 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| 450 dia hume pipe | 1 | 105.5 | 0.6 | 0.15 | 9.495
| Sub-total |  |  |  |  | 9.495 | m3 | 4370.52 | 41498.0874 |  | 4.5
| VAT calculation | [7 empty] | 3658.0209
8.3 | -Laying Work of Hume Pipe
| Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia. | 44 | 2.5 |  |  | 110
| Sub-total |  |  |  |  | 110 | m | 5129.82 | 564280.2
| VAT calculation | [7 empty] | 65809.2864
9 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 1194331.7948
| Total Estimated | 1194331.7948 |  | 100
| Budget allocated | 1000000
| Municipal payment | 950000 |  | 79.5424
| User Contribution | 244331.7948 |  | 20.4576
| Contingencies | 30000 |  | 3
| Maintanince | 20000 |  | 2

## final (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- सुन्दर बस्ती सडक | [6 empty] | F.Y.: 2079/80
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -For hume pipe | 1 | 59.2 | 0.75 | 1.2 | 53.28
| -Manhole | 5 | 1.2 | 1.2 | 1.5 | 8.4823
| Sub-total |  |  |  |  | 61.7623 | m3 | 64.63 | 3991.6975
| VAT calculation | [7 empty] | 430.0921
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Manhole | 5 | 1.2 | 1.2 | 0.15 | 0.84823
| Sub-total |  |  |  |  | 0.84823 | m3 | 4561.53 | 3869.2267
| VAT calculation | [7 empty] | 340.7913
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -Manhole | 5 | 1.2 | 1.2 | 0.075 | 0.42412
| Sub-total |  |  |  |  | 0.42412 | m3 | 10634.5 | 4510.2511
| VAT calculation | [7 empty] | 444.9119
4 | Providing and laying , fitting and placing HYSD bar reinforcement in sub-structure complete as per Drawing and Technical Specifications | No. | Length (m) | Unit weight (kg/m) | Total weight (kg)
| -Manhole cover | 61 | 0.9 | 0.88889 | 48.8 | 0.0488
| Sub-total |  |  |  |  | 0.0488 | tonne | 124140 | 6058.032
| VAT calculation | [7 empty] | 703.9302
5 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 20
| -Manhole cover | 5 | 1 | 1 | 0.1 | 0.3927
| Sub-total |  |  |  |  | 0.3927 | m3 | 11588.17 | 4550.6637
| VAT calculation | [7 empty] | 460.6413
6 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -Manhole cover | 5 | 0.97 | 0.23 | 1.5 | 5.2567
| -Deduction for opening | -10 | 0.6 | 0.23 | 0.6 | -0.65031
| Sub-total |  |  |  |  | 4.6064 | m3 | 14362.76 | 66160.0464
| VAT calculation | [7 empty] | 6174.9466
5 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia.
| -450mm dia hume pipe | 0 | 2.5 |  |  | 0
| Sub-total |  |  |  |  | 0 | m | 5129.82 | 0
| VAT calculation | [7 empty] | 0
7 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 600 mm internal dia.
| -600mm dia hume pipe | 24 | 2.5 |  |  | 60 |  |  |  |  | 17.6 | 18
| Sub-total |  |  |  |  | 60 | m | 6932.79 | 415967.4
| VAT calculation | [7 empty] | 49149.2976
8 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 563311.9283
| Total Estimated | 563311.9283 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 84.3227
| User Contribution | 88311.9283 |  | 15.6773
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2

## ग्रावेल
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- सानागाउँ पासिखेल भित्री सडक ग्राबेल | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including levelling of road removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -road | 1 | 80 | 1.8287 | 0.15 | 21.9445
| Sub-total |  |  |  |  | 21.9445 | cum | 64.63 | 1418.2749
| VAT calculation | [7 empty] | 152.8144
2 | Providing and laying local/ washing sub-base on prepared surface, mixing at OMC, and compacting to achieve the desired density, complete as per Drawing and Technical Specifications., By Mechanical means
| -road | 1 | 80 | 1.8287 | 0.15 | 21.9445 |  |  |  |  | 17.6 | 18 | 57.5
| Sub-total |  |  |  |  | 21.9445 | cum | 1693.85 | 37170.7406 |  |  |  | 23
| VAT calculation | [7 empty] | 4703.9235
3 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 43945.7534
| Total Estimated | 43945.7534
| Budget allocated | 35000
| Municipal payment | 33250 |  | 75.6615
| User Contribution | 10695.7534 |  | 24.3385
| Contingencies | 1050 |  | 3
| Maintanince | 700 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 43945.7534 |  |  |  |  | Total Valuated Amount : |  | 39545.1032
Work Started : | [7 empty] | Work Finished:
Project:- सानागाउँ पासिखेल भित्री सडक ग्राबेल | [7 empty] | F.Y:2081/2082
Location:- Shankharapur Municipality 9 | [7 empty] | Date:
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including levelling of road removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | cum | 21.9445 | 64.63 | 1418.2749 | 0 | 64.63 | 0 | -1418.2749
| VAT calculation |  |  |  | 152.8144 |  |  | 0
2 | Providing and laying local/ washing sub-base on prepared surface, mixing at OMC, and compacting to achieve the desired density, complete as per Drawing and Technical Specifications., By Mechanical means | cum | 21.9445 | 1693.85 | 37170.7406 | 20.7237 | 1693.85 | 35102.8672 | -2067.8734
| VAT calculation |  |  |  | 4703.9235 |  |  | 4442.236
3 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 0 | 500 | 0 | -500
| Total |  |  |  | 43945.7534 |  |  | 39545.1032 | -4400.6502

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- सानागाउँ पासिखेल भित्री सडक ग्राबेल | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including levelling of road removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -road | 0 | 80 | 1.8287 | 0.15 | 0
| Sub-total |  |  |  |  | 0 | cum | 64.63 | 0
| VAT calculation | [7 empty] | 0
2 | Providing and laying local/ washing sub-base on prepared surface, mixing at OMC, and compacting to achieve the desired density, complete as per Drawing and Technical Specifications., By Mechanical means
| -Chanage 0+000 | [10 empty] | 0 | 1.5239 | 0.050798 | 0 | 1.8287 | 0.076196
| -Chanage 0+000 to 0+005 | 1 | 5 | 1.9811 | 0.050798 | 0.50318 | [5 empty] | 5 | 2.4383 | 0.050798 | 5 | 2.4383 | 0.076196
| -Chanage 0+005 to 0+010 | 1 | 5 | 2.4383 | 0.057147 | 0.6967 | [5 empty] | 5 | 2.4383 | 0.063497 | 5 | 2.4383 | 0.076196
| -Chanage 0+010 to 0+015 | 1 | 5 | 2.3621 | 0.076196 | 0.89991 | [5 empty] | 5 | 2.2859 | 0.088896 | 5 | 2.2859 | 0.1016
| -Chanage 0+015 to 0+020 | 1 | 5 | 2.3621 | 0.088896 | 1.0499 | [5 empty] | 5 | 2.4383 | 0.088896 | 5 | 2.4383 | 0.1016
| -Chanage 0+020 to 0+025 | 1 | 5 | 2.4383 | 0.088896 | 1.0838 | [5 empty] | 5 | 2.4383 | 0.088896 | 5 | 2.4383 | 0.1016
| -Chanage 0+025 to 0+030 | 1 | 5 | 2.4383 | 0.088896 | 1.0838 | [5 empty] | 5 | 2.4383 | 0.088896 | 5 | 2.4383 | 0.095245
| -Chanage 0+030 to 0+035 | 1 | 5 | 2.9717 | 0.088896 | 1.3208 | [5 empty] | 5 | 3.505 | 0.088896 | 5 | 3.5812 | 0.1016
| -Chanage 0+035 to 0+038 | 1 | 3 | 3.124 | 0.095245 | 0.89265 | [5 empty] | 3 | 2.7431 | 0.1016 | 3 | 2.8955 | 0.088896
| -Chanage 0+038 to 0+043 | 1 | 5 | 2.5907 | 0.1016 | 1.316 | [5 empty] | 5 | 2.4383 | 0.1016 | 5 | 2.4383 | 0.088896
| -Chanage 0+043 to 0+048 | 1 | 5 | 2.324 | 0.11429 | 1.3281 | [5 empty] | 5 | 2.2097 | 0.12699 | 5 | 2.1335 | 0.15239
| -Chanage 0+048 to 0+053 | 1 | 5 | 2.2478 | 0.12064 | 1.3559 | [5 empty] | 5 | 2.2859 | 0.11429 | 5 | 2.4383 | 0.12699
| -Chanage 0+053 to 0+058 | 1 | 5 | 2.2985 | 0.10794 | 1.2406 | [5 empty] | 5 | 2.3112 | 0.1016 | 5 | 2.4383 | 0.12699
| -Chanage 0+058 to 0+063 | 1 | 5 | 2.4006 | 0.12064 | 1.4481 | [5 empty] | 5 | 2.4901 | 0.13969 | 5 | 2.4383 | 0.15239
| -Chanage 0+063 to 0+068 | 1 | 5 | 2.5023 | 0.13334 | 1.6683 | [5 empty] | 5 | 2.5145 | 0.12699 | 5 | 2.4383 | 0.12699
| -Chanage 0+068 to 0+073 | 1 | 5 | 2.4764 | 0.11429 | 1.4152 | [5 empty] | 5 | 2.4383 | 0.1016 | 5 | 2.3112 | 0.1016
| -Chanage 0+073 to 0+078 | 1 | 5 | 2.4383 | 0.095245 | 1.1612 | [5 empty] | 5 | 2.4383 | 0.088896 | 5 | 2.4383 | 0.088896
| -Chanage 0+078 to 0+083 | 1 | 5 | 2.4383 | 0.095245 | 1.1612 | [5 empty] | 5 | 2.4383 | 0.1016 | 5 | 2.5907 | 0.1016
| -Chanage 0+083 to 0+087.3 | 1 | 4.3 | 2.5145 | 0.1016 | 1.0985 | [5 empty] | 4.4 | 2.5907 | 0.1016 | 4.4 | 2.616 | 0.1016
| Sub-total |  |  |  |  | 20.7237 | cum | 1693.85 | 35102.8672
| VAT calculation | [7 empty] | 4442.236
3 | Information board (सुचना पाटि) | 0 |  |  |  | 0 | no. | 500 | 0
| Grand Total | [7 empty] | 39545.1032
| Total Valuated | 39545.1032
| Budget allocated | 35000
| Municipal payment | 33250 |  | 84.0812
| User Contribution | 6295.1032 |  | 15.9188
| Contingencies | 1050 |  | 3
| Maintanince | 700 |  | 2
[11 empty] | 44.9667 | 1488.506 | 160.38
[11 empty] | 931.8765 | 30847.3764 | 3323.6697
[12 empty] | 4010.1589 | 432.0771 | 4442.236

## M
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- सानागाउँ पासिखेल भित्री सडक ग्राबेल | [9 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [9 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including levelling of road removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -road | 0 | 80 | 1.8287 | 0.15 | 0
| Sub-total |  |  |  |  | 0 | cum | 64.63 | 0
| VAT calculation | [7 empty] | 0
2 | Providing and laying local/ washing sub-base on prepared surface, mixing at OMC, and compacting to achieve the desired density, complete as per Drawing and Technical Specifications., By Mechanical means
| -Chanage 0+000 | [9 empty] | 0 | 1.5239 | 0.050798 | 0 | 1.8287 | 0.076196
| -Chanage 0+000 to 0+005 | 1 | 5 | 1.9811 | 0.050798 | 0.50318 |  |  |  |  | 5 | 2.4383 | 0.050798 | 5 | 2.4383 | 0.076196
| -Chanage 0+005 to 0+010 | 1 | 5 | 2.4383 | 0.057147 | 0.6967 |  |  |  |  | 5 | 2.4383 | 0.063497 | 5 | 2.4383 | 0.076196
| -Chanage 0+010 to 0+015 | 1 | 5 | 2.3621 | 0.076196 | 0.89991 |  |  |  |  | 5 | 2.2859 | 0.088896 | 5 | 2.2859 | 0.1016
| -Chanage 0+015 to 0+020 | 1 | 5 | 2.3621 | 0.088896 | 1.0499 |  |  |  |  | 5 | 2.4383 | 0.088896 | 5 | 2.4383 | 0.1016
| -Chanage 0+020 to 0+025 | 1 | 5 | 2.4383 | 0.088896 | 1.0838 |  |  |  |  | 5 | 2.4383 | 0.088896 | 5 | 2.4383 | 0.1016
| -Chanage 0+025 to 0+030 | 1 | 5 | 2.4383 | 0.088896 | 1.0838 |  |  |  |  | 5 | 2.4383 | 0.088896 | 5 | 2.4383 | 0.095245
| -Chanage 0+030 to 0+035 | 1 | 5 | 2.9717 | 0.088896 | 1.3208 |  |  |  |  | 5 | 3.505 | 0.088896 | 5 | 3.5812 | 0.1016
| -Chanage 0+035 to 0+038 | 1 | 3 | 3.124 | 0.095245 | 0.89265 |  |  |  |  | 3 | 2.7431 | 0.1016 | 3 | 2.8955 | 0.088896
| -Chanage 0+038 to 0+043 | 1 | 5 | 2.5907 | 0.1016 | 1.316 |  |  |  |  | 5 | 2.4383 | 0.1016 | 5 | 2.4383 | 0.088896
| -Chanage 0+043 to 0+048 | 1 | 5 | 2.324 | 0.11429 | 1.3281 |  |  |  |  | 5 | 2.2097 | 0.12699 | 5 | 2.1335 | 0.15239
| -Chanage 0+048 to 0+053 | 1 | 5 | 2.2478 | 0.12064 | 1.3559 |  |  |  |  | 5 | 2.2859 | 0.11429 | 5 | 2.4383 | 0.12699
| -Chanage 0+053 to 0+058 | 1 | 5 | 2.2985 | 0.10794 | 1.2406 |  |  |  |  | 5 | 2.3112 | 0.1016 | 5 | 2.4383 | 0.12699
| -Chanage 0+058 to 0+063 | 1 | 5 | 2.4006 | 0.12064 | 1.4481 |  |  |  |  | 5 | 2.4901 | 0.13969 | 5 | 2.4383 | 0.15239
| -Chanage 0+063 to 0+068 | 1 | 5 | 2.5023 | 0.13334 | 1.6683 |  |  |  |  | 5 | 2.5145 | 0.12699 | 5 | 2.4383 | 0.12699
| -Chanage 0+068 to 0+073 | 1 | 5 | 2.4764 | 0.11429 | 1.4152 |  |  |  |  | 5 | 2.4383 | 0.1016 | 5 | 2.3112 | 0.1016
| -Chanage 0+073 to 0+078 | 1 | 5 | 2.4383 | 0.095245 | 1.1612 |  |  |  |  | 5 | 2.4383 | 0.088896 | 5 | 2.4383 | 0.088896
| -Chanage 0+078 to 0+083 | 1 | 5 | 2.4383 | 0.095245 | 1.1612 |  |  |  |  | 5 | 2.4383 | 0.1016 | 5 | 2.5907 | 0.1016
| -Chanage 0+083 to 0+087.3 | 1 | 4.3 | 2.5145 | 0.1016 | 1.0985 |  |  |  |  | 4.4 | 2.5907 | 0.1016 | 4.4 | 2.616 | 0.1016
| Sub-total |  |  |  |  | 20.7237 | cum | 1693.85 | 35102.8672
| VAT calculation | [7 empty] | 4442.236
3 | Information board (सुचना पाटि) | 0 |  |  |  | 0 | no. | 500 | 0
| Grand Total | [7 empty] | 39545.1032
| Total Valuated | 39545.1032 |  | 100
| Budget allocated | 35000
| Municipal payment | 33250 |  | 84.0812
| User Contribution | 6295.1032 |  | 15.9188
| Contingencies | 1050 |  | 3
| Maintanince | 700 |  | 2

## ग्रावेल (2) (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- सानागाउँ पासिखेल भित्री सडक ग्राबेल | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including levelling of road removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -road | 1 | 80 | 1.8287 | 0.15 | 21.9445
| Sub-total |  |  |  |  | 21.9445 | cum | 64.63 | 1418.2749
| VAT calculation | [7 empty] | 152.8144
2 | Providing and laying local/ washing sub-base on prepared surface, mixing at OMC, and compacting to achieve the desired density, complete as per Drawing and Technical Specifications., By Mechanical means
| -road | 1 | 80 | 1.8287 | 0.15 | 21.9445 |  |  |  |  | 17.6 | 18 | 57.5
| Sub-total |  |  |  |  | 21.9445 | cum | 1693.85 | 37170.7406 |  |  |  | 23
| VAT calculation | [7 empty] | 4703.9235
3 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 43945.7534
| Total Estimated | 43945.7534 |  | 100
| Budget allocated | 35000
| Municipal payment | 33250 |  | 75.6615
| User Contribution | 10695.7534 |  | 24.3385
| Contingencies | 1050 |  | 3
| Maintanince | 700 |  | 2

## Sheet4 (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- सुन्दरबस्ती सडक ग्राबेल र ढलान | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -For hume pipe | 1 | 59.2 | 0.75 | 1.2 | 53.28
| -Manhole | 5 | 1.5 | 1.5 | 1.7 | 15.0207
| Sub-total |  |  |  |  | 68.3007 | m3 | 64.63 | 4414.2768
| VAT calculation | [7 empty] | 475.6236
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Manhole | 5 | 1.5 | 1.5 | 0.15 | 1.3254
| Sub-total |  |  |  |  | 1.3254 | m3 | 4561.53 | 6045.6667
| VAT calculation | [7 empty] | 532.4865
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -Manhole | 5 | 1.5 | 1.5 | 0.075 | 0.66268
| Sub-total |  |  |  |  | 0.66268 | m3 | 10634.5 | 7047.2673
| VAT calculation | [7 empty] | 695.1748
5 | C.I. Manhole cover including frame
| -Rounded manhole cover medium duty 450mm (22") | 5 |  |  |  | 5
| Sub-total |  |  |  |  | 5 | set | 4487 | 22435
| VAT calculation | [7 empty] | 2916.55
6 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -Rounded manhole cover medium duty 450mm (22") | 5 | 0.79939 | 0.23 | 1.5 | 4.3321
| -Deduction for opening | -10 | 0.6 | 0.23 | 0.6 | -0.65031 |  |  |  |  | 0.82 | 0.55877
| Sub-total |  |  |  |  | 3.6818 | m3 | 14362.76 | 52880.2747 |  | 0.50808 | 0.66138 | 0.58473
| VAT calculation | [7 empty] | 4935.4994
7 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 600 mm internal dia.
| -600mm dia hume pipe | 24 | 2.5 |  |  | 60 |  |  |  |  | 17.6 | 18 | 57.5
| Sub-total |  |  |  |  | 60 | m | 6932.79 | 415967.4 |  |  |  | 23
| VAT calculation | [7 empty] | 49149.2976
8 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 567994.5173
| Total Estimated | 567994.5173 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 83.6276
| User Contribution | 92994.5173 |  | 16.3724
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2

## with dhalaan (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- सुन्दरबस्ती सडक ग्राबेल र ढलान | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -For hume pipe | 1 | 32.5 | 0.75 | 1.2 | 29.25 |  |  |  |  | 13
|  | 1 | 45 | 0.6 | 1.2 | 32.4
| -Manhole | 2 | 1.5 | 1.5 | 1.7 | 6.0083
| Sub-total |  |  |  |  | 67.6583 | m3 | 64.63 | 4372.7557
| VAT calculation | [7 empty] | 471.1498
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Manhole | 2 | 1.5 | 1.5 | 0.15 | 0.53014
| Sub-total |  |  |  |  | 0.53014 | m3 | 4561.53 | 2418.2667
| VAT calculation | [7 empty] | 212.9946
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -Manhole | 2 | 1.5 | 1.5 | 0.075 | 0.26507
| Sub-total |  |  |  |  | 0.26507 | m3 | 10634.5 | 2818.9069
| VAT calculation | [7 empty] | 278.0699
5 | C.I. Manhole cover including frame
| -Rounded manhole cover medium duty 500mm (24") | 2 |  |  |  | 2
| Sub-total |  |  |  |  | 2 | set | 7063 | 14126
| VAT calculation | [7 empty] | 1836.38
6 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -Rounded manhole cover medium duty 500mm (24") | 2 | 0.82479 | 0.23 | 1.5 | 1.7879
| -Deduction for opening | -5 | 0.6 | 0.23 | 0.6 | -0.32515 |  |  |  |  | 0.82 | 0.55877
| Sub-total |  |  |  |  | 1.4627 | m3 | 14362.76 | 21008.8543 |  | 0.50808 | 0.66138 | 0.58473
| VAT calculation | [7 empty] | 1960.8292
7 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 600 mm internal dia.
| -600mm dia hume pipe | 13 | 2.5 |  |  | 32.5 |  |  |  |  | 17.6 | 18 | 57.5
| Sub-total |  |  |  |  | 32.5 | m | 6932.79 | 225315.675 |  |  |  | 23
| VAT calculation | [7 empty] | 26622.5362
8 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia.
| -450mm dia hume pipe | 18 | 2.5 |  |  | 45 |  |  |  |  | 17.6 | 18 | 57.5
| Sub-total |  |  |  |  | 45 | m | 5144.96 | 231523.2 |  |  |  | 23
| VAT calculation | [7 empty] | 26846.6328
9 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 560312.251
| Total Estimated | 560312.251 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 84.7742
| User Contribution | 85312.251 |  | 15.2258
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2

## Sheet4 (2) (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- सुन्दरबस्ती सडक ग्राबेल र ढलान (ढल निर्माण कार्य) | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/06/08
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -For hume pipe | 1 | 60.2 | 0.75 | 1.2 | 54.18
| -Manhole | 2 | 1.5 | 1.5 | 1.7 | 6.0083
| Sub-total |  |  |  |  | 60.1883 | m3 | 64.63 | 3889.9696
| VAT calculation | [7 empty] | 419.1312
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Manhole | 2 | 1.5 | 1.5 | 0.15 | 0.53014
| Sub-total |  |  |  |  | 0.53014 | m3 | 4561.53 | 2418.2667
| VAT calculation | [7 empty] | 212.9946
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -Manhole | 2 | 1.5 | 1.5 | 0.075 | 0.26507
| Sub-total |  |  |  |  | 0.26507 | m3 | 10634.5 | 2818.9069
| VAT calculation | [7 empty] | 278.0699
5 | C.I. Manhole cover including frame
| -Rounded manhole cover medium duty 500mm (24") | 2 |  |  |  | 2
| Sub-total |  |  |  |  | 2 | set | 7063 | 14126
| VAT calculation | [7 empty] | 1836.38
6 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -Rounded manhole cover medium duty 500mm (24") | 2 | 0.82479 | 0.23 | 1.5 | 1.7879
| -Deduction for opening | -5 | 0.6 | 0.23 | 0.6 | -0.32515 |  |  |  |  | 0.82 | 0.55877
| Sub-total |  |  |  |  | 1.4627 | m3 | 14362.76 | 21008.8543 |  | 0.50808 | 0.66138 | 0.58473
| VAT calculation | [7 empty] | 1960.8292
7 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 600 mm internal dia.
| -600mm dia hume pipe | 26 | 2.5 |  |  | 65 |  |  |  |  | 17.6 | 18 | 57.5
| Sub-total |  |  |  |  | 65 | m | 6932.79 | 450631.35 |  |  |  | 23
| VAT calculation | [7 empty] | 53245.0724
8 | Provisional sum for unforeseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
9 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 558845.8248
| Total Estimated | 558845.8248 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 84.9966
| User Contribution | 83845.8248 |  | 15.0034
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2