## re-estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- धन बहादुर श्रेष्ठको घर पछाडी पहिरो संरक्षण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/11
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Manual Means ., Roadway Excavation in all types of soil as per drawing and technical specification, including removal of stumps and other deleterious matter, with all lifts and lead as per Drawing and instruction of the Engineer. | [8 empty] | Road rate Norms No. 9.1.I.A
| -for gabion wall | 1 | 95 | 3.9622 | 0.15 | 56.4614
| Sub-total |  |  |  |  | 56.4614 | m3 | 736.88 | 41605.3094
2 | Providing and laying granular sub-base on prepared surface, mixing at OMC, and compacting to achieve the desired density, complete as per Drawing and Technical Specifications., By Mechanical means | [8 empty] | Road rate Norms No. 12.1.A (3244.12/1.15)
| -for gabion wall base | 1 | 95 | 3.9622 | 0.15 | 56.4614 |  |  |  |  | unit |  | 300 | unit
| Sub-total |  |  |  |  | 56.4614 | m3 | 2820.974 | 159276.2674 |  | 3244.12 | 2820.9739 | 826398.7 | 2754.6623
| -VAT 13% calculation | [7 empty] | 20219.1879
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 221600.7647
| Total Estimated | 221600.7647 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 85.7398
| User Contribution | 31600.7647 |  | 14.2602
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | #REF! |  |  |  |  | Total Valuated Amount : |  | #REF!
Work Started : | [7 empty] | Work Finished:
#REF! | [7 empty] | F.Y:2079/80
#REF! | [7 empty] | Date:2079/06/13
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  |  | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total |  |  |  | #REF! |  |  | #REF! | #REF!

## local
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:-चनौटे, घट्टेखोला सडक ग्राबेल | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/02/12
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Providing and laying local/ washing sub-base on prepared surface, mixing at OMC, and compacting to achieve the desired density, complete as per Drawing and Technical Specifications., By Mechanical means | [9 empty] | 135000 | 30000
| -for gabion wall base | 1 | 90 | 3.0479 | 0.125 | 34.2883 |  |  |  |  | unit |  | 300 | unit
| Sub-total |  |  |  |  | 34.2883 | m3 | 1693.85 | 58079.2822 |  | 3244.12 | 2820.9739 | 826398.7 | 2754.6623
| -VAT 13% calculation | [7 empty] | 6634.9894
2 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 65214.2716
| Total Estimated | 65214.2716 |  | 100
| Budget allocated | 50000
| Municipal payment | 47500 |  | 72.8368
| User Contribution | 17714.2716 |  | 27.1632
| Contingencies | 1500 |  | 3
| Maintanince | 1000 |  | 2