## just 15%
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- कालिका भगवती मन्दिर परिसरमा विभिन्न भौतिक संरचना निर्माण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/10/15
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -for toilet | 1 | 3.1493 | 3.1493 | 1.8287 | 18.1378 |  |  |  |  | 106.7605
| Sub-total |  |  |  |  | 18.1378 | m3 | 663.31 | 12031.0065
2 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf
| -for toilet | 1 | 3.1493 | 3.1493 | 0.15 | 1.4878
| Sub-total |  |  |  |  | 1.4878 | m3 | 4473.15 | 6654.9549
| VAT calculation | [7 empty] | 598.2407
3 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for toilet | 1 | 3.1493 | 3.1493 | 0.075 | 0.74388
| Sub-total |  |  |  |  | 0.74388 | m3 | 12983.1 | 9657.8413
| VAT calculation | [7 empty] | 781.1866
4 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for toilet | 1 | 3.0479 | 3.0479 |  | 9.2894
| -for toilet roof | 0 | 3.6574 | 3.6574 |  | 0
| Sub-total |  |  |  |  | 9.2894 | m2 | 915.42 | 8503.7001
| VAT calculation | [7 empty] | 565.5035
5 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit length (kg/m) | Weight (kg) | Weight (MT)
| -for toilet footing | 40 | 3.0479 | 0.39506 | 48.1636 | 0.048164
| -for toilet base | 80 | 3.0479 | 0.39506 | 96.3272 | 0.096327
| -for toilet roof | 0 | 3.6574 | 0.39506 | 0 | 0
| Sub-total |  |  |  |  | 0.14449 | MT | 131940 | 19064.1065
| VAT calculation | [7 empty] | 1994.839
6 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -for toilet footing | 1 | 3.0493 | 3.0493 | 0.1 | 0.92985
| -for toilet base | 1 | 3.0479 | 3.0479 | 0.125 | 1.1612
| -for toilet roof | 0 | 3.6574 | 3.6574 | 0.125 | 0
| -deduction for toilet fixture | -1 | 0.1 | 0.1 | 0.125 | -0.003927
| Sub-total |  |  |  |  | 2.0871 | m3 | 13568.9 | 28319.624
| VAT calculation | [7 empty] | 2584.132
7 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for septic tank | 2 | 3.0479 | 0.23 | 1.8287 | 2.5639
|  | 2 | 2.5907 | 0.23 | 1.8287 | 2.1793
|  | 1 | 2.5907 | 0.1 | 1.8287 | 0.47376
| -for toilet | 2 | 1.5747 | 0.23 | 2.1335 | 1.5455
|  | 1 | 2.5907 | 0.23 | 2.1335 | 1.2713
|  | 1 | 2.5907 | 0.1 | 2.1335 | 0.55272
| -deduction for windows | -1 | 0.45 | 0.23 | 0.60957 | -0.063091
| -deduction for door | -1 | 0.75 | 0.23 | 1.8287 | -0.31545
| Sub-total |  |  |  |  | 8.2078 | m3 | 14362.76 | 117886.8284
| VAT calculation | [7 empty] | 11002.7865
8 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -Inner walls | 1 | 15.2393 |  | 1.8 | 27.4307
| -Outer walls | 1 | 12.1914 |  | 1.8 | 21.9445
| Sub-total |  |  |  |  | 49.3752 | sqm | 405.86 | 20039.4148
| VAT calculation | [7 empty] | 716.7332
9 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -%) dL=dL=_
| -flooring at footing | 2 | 1.2191 | 2.5907 |  | 6.3168
| Sub-total |  |  |  |  | 6.3168 | sqm | 816.74 | 5159.1752
| VAT calculation | [7 empty] | 356.1157
10 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd
| -Inner walls | 1 | 15.2393 |  | 1.8 | 27.4307
| -Outer walls | 1 | 12.1914 |  | 1.8 | 21.9445
| -flooring at footing | 2 | 1.2191 | 2.5907 |  | 6.3168
| Sub-total |  |  |  |  | 55.692 | sqm | 279.03 | 15539.7334
| VAT calculation | [7 empty] | 467.2379
11 | cu¦fv sf7sf] rf}s; agfO hf]8\g] sfd
| -flooring at footing | 1 | 4.8766 | 0.1 | 0.075 | 0.036574
| Sub-total |  |  |  |  | 0 | cum | 284000.83 | 0
| VAT calculation | [7 empty] | 0
11 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 262423.1603
| Total Estimated | 262423.1603 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 72.4021
| User Contribution | 72423.1603 |  | 27.5979
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 262423.1603 |  |  |  |  | Total Valuated Amount : |  | 239808.02
Work Started : | [7 empty] | Work Finished:
Project:- कालिका भगवती मन्दिर परिसरमा विभिन्न भौतिक संरचना निर्माण | [7 empty] | F.Y:2079/80
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2079/06/13
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | m3 | 18.1378 | 663.31 | 12031.0065 | 16.9876 | 663.31 | 11268.0588 | -762.9478
2 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfd | m3 | 1.4878 | 4473.15 | 6654.9549 | 1.3934 | 4473.15 | 6232.9302 | -422.0248
| VAT calculation |  |  |  | 598.2407 |  |  | 560.3032 | -37.9375
3 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_ | m3 | 0.74388 | 12983.1 | 9657.8413 | 0 | 12983.1 | 0 | -9657.8413
| VAT calculation |  |  |  | 781.1866 |  |  | 0 | -781.1866
4 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd | m2 | 9.2894 | 915.42 | 8503.7001 | 6.4479 | 915.42 | 5902.5033 | -2601.1968
| VAT calculation |  |  |  | 565.5035 |  |  | 392.5216 | -172.9819
5 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | MT | 0.14449 | 131940 | 19064.1065 | 0.10974 | 131940 | 14478.7253 | -4585.3812
| VAT calculation |  |  |  | 1994.839 |  |  | 1515.0317 | -479.8073
6 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_ | m3 | 2.0871 | 13568.9 | 28319.624 | 3.2752 | 13568.9 | 44440.8166 | 16121.1926
| VAT calculation |  |  |  | 2584.132 |  |  | 4055.1717 | 1471.0397
7 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | m3 | 8.2078 | 14362.76 | 117886.8284 | 7.8783 | 14362.76 | 113154.6735 | -4732.155
| VAT calculation |  |  |  | 11002.7865 |  |  | 10561.1181 | -441.6684
8 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/ | sqm | 49.3752 | 405.86 | 20039.4148 | 27.4307 | 405.86 | 11133.0082 | -8906.4066
| VAT calculation |  |  |  | 716.7332 |  |  | 398.1851 | -318.5481
9 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_-%) dL=dL=_ | sqm | 6.3168 | 816.74 | 5159.1752 | 6.3168 | 816.74 | 5159.1752 | 0
| VAT calculation |  |  |  | 356.1157 |  |  | 356.1157 | 0
10 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd | sqm | 55.692 | 279.03 | 15539.7334 | 33.7475 | 279.03 | 9416.5514 | -6123.182
| VAT calculation |  |  |  | 467.2379 |  |  | 283.1303 | -184.1076
11 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0
| Total |  |  |  | 262423.1603 |  |  | 239808.02 | -22615.1404

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- कालिका भगवती मन्दिर परिसरमा विभिन्न भौतिक संरचना निर्माण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/10/15
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -for toilet | 1 | 3.0479 | 3.0479 | 1.8287 | 16.9876 |  |  |  |  | 99.9902
| Sub-total |  |  |  |  | 16.9876 | m3 | 663.31 | 11268.0588
2 | husf] vf8ndf 9'+uf eg]{ / n]en ug]{ sfddf
| -for toilet | 1 | 3.0479 | 3.0479 | 0.15 | 1.3934
| Sub-total |  |  |  |  | 1.3934 | m3 | 4473.15 | 6232.9302
| VAT calculation | [7 empty] | 560.3032
3 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for toilet | 0 | 3.0479 | 3.0479 | 0.075 | 0
| Sub-total |  |  |  |  | 0 | m3 | 12983.1 | 0
| VAT calculation | [7 empty] | 0
4 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for toilet | 2 | 2.5907 | 1.2444 |  | 6.4479
| -for toilet roof | 0 | 3.6574 | 3.6574 |  | 0
| Sub-total |  |  |  |  | 6.4479 | m2 | 915.42 | 5902.5033
| VAT calculation | [7 empty] | 392.5216
5 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit length (kg/m) | Weight (kg) | Weight (MT)
| -for toilet footing | 6 | 1.092 | 0.39506 | 2.5886 | 0.0025886
|  | 14 | 2.46 | 0.39506 | 13.6059 | 0.013606
|  | 32 | 3.18 | 0.39506 | 40.2015 | 0.040201
|  | 6 | 1.15 | 0.39506 | 2.7259 | 0.0027259
|  | 38 | 3.3 | 0.39506 | 49.5407 | 0.049541
|  | 16 | 0.17 | 0.39506 | 1.0746 | 0.0010746
| Sub-total |  |  |  |  | 0.10974 | MT | 131940 | 14478.7253
| VAT calculation | [7 empty] | 1515.0317
6 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -for toilet footing | 1 | 3.3526 | 3.2002 | 0.125 | 1.3412
| -void | -1 | 0.55877 | 1.1429 | 0.125 | -0.2508
| -deduction for toilet fixture | -1 | 0.1 | 0.1 | 0.125 | -0.003927
| -footing | 1 | 3.0479 | 3.0479 | 0.075 | 2.1888
| Sub-total |  |  |  |  | 3.2752 | m3 | 13568.9 | 44440.8166
| VAT calculation | [7 empty] | 4055.1717
7 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for septic tank | 2 | 3.0479 | 0.23 | 1.8287 | 2.5639
|  | 2 | 2.5907 | 0.23 | 1.8287 | 2.1793
|  | 1 | 2.5907 | 0.1 | 1.8287 | 0.47376
| -for toilet | 2 | 1.6763 | 0.23 | 2.1335 | 1.6452
|  | 1 | 1.9811 | 0.23 | 2.1335 | 0.97214
|  | 1 | 1.9811 | 0.1 | 2.1335 | 0.42267
| -deduction for windows | -1 | 0.45 | 0.23 | 0.60957 | -0.063091
| -deduction for door | -1 | 0.75 | 0.23 | 1.8287 | -0.31545
| Sub-total |  |  |  |  | 7.8783 | m3 | 14362.76 | 113154.6735
| VAT calculation | [7 empty] | 10561.1181
8 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -Inner walls | 1 | 15.2393 |  | 1.8 | 27.4307
| -Outer walls | 0 | 12.1914 |  | 1.8 | 0
| Sub-total |  |  |  |  | 27.4307 | sqm | 405.86 | 11133.0082
| VAT calculation | [7 empty] | 398.1851
9 | l;d]G6 s+qmL6 ˆnf]l/Ë -!M@M$_ -%) dL=dL=_
| -flooring at footing | 2 | 1.2191 | 2.5907 |  | 6.3168
| Sub-total |  |  |  |  | 6.3168 | sqm | 816.74 | 5159.1752
| VAT calculation | [7 empty] | 356.1157
10 | # dL=dL= df]6fO{ d;Lgf] l;d]G6 3f]6\g] sfd
| -Inner walls | 1 | 15.2393 |  | 1.8 | 27.4307
| -Outer walls | 0 | 12.1914 |  | 1.8 | 0
| -flooring at footing | 2 | 1.2191 | 2.5907 |  | 6.3168
| Sub-total |  |  |  |  | 33.7475 | sqm | 279.03 | 9416.5514
| VAT calculation | [7 empty] | 283.1303
11 | cu¦fv sf7sf] rf}s; agfO hf]8\g] sfd
| -flooring at footing | 1 | 4.8766 | 0.1 | 0.075 | 0.036574
| Sub-total |  |  |  |  | 0.036574 | cum | 284000.83 | 10387.1075
| VAT calculation | [7 empty] | 1137.4203
11 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 251332.5478
| Total Estimated | 251332.5478 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 75.5971
| User Contribution | 61332.5478 |  | 24.4029
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2