## Estimate (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- बेन्डोल हाईट सडक निर्माण | [6 empty] | F.Y.: 2079/80
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -Road | 1 | 25 | 3.253 | 0.2 | 16.2652
| -Manhole | 5 | 1.0671 | 1.0671 | 1.35 | 7.6859
| -Drain | 1 | 25 | 1.0152 | 0.5 | 12.6905 | [5 empty] | 1.0152
| Sub-total |  |  |  |  | 36.6416 | cum | 67.51 | 2473.6776
| VAT calculation | [7 empty] | 269.9268
2 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Road | 1 | 25 | 3.253 | 0.15 | 12.1989
| -Manhole | 5 | 1.0671 | 1.0671 | 0.15 | 0.85398
| -Drain | 1 | 25 | 1.0152 | 0.15 | 3.8072
| Sub-total |  |  |  |  | 16.8601 | m3 | 4370.52 | 73687.3231
| VAT calculation | [7 empty] | 6495.4745
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -Drain | 1 | 25 | 1.0152 | 0.075 | 1.9036
| -Top cover/cap | 1 | 25 | 0.35 | 0.05 | 0.4375
| -Manhole | 5 | 1.0671 | 1.0671 | 0.075 | 0.42699
| Sub-total |  |  |  |  | 2.7681 | m3 | 4370.52 | 12097.9239
| VAT calculation | [7 empty] | 1066.4216
4 | Providing and laying Brick Masonry Work in Cement mortar in Foundation / structure complete excluding Pointing and Plastering, as per Drawing and Technical Specifications., Cement sand mortar (1:6)
| -Manhole | 5 | 3.3537 | 0.23 | 1.35 | 5.2066
| -Deduction for manhole | -10 | 0.6 | 0.6 | 0.23 | -0.828
| Sub-total |  |  |  |  | 4.3786 | cum | 14197.17 | 62163.088
| VAT calculation | [7 empty] | 6083.2725
5 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -Drain | 2 | 25 | 0.35 | 0.5 | 8.75
| Sub-total |  |  |  |  | 8.75 | cum | 9882.71 | 86473.7125
| VAT calculation | [7 empty] | 6583.5315
6 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 20
| -Road | 1 | 25 | 3.6067 | 0.15 | 13.5252
| Sub-total |  |  |  |  | 13.5252 | cum | 12442.52 | 168286.9797
| VAT calculation | [7 empty] | 18401.2197
7 | Providing and laying , fitting and placing HYSD bar reinforcement in sub-structure complete as per Drawing and Technical Specifications |  | length(m) | Unit Wt. (Kg/m) | Total weight (kg)
| -Along road width | 21 | 24.9 | 0.61728 | 322.7778 | 0.32278
| -Along road length | 166 | 3.153 | 0.39506 | 206.7777 | 0.20678
| Sub-total |  |  |  |  | 0.52956 | tonne | 121218 | 64191.658
| VAT calculation | [7 empty] | 7479.5689
8 | Hume Pipes
8.1 | -Earthwork in excavation for laying hume pipe
| 450 dia hume pipe | 1 | 105.5 | 0.6 | 0.6 | 37.98
| Sub-total |  |  |  |  | 37.98 | m3 | 67.21 | 2552.6358
| VAT calculation | [7 empty] | 279.786
8.2 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| 450 dia hume pipe | 1 | 105.5 | 0.6 | 0.15 | 9.495
| Sub-total |  |  |  |  | 9.495 | m3 | 4370.52 | 41498.0874 |  | 4.5
| VAT calculation | [7 empty] | 3658.0209
8.3 | -Laying Work of Hume Pipe
| Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia. | 44 | 2.5 |  |  | 110
| Sub-total |  |  |  |  | 110 | m | 5129.82 | 564280.2
| VAT calculation | [7 empty] | 65809.2864
9 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 1194331.7948
| Total Estimated | 1194331.7948 |  | 100
| Budget allocated | 1000000
| Municipal payment | 950000 |  | 79.5424
| User Contribution | 244331.7948 |  | 20.4576
| Contingencies | 30000 |  | 3
| Maintanince | 20000 |  | 2

## final
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- सुन्दर बस्ती सडक | [6 empty] | F.Y.: 2079/80
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -For hume pipe | 1 | 59.2 | 0.75 | 1.2 | 53.28
| -Manhole | 5 | 1.2 | 1.2 | 1.5 | 8.4823
| Sub-total |  |  |  |  | 61.7623 | m3 | 64.63 | 3991.6975
| VAT calculation | [7 empty] | 430.0921
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Manhole | 5 | 1.2 | 1.2 | 0.15 | 0.84823
| Sub-total |  |  |  |  | 0.84823 | m3 | 4561.53 | 3869.2267
| VAT calculation | [7 empty] | 340.7913
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -Manhole | 5 | 1.2 | 1.2 | 0.075 | 0.42412
| Sub-total |  |  |  |  | 0.42412 | m3 | 10634.5 | 4510.2511
| VAT calculation | [7 empty] | 444.9119
4 | Providing and laying , fitting and placing HYSD bar reinforcement in sub-structure complete as per Drawing and Technical Specifications | No. | Length (m) | Unit weight (kg/m) | Total weight (kg)
| -Manhole cover | 61 | 0.9 | 0.88889 | 48.8 | 0.0488
| Sub-total |  |  |  |  | 0.0488 | tonne | 124140 | 6058.032
| VAT calculation | [7 empty] | 703.9302
5 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 20
| -Manhole cover | 5 | 1 | 1 | 0.1 | 0.3927
| Sub-total |  |  |  |  | 0.3927 | m3 | 11588.17 | 4550.6637
| VAT calculation | [7 empty] | 460.6413
6 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -Manhole cover | 5 | 0.97 | 0.23 | 1.5 | 5.2567
| -Deduction for opening | -10 | 0.6 | 0.23 | 0.6 | -0.65031
| Sub-total |  |  |  |  | 4.6064 | m3 | 14362.76 | 66160.0464
| VAT calculation | [7 empty] | 6174.9466
5 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia.
| -450mm dia hume pipe | 0 | 2.5 |  |  | 0
| Sub-total |  |  |  |  | 0 | m | 5129.82 | 0
| VAT calculation | [7 empty] | 0
7 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 600 mm internal dia.
| -600mm dia hume pipe | 24 | 2.5 |  |  | 60 |  |  |  |  | 17.6 | 18
| Sub-total |  |  |  |  | 60 | m | 6932.79 | 415967.4
| VAT calculation | [7 empty] | 49149.2976
8 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 563311.9283
| Total Estimated | 563311.9283 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 84.3227
| User Contribution | 88311.9283 |  | 15.6773
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | #REF! |  |  |  |  | Total Valuated Amount : |  | 291284.227
Work Started : | [7 empty] | Work Finished:
Project:- बेन्डोल हाईट सडक निर्माण | [7 empty] | F.Y:2079/80
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2079/06/13
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Providing and laying Brick Masonry Work in Cement mortar in Foundation / structure complete excluding Pointing and Plastering, as per Drawing and Technical Specifications., Cement sand mortar (1:6) | cum | 36.6416 | 67.51 | 2473.6776 | 38 | 7062.79 | 268386.02 | 265912.3424
| #REF! |  |  |  | #REF! |  |  | 22398.207
9 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0
| Total |  |  |  | #REF! |  |  | 291284.227 | #REF!

## Valuated
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- बेन्डोल हाईट सडक निर्माण | [6 empty] | F.Y.: 2079/80
Location:- Shankharapur Municipality 9 | [6 empty] | Date: 2079/06/13
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Gabion Structure for Retaining Earth, Providing and laying Gabion structure for retaining earth with diaphragm including rolling, cutting, weaving, placing, laying sides and diaphragms with binding wire and filling boulders all complete as per drawing and technical specification Mesh wire- 10 Swg(0.0615 kg/m), Selvedge Wire 8 Swg ( 0.1057 kg/m), binding wire 12 Swg (0.0409 kg/m) Hexagonal mesh Type 100 mm X 120 mm,, Box size 2 X 1 X 1 m ( 11 sqm) | 19 | 2 | 1 | 1 | 38 |  |  |  |  | 0.12703
[6 empty] | 38 | cum | 7062.79 | 268386.02
| VAT 13% for material | [7 empty] | 22398.207
2 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 291284.227
| Total Valuated | 291284.227 |  | 100
| Budget allocated | 250000
| Municipal payment | 237500 |  | 81.5355
| User Contribution | 53784.227 |  | 18.4645
| Contingencies | 7500 |  | 3
| Maintanince | 5000 |  | 2

## measurement
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- बेन्डोल हाईट सडक निर्माण | [5 empty] | F.Y.: 2079/80
Location:- Shankharapur Municipality 9 | [5 empty] | Date: 2079/06/13
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Gabion Structure for Retaining Earth, Providing and laying Gabion structure for retaining earth with diaphragm including rolling, cutting, weaving, placing, laying sides and diaphragms with binding wire and filling boulders all complete as per drawing and technical specification Mesh wire- 10 Swg(0.0615 kg/m), Selvedge Wire 8 Swg ( 0.1057 kg/m), binding wire 12 Swg (0.0409 kg/m) Hexagonal mesh Type 100 mm X 120 mm,, Box size 2 X 1 X 1 m ( 11 sqm) | 19 | 2 | 1 | 1 | 38 |  |  |  |  | 0.12703
[6 empty] | 38 | cum | 7062.79 | 268386.02
| VAT 13% for material | [7 empty] | 22398.207
2 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 291284.227
| Total Estimated | 291284.227 |  | 100
| Budget allocated | 600000
| Municipal payment | 570000 |  | 195.6852
| User Contribution | -278715.773 |  | -95.6852
| Contingencies | 18000 |  | 3
| Maintanince | 12000 |  | 2