## estimated upabhokta
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimate Sheet
Project:- इन्द्रायणी सार्वजनिक शौचालय बनाउने काम (भैपरी आउने बिबिध पुँजिगत खर्च) | [6 empty] | F.Y.: 2079/80
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2079
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Toilet fitings
| PP-R Pipe (PN-10) 20mm outer, 1.9mm thick, 0.107 kg/m | 1 | 14.6805 |  |  | 14.6805 | rm | 56 | 822.1071
| Female elbow 20mmX1/2" | 7 |  |  |  | 7 | no. | 113 | 791
| Female tee 20mmX1/2" | 3 |  |  |  | 3 | no. | 116 | 348
| Elbow90o | 8 |  |  |  | 8 | no. | 11 | 88
| Cross Tee | 6 |  |  |  | 6 | no. | 26 | 156
| Plug 20mm | 5 |  |  |  | 5 | no. | 13 | 65
| UPVC Pipe NS 206/046 -4kg/cm2 pressure 75mm | 1 | 8.9404 |  |  | 8.9404 | rm | 181 | 1618.2058
| UPVC Pipe NS 206/046 -6kg/cm2 pressure 50mm | 1 | 4.0638 |  |  | 4.0638 | rm | 117 | 475.4648
| UPVC Pipe NS 206/046 -2.5kg/cm2 pressure 110mm | 1 | 2.8701 |  |  | 2.8701 | rm | 247 | 708.9048
| 110mm UPVC bend 45o | 2 |  |  |  | 2 | no. | 185 | 370
| 110mm UPVC single tee | 2 |  |  |  | 2 | no. | 327 | 654
| 110mm HDPE pipe | 1 | 3.0479 |  |  | 3.0479 | Kg | 287 | 874.7333
| 20mm G.I Pipe threaded - Light class | 1 | 0.6 |  |  | 0.6 | rm | 323 | 193.8
| 20mm G.I Union | 1 |  |  |  | 1 | no. | 153 | 153
| 500mm size white glazed without siphon | 2 |  |  |  | 2 | set | 2741 | 5482
| Multi-floor trap | 2 |  |  |  | 2 | no. | 329 | 658
| PVC Cistern Set single flush complete set | 2 |  |  |  | 2 | set | 1973 | 3946
| Urinal set- Porcelain clay small urinal (46.5*35.5*26.5)cm size | 3 |  |  |  | 3 | set | 1880 | 5640
| Porcelain clay white glaze wash basin (500*400)cm size regular | 2 |  |  |  | 2 | set | 1095 | 2190
| VAT calculation | [7 empty] | 3280.4481
2 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -Outer face of Toilet wall | 1 | 15 |  | 1.2191 | 18.2871
| -Inner face of Toilet wall | 1 | 19.2 |  | 1.1429 | 21.9445
| -Deduction for door | -4 |  | 0.9 | 1.2191 | -4.3889
| -Deduction for window | -4 |  | 1.2 | 0.75 | -3.6
| Sub-total |  |  |  |  | 32.2427 | sqm | 405.86 | 7422.0055
| VAT calculation | [7 empty] | 468.0374
3 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 tof/L jf;]jn l8:6]Dk/ nufpg] sfd .
| As per plaster | 1 |  |  |  | 32.2427
| Sub-total |  |  |  |  | 32.2427 | sqm | 184.41 | 5945.882
| VAT calculation | [7 empty] | 251.4933
4 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd .
| -Inner face of Toilet wall | 1 | 19.2 |  | 1.4477 | 27.7964
| -Floor | 2 | 1.8287 | 3.0479 |  | 11.1473
| -Deduction for door | -4 |  | 0.9 | 1.5239 | -5.4861
| Sub-total |  |  |  |  | 33.4575 | sqm | 2807.39 | 93928.3858
| VAT calculation | [7 empty] | 3483.4778
5 | Providing and fixing Single Panel Casement (Hinged) door of aluminium section in natural or color anodized/powder coated color section size(102x45x1.5 mm) fitted with 5 mm clear glass of 9 mm both side laminated board (excluding the cost of handle and door closer).
| -Door | 2 |  | 0.9 | 2.1335 | 3.8403
| Sub-total |  |  |  |  | 3.8403 | sqm | 7069.31 | 27148.2188
| VAT calculation | [7 empty] | 3529.2684
6 | Provisional sum for fittings works, electric fittings items & other unforseen works/items | 1 |  |  |  | 1 | LS | 20000 | 20000
7 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 191191.433
| Total Estimated | 191191.433 |  | 100
| Budget allocated | 160000
| Municipal payment | 152000 |  | 79.5015
| User Contribution | 39191.433 |  | 20.4985
| Contingencies | 4800 |  | 3
| Maintanince | 3200 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | #REF! |  |  |  |  | Total Valuated Amount : |  | #REF!
Work Started : | [7 empty] | Work Finished:
Project:- इन्द्रायणी सार्वजनिक शौचालय बनाउने काम (भैपरी आउने बिबिध पुँजिगत खर्च) | [7 empty] | F.Y:2079/80
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2079/ /
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Toilet fitings | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| VAT calculation |  |  |  | 3280.4481 |  |  | #REF! | #REF!
7 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | #REF! | #REF! | #REF! | #REF!
| Total |  |  |  | #REF! |  |  | #REF! | #REF!

## quotation
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- इन्द्रायणी सार्वजनिक शौचालय बनाउने काम (भैपरी आउने बिबिध पुँजिगत खर्च) | [6 empty] | F.Y.: 2081/82
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Toilet fitings
| PP-R Pipe (PN-10) 20mm outer, 1.9mm thick, 0.107 kg/m | 1 | 14.6805 |  |  | 14.6805 | rm | 56 | 822.1071
| Female elbow 20mmX1/2" | 7 |  |  |  | 7 | no. | 113 | 791
| Female tee 20mmX1/2" | 3 |  |  |  | 3 | no. | 116 | 348
| Elbow90o | 8 |  |  |  | 8 | no. | 11 | 88
| Cross Tee | 6 |  |  |  | 6 | no. | 26 | 156
| Plug 20mm | 5 |  |  |  | 5 | no. | 13 | 65
| UPVC Pipe NS 206/046 -4kg/cm2 pressure 75mm | 1 | 8.9404 |  |  | 8.9404 | rm | 181 | 1618.2058
| UPVC Pipe NS 206/046 -6kg/cm2 pressure 50mm | 1 | 4.0638 |  |  | 4.0638 | rm | 117 | 475.4648
| UPVC Pipe NS 206/046 -2.5kg/cm2 pressure 110mm | 1 | 2.8701 |  |  | 2.8701 | rm | 247 | 708.9048
| 110mm UPVC bend 45o | 2 |  |  |  | 2 | no. | 185 | 370
| 110mm UPVC single tee | 2 |  |  |  | 2 | no. | 327 | 654
| 110mm HDPE pipe | 1 | 3.0479 |  |  | 3.0479 | Kg | 287 | 874.7333
| 20mm G.I Pipe threaded - Light class | 1 | 0.6 |  |  | 0.6 | rm | 323 | 193.8
| 20mm G.I Union | 1 |  |  |  | 1 | no. | 153 | 153
| 500mm size white glazed without siphon | 2 |  |  |  | 2 | set | 2741 | 5482
| Multi-floor trap | 2 |  |  |  | 2 | no. | 329 | 658
| PVC Cistern Set single flush complete set | 2 |  |  |  | 2 | set | 1973 | 3946
| Urinal set- Porcelain clay small urinal (46.5*35.5*26.5)cm size | 3 |  |  |  | 3 | set | 1880 | 5640
| Porcelain clay white glaze wash basin (500*400)cm size regular | 2 |  |  |  | 2 | set | 1095 | 2190
2 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -Outer face of Toilet wall | 1 | 15 |  | 1.2191 | 18.2871
| -Inner face of Toilet wall | 1 | 19.2 |  | 1.1429 | 21.9445
| -Deduction for door | -4 |  | 0.9 | 1.2191 | -4.3889
| -Deduction for window | -4 |  | 1.2 | 0.75 | -3.6
| Sub-total |  |  |  |  | 32.2427 | sqm | 466.739 | 8535.3063
3 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 tof/L jf;]jn l8:6]Dk/ nufpg] sfd .
| As per plaster | 1 |  |  |  | 32.2427
| Sub-total |  |  |  |  | 32.2427 | sqm | 212.0715 | 6837.7643
4 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd .
| -Inner face of Toilet wall | 1 | 19.2 |  | 1.4477 | 27.7964
| -Floor | 2 | 1.8287 | 3.0479 |  | 11.1473
| -Deduction for door | -4 |  | 0.9 | 1.5239 | -5.4861
| Sub-total |  |  |  |  | 33.4575 | sqm | 3228.4985 | 108017.6437
5 | UPVC Singl Door with full pannel (frame 60*60mm sash 60X100mm) white colour with panel
| -Door | 2 |  | 0.9 | 2.1335 | 3.8403
| Sub-total |  |  |  |  | 3.8403 | sqm | 10055.6 | 38616.4462
6 | UPVC Casement Window(frame 60*60 mm, sash 60*78mm White Colour With 5mm Glass)
| -Window | 2 |  | 1.2 | 0.75 | 1.8
| Sub-total |  |  |  |  | 1.8 | sqm | 9047.05 | 16284.69
7 | Provisional sum for fittings works, electric fittings items & other unforseen works/items | 1 |  |  |  | 1 | LS | 20000 | 20000
8 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 224026.0664
| Total Estimated | 224026.0664
| VAT 13% | 29123.3886
| Grand total | 253149.455

## estimated quotation (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimate Sheet
Project:- बिद्यालय क्षेत्र अगाडी स्पिड ब्रेकर बनाउने काम (भैपरी आउने बिबिध पुँजिगत खर्च) | [6 empty] | F.Y.: 2079/80
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2079
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Toilet fitings
| PP-R Pipe (PN-10) 20mm outer, 1.9mm thick, 0.107 kg/m | 1 | 14.6805 |  |  | 14.6805 | rm | 56 | 822.1071
| Female elbow 20mmX1/2" | 7 |  |  |  | 7 | no. | 113 | 791
| Female tee 20mmX1/2" | 3 |  |  |  | 3 | no. | 116 | 348
| Elbow90o | 8 |  |  |  | 8 | no. | 11 | 88
| Cross Tee | 6 |  |  |  | 6 | no. | 26 | 156
| Plug 20mm | 5 |  |  |  | 5 | no. | 13 | 65
| UPVC Pipe NS 206/046 -4kg/cm2 pressure 75mm | 1 | 8.9404 |  |  | 8.9404 | rm | 181 | 1618.2058
| UPVC Pipe NS 206/046 -6kg/cm2 pressure 50mm | 1 | 4.0638 |  |  | 4.0638 | rm | 117 | 475.4648
| UPVC Pipe NS 206/046 -2.5kg/cm2 pressure 110mm | 1 | 2.8701 |  |  | 2.8701 | rm | 247 | 708.9048
| 110mm UPVC bend | 2 |  |  |  | 2 | no. | 185 | 370
| 110mm UPVC single tee | 2 |  |  |  | 2 | no. | 327 | 654
| 110mm HDPE pipe | 1 | 3.0479 |  |  | 3.0479 | Kg | 287 | 874.7333
| 20mm G.I Pipe threaded - Light class | 1 | 0.6 |  |  | 0.6 | rm | 323 | 193.8
| 20mm G.I Union | 1 |  |  |  | 1 | no. | 153 | 153
| 500mm size white glazed without siphon | 2 |  |  |  | 2 | set | 2741 | 5482
| Multi-floor trap | 2 |  |  |  | 2 | no. | 329 | 658
| PVC Cistern Set single flush complete set | 2 |  |  |  | 2 | set | 1973 | 3946
| Urinal set- Porcelain clay small urinal (46.5*35.5*26.5)cm size | 3 |  |  |  | 3 | set | 1880 | 5640
| Porcelain clay white glaze wash basin (500*400)cm size regular | 2 |  |  |  | 2 | set | 1095 | 2190
| Other fittings & electric fittings items | 1 |  |  |  | 1 | LS | 10000 | 10000
2 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -Outer face of Toilet wall | 1 | 15 |  | 1.2191 | 18.2871
| -Inner face of Toilet wall | 1 | 19.2 |  | 1.1429 | 21.9445
| -Deduction for door | -4 |  | 0.9 | 1.2191 | -4.3889
| -Deduction for window | -4 |  | 1.2 | 0.75 | -3.6
| Sub-total |  |  |  |  | 32.2427 | sqm | 466.25 | 8526.3639
3 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 tof/L jf;]jn l8:6]Dk/ nufpg] sfd .
| As per plaster | 1 |  |  |  | 32.2427
| Sub-total |  |  |  |  | 32.2427 | sqm | 206.07 | 6644.2596
4 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd .
| -Inner face of Toilet wall | 1 | 19.2 |  | 1.4477 | 27.7964
| -Floor | 2 | 1.8287 | 3.0479 |  | 11.1473
| -Deduction for door | -4 |  | 0.9 | 1.5239 | -5.4861
| Sub-total |  |  |  |  | 33.4575 | sqm | 3157.64 | 105646.892
5 | Providing and fixing Single Panel Casement (Hinged) door of aluminium section in natural or color anodized/powder coated color section size(102x45x1.5 mm) fitted with 5 mm clear glass of 9 mm both side laminated board (excluding the cost of handle and door closer).
| -Door | 2 |  | 0.9 | 2.1335 | 3.8403
| Sub-total |  |  |  |  | 3.8403 | sqm | 8129.71 | 31220.4651
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 187772.1964
| Total Estimated | 187772.1964
| VAT 13% | 24410.3855
| Grand Total | 212182.582