## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- सुन्दरबस्ती सडक ग्राबेल र ढलान (ढल निर्माण कार्य) | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/06/08
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -For hume pipe | 1 | 60.2 | 0.75 | 1.2 | 54.18
| -Manhole | 2 | 1.5 | 1.5 | 1.7 | 6.0083
| Sub-total |  |  |  |  | 60.1883 | m3 | 64.63 | 3889.9696
| VAT calculation | [7 empty] | 419.1312
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Manhole | 2 | 1.5 | 1.5 | 0.15 | 0.53014
| Sub-total |  |  |  |  | 0.53014 | m3 | 4561.53 | 2418.2667
| VAT calculation | [7 empty] | 212.9946
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -Manhole | 2 | 1.5 | 1.5 | 0.075 | 0.26507
| Sub-total |  |  |  |  | 0.26507 | m3 | 10634.5 | 2818.9069
| VAT calculation | [7 empty] | 278.0699
4 | C.I. Manhole cover including frame
| -Rounded manhole cover medium duty 500mm (24") | 2 |  |  |  | 2
| Sub-total |  |  |  |  | 2 | set | 7063 | 14126
| VAT calculation | [7 empty] | 1836.38
5 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -Rounded manhole cover medium duty 500mm (24") | 2 | 0.82479 | 0.23 | 1.5 | 1.7879
| -Deduction for opening | -5 | 0.6 | 0.23 | 0.6 | -0.32515 |  |  |  |  | 0.82 | 0.55877
| Sub-total |  |  |  |  | 1.4627 | m3 | 14362.76 | 21008.8543 |  | 0.50808 | 0.66138 | 0.58473
| VAT calculation | [7 empty] | 1960.8292
6 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 600 mm internal dia.
| -600mm dia hume pipe | 26 | 2.5 |  |  | 65 |  |  |  |  | 17.6 | 18 | 57.5
| Sub-total |  |  |  |  | 65 | m | 6932.79 | 450631.35 |  |  |  | 23
| VAT calculation | [7 empty] | 53245.0724
7 | Provisional sum for unforeseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
8 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 558845.8248
| Total Estimated | 558845.8248 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 84.9966
| User Contribution | 83845.8248 |  | 15.0034
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 558845.8248 |  |  |  |  | Total Valuated Amount : |  | 577558.6809
Work Started : | [7 empty] | Work Finished:
#REF! | [7 empty] | F.Y:2079/80
#REF! | [7 empty] | Date:2079/06/13
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | m3 | 60.1883 | 64.63 | 3889.9696 | 59.1068 | 64.63 | 3820.0727 | -69.8969
| VAT calculation |  |  |  | 419.1312 |  |  | 411.6001 | -7.5312
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | m3 | 0.53014 | 4561.53 | 2418.2667 | 0.43472 | 4561.53 | 1982.9787 | -435.288
| VAT calculation |  |  |  | 212.9946 |  |  | 174.6556 | -38.339
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 | m3 | 0.26507 | 10634.5 | 2818.9069 | 0.21736 | 10634.5 | 2311.5037 | -507.4032
| VAT calculation |  |  |  | 278.0699 |  |  | 228.0173 | -50.0526
4 | C.I. Manhole cover including frame | set | 2 | 7063 | 14126 | 2 | 7063 | 14126 | 0
| VAT calculation |  |  |  | 1836.38 |  |  | 1836.38 | 0
5 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | m3 | 1.4627 | 14362.76 | 21008.8543 | 3.0434 | 14362.76 | 43711.3213 | 22702.4671
| VAT calculation |  |  |  | 1960.8292 |  |  | 4079.7292 | 2118.9
6 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 600 mm internal dia. | m | 65 | 6932.79 | 450631.35 | 65 | 6932.79 | 450631.35 | 0
| VAT calculation |  |  |  | 53245.0724 |  |  | 53245.0724 | 0
7 | Provisional sum for unforeseen works | PS | 1 | 5000 | 5000 | 0 | 5000 | 0 | -5000
8 | Information board (सुचना पाटि) | no. | 1 | 1000 | 1000 | 1 | 1000 | 1000 | 0
| Total |  |  |  | 558845.8248 |  |  | 577558.6809 | 18712.8562

## valuated
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- सुन्दरबस्ती सडक ग्राबेल र ढलान (ढल निर्माण कार्य) | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/06/08
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -For hume pipe | 1 | 60.2 | 0.75 | 1.2 | 54.18
| -Manhole | 1 | 1.5 | 1.5 | 1.7 | 3.0041
|  | 1 | 1.2 | 1.2 | 1.7 | 1.9227
| Sub-total |  |  |  |  | 59.1068 | m3 | 64.63 | 3820.0727
| VAT calculation | [7 empty] | 411.6001
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Manhole | 1 | 1.5 | 1.5 | 0.15 | 0.26507
|  | 1 | 1.2 | 1.2 | 0.15 | 0.16965
| Sub-total |  |  |  |  | 0.43472 | m3 | 4561.53 | 1982.9787
| VAT calculation | [7 empty] | 174.6556
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -Manhole | 1 | 1.5 | 1.5 | 0.075 | 0.13254
|  | 1 | 1.2 | 1.2 | 0.075 | 0.084823
| Sub-total |  |  |  |  | 0.21736 | m3 | 10634.5 | 2311.5037
| VAT calculation | [7 empty] | 228.0173
4 | C.I. Manhole cover including frame
| -Rounded manhole cover medium duty 500mm (24") | 2 |  |  |  | 2
| Sub-total |  |  |  |  | 2 | set | 7063 | 14126
| VAT calculation | [7 empty] | 1836.38
5 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -Rounded manhole cover medium duty 500mm (24") | 2 | 0.82479 | 0.23 | 1.8287 | 2.1797
| -Deduction for opening | -3 | 0.6 | 0.23 | 0.6 | -0.19509 |  |  |  |  | 0.82 | 0.55877
| VAT calculation | 2 | 0.67479 | 0.23 | 1.2191 | 1.1888
| -Deduction for opening | -2 | 0.6 | 0.23 | 0.6 | -0.13006 |  |  |  |  | 0.82 | 0.55877
| Sub-total |  |  |  |  | 3.0434 | m3 | 14362.76 | 43711.3213 |  | 0.50808 | 0.66138 | 0.58473
| VAT calculation | [7 empty] | 4079.7292
6 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 600 mm internal dia.
| -600mm dia hume pipe | 26 | 2.5 |  |  | 65 |  |  |  |  | 17.6 | 18 | 57.5
| Sub-total |  |  |  |  | 65 | m | 6932.79 | 450631.35 |  |  |  | 23
| VAT calculation | [7 empty] | 53245.0724
7 | Provisional sum for unforeseen works | 0 |  |  |  | 0 | PS | 5000 | 0
8 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 577558.6809
| Total Estimated | 577558.6809 |  | 100
| Budget allocated | 500000
| Municipal payment | 490924.8788 |  | 85
| User Contribution | 86633.8021 |  | 15
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2