## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- वडा कार्यालय अगाडी ढलान गरि ब्लक बिछ्याउने कार्य | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -For stone masonary | 1 | 3.65 | 3.2 | 0.1 | 1.168
| -deduction for occupied area | -1 | 1.32 | 0.5 | 0.1 | -0.066
|  | -1 | 0.60957 | 0.60957 | 0.1 | -0.037158
| Sub-total |  |  |  |  | 1.0648 | m3 | 663.31 | 706.3206
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -For stone masonary | 1 | 3.65 | 3.2 | 0.1 | 1.168
| -deduction for occupied area | -1 | 1.32 | 0.5 | 0.1 | -0.066
|  | -1 | 0.60957 | 0.60957 | 0.1 | -0.037158
| Sub-total |  |  |  |  | 1.0648 | m3 | 4434.52 | 4722.065
| VAT calculation | [7 empty] | 410.2386
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For stone masonary | 1 | 3.65 | 3.2 | 0.05 | 0.584
| -deduction for occupied area | -1 | 1.32 | 0.5 | 0.05 | -0.033
|  | -1 | 0.60957 | 0.60957 | 0.05 | -0.018579
| Sub-total |  |  |  |  | 0.53242 | m3 | 10634.5 | 5662.0333
| VAT calculation | [7 empty] | 558.5289
4 | dfn;fdfg pknAw u/L %) dL=dL= df]6f] x]eL 8o"6L OG6/nls+u s+lqm6Ans %) dL=dL=df]6fOsf] qm;/ 8:6 dfyL /fvL la5ofpg]] sfd k'/f
| -For stone masonary | 1 | 3.65 | 3.2 |  | 11.68
| -deduction for occupied area | -1 | 1.32 | 0.5 |  | -0.66
| Sub-total |  |  |  |  | 11.02 | m2 | 1737.28 | 19144.8256
| VAT calculation | [7 empty] | 995.3418
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 32699.3539
| Total Estimated | 32699.3539
| Budget allocated | 28000
| Municipal payment | 26600 |  | 81.3472
| User Contribution | 6099.3539 |  | 18.6528
| Contingencies | 840 |  | 3
| Maintanince | 560 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 32699.3539 |  |  |  |  | Total Valuated Amount : |  | 32199.3539
Work Started : | [7 empty] | Work Finished:
Project:- वडा कार्यालय अगाडी ढलान गरि ब्लक बिछ्याउने कार्य | [7 empty] | F.Y:2081/82
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2082/01/12
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | m3 | 1.0648 | 663.31 | 706.3206 | 1.0648 | 663.31 | 706.3206 | 0
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | m3 | 1.0648 | 4434.52 | 4722.065 | 1.0648 | 4434.52 | 4722.065 | 0
| VAT calculation |  |  |  | 410.2386 |  |  | 410.2386 | 0
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 | m3 | 0.53242 | 10634.5 | 5662.0333 | 0.53242 | 10634.5 | 5662.0333 | 0
| VAT calculation |  |  |  | 558.5289 |  |  | 558.5289 | 0
4 | dfn;fdfg pknAw u/L %) dL=dL= df]6f] x]eL 8o"6L OG6/nls+u s+lqm6Ans %) dL=dL=df]6fOsf] qm;/ 8:6 dfyL /fvL la5ofpg]] sfd k'/f | m2 | 11.02 | 1737.28 | 19144.8256 | 11.02 | 1737.28 | 19144.8256 | 0
| VAT calculation |  |  |  | 995.3418 |  |  | 995.3418 | 0
5 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 0 | 500 | 0 | -500
| Total |  |  |  | 32699.3539 |  |  | 32199.3539 | -500

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- वडा कार्यालय अगाडी ढलान गरि ब्लक बिछ्याउने कार्य | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -For stone masonary | 1 | 3.65 | 3.2 | 0.1 | 1.168
| -deduction for occupied area | -1 | 1.32 | 0.5 | 0.1 | -0.066
|  | -1 | 0.60957 | 0.60957 | 0.1 | -0.037158
| Sub-total |  |  |  |  | 1.0648 | m3 | 663.31 | 706.3206
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -For stone masonary | 1 | 3.65 | 3.2 | 0.1 | 1.168
| -deduction for occupied area | -1 | 1.32 | 0.5 | 0.1 | -0.066
|  | -1 | 0.60957 | 0.60957 | 0.1 | -0.037158
| Sub-total |  |  |  |  | 1.0648 | m3 | 4434.52 | 4722.065
| VAT calculation | [7 empty] | 410.2386
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For stone masonary | 1 | 3.65 | 3.2 | 0.05 | 0.584
| -deduction for occupied area | -1 | 1.32 | 0.5 | 0.05 | -0.033
|  | -1 | 0.60957 | 0.60957 | 0.05 | -0.018579
| Sub-total |  |  |  |  | 0.53242 | m3 | 10634.5 | 5662.0333
| VAT calculation | [7 empty] | 558.5289
4 | dfn;fdfg pknAw u/L %) dL=dL= df]6f] x]eL 8o"6L OG6/nls+u s+lqm6Ans %) dL=dL=df]6fOsf] qm;/ 8:6 dfyL /fvL la5ofpg]] sfd k'/f
| -For stone masonary | 1 | 3.65 | 3.2 |  | 11.68
| -deduction for occupied area | -1 | 1.32 | 0.5 |  | -0.66
| Sub-total |  |  |  |  | 11.02 | m2 | 1737.28 | 19144.8256
| VAT calculation | [7 empty] | 995.3418
5 | Information board (सुचना पाटि) | 0 |  |  |  | 0 | no. | 500 | 0
| Grand Total | [7 empty] | 32199.3539
| Total Valuated | 32199.3539
| Budget allocated | 28000
| Municipal payment | 26600 |  | 82.6104
| User Contribution | 5599.3539 |  | 17.3896
| Contingencies | 840 |  | 3
| Maintanince | 560 |  | 2