## local
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:-चनौटे, घट्टेखोला सडक ग्राबेल | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/02/12
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Providing and laying local/ washing sub-base on prepared surface, mixing at OMC, and compacting to achieve the desired density, complete as per Drawing and Technical Specifications., By Mechanical means | [9 empty] | 135000 | 30000
| -for gabion wall base | 1 | 90 | 3.0479 | 0.125 | 34.2883 |  |  |  |  | unit |  | 300 | unit
| Sub-total |  |  |  |  | 34.2883 | m3 | 1693.85 | 58079.2822 |  | 3244.12 | 2820.9739 | 826398.7 | 2754.6623
| -VAT 13% calculation | [7 empty] | 6634.9894
2 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 65214.2716
| Total Estimated | 65214.2716 |  | 100
| Budget allocated | 50000
| Municipal payment | 47500 |  | 72.8368
| User Contribution | 17714.2716 |  | 27.1632
| Contingencies | 1500 |  | 3
| Maintanince | 1000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | #REF! |  |  |  |  | Total Valuated Amount : |  | #REF!
Work Started : | [7 empty] | Work Finished:
#REF! | [7 empty] | F.Y:2079/80
#REF! | [7 empty] | Date:2079/06/13
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  |  | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total |  |  |  | #REF! |  |  | #REF! | #REF!

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:-चनौटे, घट्टेखोला सडक ग्राबेल | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/02/12
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Providing and laying local/ washing sub-base on prepared surface, mixing at OMC, and compacting to achieve the desired density, complete as per Drawing and Technical Specifications., By Mechanical means | [9 empty] | L | W | H
| -Chainage at 0+000 | [10 empty] | 2.6669 | 0.12801
| Chainage at 0+000 to 0+005 | 1 | 5 | 2.705 | 0.12801 | 1.7313 |  |  |  |  | 5 | 2.7431 | 0.12801
| Chainage at 0+005 to 0+010 | 1 | 5 | 3.0479 | 0.1402 | 2.1366 |  |  |  |  | 5 | 3.3526 | 0.15239
| Chainage at 0+010 to 0+015 | 1 | 5 | 3.1341 | 0.12649 | 1.9821 |  |  |  |  | 5 | 2.9156 | 0.10058
| Chainage at 0+015 to 0+020 | 1 | 5 | 2.9055 | 0.12649 | 1.8375 |  |  |  |  | 5 | 2.8955 | 0.15239
| Chainage at 0+020 to 0+025 | 1 | 5 | 2.8193 | 0.15 | 2.1144 |  |  |  |  | 5 | 2.7431 | 0.17769
| Chainage at 0+025 to 0+030 | 1 | 5 | 2.6669 | 0.15 | 2.0002 |  |  |  |  | 5 | 2.5907 | 0.22859
| Chainage at 0+030 to 0+035 | 1 | 5 | 2.5907 | 0.15 | 1.943 |  |  |  |  | 5 | 2.5907 | 0.15239
| Chainage at 0+035 to 0+040 | 1 | 5 | 2.6669 | 0.12649 | 1.6866 |  |  |  |  | 5 | 2.7431 | 0.10058
| Chainage at 0+040 to 0+045 | 1 | 5 | 2.8447 | 0.10058 | 1.4306 |  |  |  |  | 5 | 2.9464 | 0.10058
| Chainage at 0+045 to 0+050 | 1 | 5 | 2.9464 | 0.11429 | 1.6838 |  |  |  |  | 5 | 2.9464 | 0.12801
| Chainage at 0+050 to 0+060 | 1 | 5 | 3.2135 | 0.12801 | 2.0568 |  |  |  |  | 5 | 3.4806 | 0.12801
| Chainage at 0+060 to 0+066 | 1 | 6 | 3.4806 | 0.1402 | 2.9279 |  |  |  |  | 6 | 3.4806 | 0.15239
| -Gravel | 1 | 8 | 3.1881 | 0.1512 | 3.8562 |  |  |  |  | 8 | 2.8955 | 0.15
| Sub-total |  |  |  |  | 27.387 | m3 | 1693.85 | 46389.4995
| -VAT 13% calculation | [7 empty] | 5299.5462
2 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 52189.0457
| Total Estimated | 52189.0457 |  | 100
| Budget allocated | 50000
| Municipal payment | 47500 |  | 91.0153
| User Contribution | 4689.0457 |  | 8.9847
| Contingencies | 1500 |  | 3
| Maintanince | 1000 |  | 2