## Estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- सुन्दरबस्ती सडक ग्राबेल र ढलान (ढल निर्माण कार्य) | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/06/08
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_ | [12 empty] | 0.397
| -slab | 1 | 18.28 | 9.14 | 0.12699 | 21.218 |  |  |  |  | 18.2871 | 9.1436
| -cantilever slab | 1 | 5.49 | 1.067 | 0.12699 | 0.74391 |  |  |  |  | 5.4938 | 1.0667
|  | 1 | 5.44 | 1.05 | 0.12699 | 0.72539
| -deduction for staircase area | -1 | 3.4 | 3.18 | 0.12699 | -1.3731 | [5 empty] | 0.40638 | 1.7192
| -column | 15 | 0.4 | 0.4 | 0.397 | 0.9528
| -beam | 6 | 4.6998 | 0.3 | 0.3566 | 3.0167
|  | 3 | 3.7092 | 0.3 | 0.3566 | 1.1904
|  | 3 | 3.1484 | 0.3 | 0.3566 | 1.0105
|  | 5 | 4.2161 | 0.3 | 0.3566 | 2.2552
|  | 5 | 3.7092 | 0.3 | 0.3566 | 1.9841
| Sub-total |  |  |  |  | 31.7239 | sqm | 13568.9 | 430458.1746
| VAT calculation | [7 empty] | 39278.7969
2 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -slab | 1 | 18.28 | 9.14 |  | 167.0792 |  |  |  |  | 18.2871 | 9.1436
| -cantilever slab | 1 | 5.49 | 1.067 |  | 5.8578 |  |  |  |  | 5.4938 | 1.0667
|  | 1 | 5.44 | 1.05 |  | 5.712
| -deduction for staircase area | -1 | 3.4 | 3.18 |  | -10.812 | [5 empty] | 0.40638 | 1.7192
| -column | 15 | 1.6 |  | 0.3566 | 8.5584
| -beam | 6 | 4.6998 |  | 0.7132 | 20.1112
|  | 3 | 3.7092 |  | 0.7132 | 7.9362
|  | 3 | 3.1484 |  | 0.7132 | 6.7364
|  | 5 | 4.2161 |  | 0.7132 | 15.0345
|  | 5 | 3.7092 |  | 0.7132 | 13.2271
| Sub-total |  |  |  |  | 239.4409 | sqm | 915.42 | 219188.9472
| VAT calculation | [7 empty] | 14576.2568
9 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 704002.1755
| Total Estimated | 704002.1755 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 67.4714
| User Contribution | 229002.1755 |  | 32.5286
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | #REF! |  |  |  |  | Total Valuated Amount : |  | #REF!
Work Started : | [7 empty] | Work Finished:
#REF! | [7 empty] | F.Y:2079/80
#REF! | [7 empty] | Date:2079/06/13
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  |  | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total |  |  |  | #REF! |  |  | #REF! | #REF!

## 500k estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- लाकिला भुमेथली सचितानन्द सन्त संघ मन्दिर निर्माण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/06/08
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_ | [12 empty] | 0.397
| -slab | 1 | 18.2 | 9.1 | 0.125 | 20.7025 |  |  |  |  | 18.2871 | 9.1436
| -cantilever slab | 0 | 5.49 | 1.067 | 0.125 | 0 |  |  |  |  | 5.4938 | 1.0667
|  | 0 | 5.44 | 1.05 | 0.125 | 0
| -deduction for staircase area | -1 | 3.4 | 3.18 | 0.125 | -1.3515 | [5 empty] | 0.40638 | 1.7192
| -column | 0 | 0.4 | 0.4 | 0.397 | 0
| -beam | 6 | 4.6998 | 0.3 | 0.3 | 2.5379
|  | 3 | 3.7092 | 0.3 | 0.3 | 1.0015
|  | 2 | 3.1484 | 0.3 | 0.3 | 0.56672
|  | 4 | 4.2161 | 0.3 | 0.3 | 1.5178
|  | 5 | 3.7092 | 0.3 | 0.3 | 1.6692
| Sub-total |  |  |  |  | 26.644 | sqm | 13568.9 | 361530.3795
| VAT calculation | [7 empty] | 32989.2175
2 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -slab | 1 | 18.2 | 9.1 |  | 165.62 |  |  |  |  | 18.2871 | 9.1436
| -cantilever slab | 0 | 5.49 | 1.067 |  | 0 |  |  |  |  | 5.4938 | 1.0667
|  | 0 | 5.44 | 1.05 |  | 0
| -deduction for staircase area | -1 | 3.4 | 3.18 |  | -10.812 | [5 empty] | 0.40638 | 1.7192
| -column | 0 | 1.6 |  | 0.3566 | 0
| -beam | 6 | 4.6998 |  | 0.6 | 16.9192
|  | 3 | 3.7092 |  | 0.6 | 6.6766
|  | 2 | 3.1484 |  | 0.6 | 3.7781
|  | 4 | 4.2161 |  | 0.6 | 10.1186
|  | 5 | 3.7092 |  | 0.6 | 11.1277
| Sub-total |  |  |  |  | 203.4283 | sqm | 915.42 | 186222.3332
| VAT calculation | [7 empty] | 12383.9481
3 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 593625.8783
| Total Estimated | 593625.8783 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 80.0167
| User Contribution | 118625.8783 |  | 19.9833
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2