## re-estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- गणपती गणेश मन्दिर मनोहरा नदीबाट कटान संरक्षण गर्ने | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/12/08
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Manual Means ., Roadway Excavation in all types of soil as per drawing and technical specification, including removal of stumps and other deleterious matter, with all lifts and lead as per Drawing and instruction of the Engineer.
| -for gabion wall | 1 | 13 | 2.9 | 1 | 37.7
| Sub-total |  |  |  |  | 37.7 | m3 | 64.63 | 2436.551
| -VAT 13% calculation | [7 empty] | 262.5302
2 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod(without watering)
| -for gabion wall | 1 | 13 | 0.5 | 1 | 6.5
| Sub-total |  |  |  |  | 6.5 | m3 | 404.28 | 2627.82
3 | Gabion Structure for Retaining Earth, Providing and laying Gabion structure for retaining earth with diaphragm including rolling, cutting, weaving, placing, laying sides and diaphragms with binding wire and filling boulders all complete as per drawing and technical specification Mesh wire- 10 Swg(0.0615 kg/m), Selvedge Wire 8 Swg ( 0.1057 kg/m), binding wire 12 Swg (0.0409 kg/m) Hexagonal mesh Type 100 mm X 120 mm,, Box size 2 X 1 X 1 m ( 11 sqm)
| -for gabion wall | 1 | 13 | 2.5 | 1 | 32.5
|  | 1 | 13 | 2 | 1 | 26
|  | 1 | 13 | 1.5 | 1 | 19.5
| Sub-total |  |  |  |  | 78 | m3 | 6509.3 | 507725.4 |  | 7485.69 | 4746.7977
| -VAT 13% calculation | [7 empty] | 48132.5317
4 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications.
| -for gabion wall back edge | 1 | 13 |  | 3 | 39
| Sub-total |  |  |  |  | 39 | m2 | 161.42 | 6295.38 |  | 7485.69 | 4746.7977
| -VAT 13% calculation | [7 empty] | 766.584
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 568746.797
| Total Estimated | 568746.797 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 83.517
| User Contribution | 93746.797 |  | 16.483
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 568746.797 |  |  |  |  | Total Valuated Amount : |  | 568795.2682
Work Started : | [7 empty] | Work Finished:
Project:- गणपती गणेश मन्दिर मनोहरा नदीबाट कटान संरक्षण गर्ने | [7 empty] | F.Y:2081/2082
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2082/02/20
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Manual Means ., Roadway Excavation in all types of soil as per drawing and technical specification, including removal of stumps and other deleterious matter, with all lifts and lead as per Drawing and instruction of the Engineer. | m3 | 37.7 | 64.63 | 2436.551 | 45.4 | 64.63 | 2934.202 | 497.651 |  | 3045.6887
| -VAT 13% calculation |  |  |  | 262.5302 |  |  | 316.1505 | 53.6202
2 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod(without watering) | m3 | 6.5 | 404.28 | 2627.82 | 6.6 | 404.28 | 2668.248 | 40.428 |  | 3284.775
3 | Gabion Structure for Retaining Earth, Providing and laying Gabion structure for retaining earth with diaphragm including rolling, cutting, weaving, placing, laying sides and diaphragms with binding wire and filling boulders all complete as per drawing and technical specification Mesh wire- 10 Swg(0.0615 kg/m), Selvedge Wire 8 Swg ( 0.1057 kg/m), binding wire 12 Swg (0.0409 kg/m) Hexagonal mesh Type 100 mm X 120 mm,, Box size 2 X 1 X 1 m ( 11 sqm) | m3 | 78 | 6509.3 | 507725.4 | 78 | 6509.3 | 507725.4 | 0
| -VAT 13% calculation |  |  |  | 48132.5317 |  |  | 48132.5317 | 0
4 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications. | m2 | 39 | 161.42 | 6295.38 | 36 | 161.42 | 5811.12 | -484.26
| -VAT 13% calculation |  |  |  | 766.584 |  |  | 707.616 | -58.968
5 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0
| Total |  |  |  | 568746.797 |  |  | 568795.2682 | 48.4712

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- गणपती गणेश मन्दिर मनोहरा नदीबाट कटान संरक्षण गर्ने | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2082/02/20
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Manual Means ., Roadway Excavation in all types of soil as per drawing and technical specification, including removal of stumps and other deleterious matter, with all lifts and lead as per Drawing and instruction of the Engineer.
| -for gabion wall | 1 | 14 | 2.9 | 1 | 40.6
|  | 1 | 2 | 2.4 | 1 | 4.8
| Sub-total |  |  |  |  | 45.4 | m3 | 64.63 | 2934.202
| -VAT 13% calculation | [7 empty] | 316.1505
2 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod(without watering)
| -for gabion wall | 1 | 14 | 0.45 | 1 | 6.3
|  | 1 | 2 | 0.3 | 0.5 | 0.3
| Sub-total |  |  |  |  | 6.6 | m3 | 404.28 | 2668.248
3 | Gabion Structure for Retaining Earth, Providing and laying Gabion structure for retaining earth with diaphragm including rolling, cutting, weaving, placing, laying sides and diaphragms with binding wire and filling boulders all complete as per drawing and technical specification Mesh wire- 10 Swg(0.0615 kg/m), Selvedge Wire 8 Swg ( 0.1057 kg/m), binding wire 12 Swg (0.0409 kg/m) Hexagonal mesh Type 100 mm X 120 mm,, Box size 2 X 1 X 1 m ( 11 sqm)
| -for gabion wall | 1 | 3 | 1 | 1 | 3
|  | 21 | 2 | 1 | 1 | 42
|  | 22 | 1.5 | 1 | 1 | 33
| Sub-total |  |  |  |  | 78 | m3 | 6509.3 | 507725.4 |  | 7485.69 | 4746.7977
| -VAT 13% calculation | [7 empty] | 48132.5317
4 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications.
| -for gabion wall back edge | 1 | 14 |  | 1 | 14
|  | 1 | 12 |  | 1 | 12
|  | 1 | 6 |  | 1 | 6
|  | 1 | 2 |  | 2 | 4
| Sub-total |  |  |  |  | 36 | m2 | 161.42 | 5811.12 |  | 7485.69 | 4746.7977
| -VAT 13% calculation | [7 empty] | 707.616
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 568795.2682
| Total Valuated | 568795.2682 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 83.5098
| User Contribution | 93795.2682 |  | 16.4902
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2

## M
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- गणपती गणेश मन्दिर मनोहरा नदीबाट कटान संरक्षण गर्ने | [9 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [9 empty] | Date: 2082/02/20
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Manual Means ., Roadway Excavation in all types of soil as per drawing and technical specification, including removal of stumps and other deleterious matter, with all lifts and lead as per Drawing and instruction of the Engineer.
| -for gabion wall | 1 | 14 | 2.9 | 1 | 40.6
|  | 1 | 2 | 2.4 | 1 | 4.8
| Sub-total |  |  |  |  | 45.4 | m3 | 64.63 | 2934.202
| -VAT 13% calculation | [7 empty] | 316.1505
2 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod(without watering)
| -for gabion wall | 1 | 14 | 0.45 | 1 | 6.3
|  | 1 | 2 | 0.3 | 0.5 | 0.3
| Sub-total |  |  |  |  | 6.6 | m3 | 404.28 | 2668.248
3 | Gabion Structure for Retaining Earth, Providing and laying Gabion structure for retaining earth with diaphragm including rolling, cutting, weaving, placing, laying sides and diaphragms with binding wire and filling boulders all complete as per drawing and technical specification Mesh wire- 10 Swg(0.0615 kg/m), Selvedge Wire 8 Swg ( 0.1057 kg/m), binding wire 12 Swg (0.0409 kg/m) Hexagonal mesh Type 100 mm X 120 mm,, Box size 2 X 1 X 1 m ( 11 sqm)
| -for gabion wall | 1 | 3 | 1 | 1 | 3
|  | 21 | 2 | 1 | 1 | 42
|  | 22 | 1.5 | 1 | 1 | 33
| Sub-total |  |  |  |  | 78 | m3 | 6509.3 | 507725.4 |  | 7485.69 | 4746.7977
| -VAT 13% calculation | [7 empty] | 48132.5317
4 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications.
| -for gabion wall back edge | 1 | 14 |  | 1 | 14
|  | 1 | 12 |  | 1 | 12
|  | 1 | 6 |  | 1 | 6
|  | 1 | 2 |  | 2 | 4
| Sub-total |  |  |  |  | 36 | m2 | 161.42 | 5811.12 |  | 7485.69 | 4746.7977
| -VAT 13% calculation | [7 empty] | 707.616
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 568795.2682
| Total Valuated | 568795.2682 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 83.5098
| User Contribution | 93795.2682 |  | 16.4902
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2