## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | #REF! |  |  |  |  | Total Valuated Amount : |  | #REF!
Work Started : | [7 empty] | Work Finished:
#REF! | [7 empty] | F.Y:2079/80
#REF! | [7 empty] | Date:2079/06/13
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  |  | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total |  |  |  | #REF! |  |  | #REF! | #REF!

## Estimate (3)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- Ukhutaar bhitri sadak | [6 empty] | F.Y.: 2081/2082 |  |  |  |  | subservience
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/28
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks | 45m
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य) | [9 empty] | 13m | ht=3'9"
| -For stone masonary | 0.5 | 10 | 0.90674 | 1.8135 | 8.2217
|  | 0.5 | 20 | 0.90674 | 0.9 | 8.1606
| -for hume pipe | 1 | 30 | 0.5 | 1.2 | 18
| Sub-total |  |  |  |  | 34.3823 | m3 | 64.63 | 2222.1293
| VAT calculation | [7 empty] | 239.427
2 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod(without watering)
| -for road | 0.5 | 20 | 4.8671 | 1.5 | 73.0067
| Sub-total |  |  |  |  | 73.0067 | m3 | 404.28 | 29515.1508
3 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -For stone masonary | 1 | 30 | 0.90674 | 0.15 | 4.0803
| -for road | 1 | 30 | 4.8671 | 0.15 | 21.902
| -manhole | 2 | 1.8 | 1.8 | 0.15 | 0.76341
| Sub-total |  |  |  |  | 26.7457 | m3 | 4434.52 | 118604.4723
| VAT calculation | [7 empty] | 10303.9955
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 20
| -for road | 1 | 30 | 4.8671 | 0.15 | 21.902
| Sub-total |  |  |  |  | 21.902 | m3 | 11588.17 | 253804.2336
| VAT calculation | [7 empty] | 25691.3531
5 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For stone masonary | 1 | 30 | 0.90674 | 0.075 | 2.0402
|  | 1 | 30 | 0.5 | 0.05 | 0.75
| -manhole | 2 | 1.8 | 1.8 | 0.08 | 0.40715
| Sub-total |  |  |  |  | 3.1973 | m3 | 10634.5 | 34001.749
| VAT calculation | [7 empty] | 3354.0885
6 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -For stone masonary | 1 | 30 | 0.70337 | 1.8135 | 38.2661
| Sub-total |  |  |  |  | 38.2661 | m3 | 9709.43 | 371542.2907
| VAT calculation | [7 empty] | 26954.4539
7 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -for road | 200 | 29.9 | 0.88889 | 5315.5556 | 5.3156
| -For stirrups | 32 | 4.7671 | 0.88889 | 135.5979 | 0.1356
| Sub-total |  |  |  |  | 5.4512 | MT | 131940 | 719225.187
| VAT calculation | [7 empty] | 75258.6246
8 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia. | 12 | 2.5 |  |  | 30
| Sub-total |  |  |  |  | 30 | rm | 5144.96 | 154348.8
| VAT calculation | [7 empty] | 17897.7552
9 | Providing and laying Brick masonry work in superstructure/ sub-structure complete excluding pointing and plastering, as per drawing and Technical Specifications, Cement Mortar 1:6 (1 cement : 6 sand)
| -manhole | 1 | 0.96908 | 0.35 | 3.3526 | 3.5724
| -Deduction for opening | -3 | 0.6 | 0.35 | 0.6 | -0.29688 |  |  |  |  | 0.82 | 0.55877
| -manhole | 1 | 0.70479 | 0.35 | 2.1335 | 1.6534
| -Deduction for opening | -2 | 0.6 | 0.35 | 0.6 | -0.19792 |  |  |  |  | 0.82 | 0.55877
| Sub-total |  |  |  |  | 4.731 | m3 | 15258.1565 | 72186.1259 |  | 0.50808 | 0.66138 | 0.58473
| VAT calculation | [7 empty] | 6745.1125
10 | C.I. Manhole cover including frame
| -Rounded manhole cover medium duty 500mm (24") | 2 |  |  |  | 2
| Sub-total |  |  |  |  | 2 | set | 7063 | 14126
| VAT calculation | [7 empty] | 1836.38
11 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500 |  |  |  | 1 | 20 | 0.05
[13 empty] | 1 | 16.6667 | 0.06
| Grand Total | [7 empty] | 1938357.3289 |  |  |  | 1 | 14.2857 | 0.07
[13 empty] | 1 | 12.5 | 0.08
| Total Estimated | 1938357.3289 |  | 100 | [8 empty] | 1 | 11.1111 | 0.09
| Budget allocated | 1300000 | [10 empty] | 1 | 9.0909 | 0.11
| Municipal payment | 1235000 |  | 63.7137 | [8 empty] | 1 | 8.3333 | 0.12
| User Contribution | 703357.3289 |  | 36.2863
| Contingencies | 39000 |  | 3
| Maintanince | 26000 |  | 2

## quotation single wall
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- Ukhutaar bhitri sadak | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य)
| -For stone masonary | 0.5 | 10 | 0.90674 | 1.8135 | 8.2217
|  | 0.5 | 20 | 0.90674 | 0.9 | 8.1606
| -for hume pipe | 1 | 30 | 0.5 | 1.2 | 18
| Sub-total |  |  |  |  | 34.3823 | m3 | 74.3245 | 2555.4487
2 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod(without watering)
| -for road | 0.5 | 20 | 4.8671 | 1.5 | 73.0067
| Sub-total |  |  |  |  | 73.0067 | m3 | 464.922 | 33942.4234
3 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -For stone masonary | 1 | 30 | 0.90674 | 0.15 | 4.0803
| -for road | 1 | 30 | 4.8671 | 0.15 | 21.902
| -manhole | 2 | 1.8 | 1.8 | 0.15 | 0.76341
| Sub-total |  |  |  |  | 26.7457 | m3 | 5099.698 | 136395.1431
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 20
| -for road | 1 | 30 | 4.8671 | 0.15 | 21.902
| Sub-total |  |  |  |  | 21.902 | m3 | 13326.3955 | 291874.8686
5 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For stone masonary | 1 | 30 | 0.90674 | 0.075 | 2.0402
|  | 1 | 30 | 0.5 | 0.05 | 0.75
| -manhole | 2 | 1.8 | 1.8 | 0.08 | 0.40715
| Sub-total |  |  |  |  | 3.1973 | m3 | 12229.675 | 39102.0114
6 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -For stone masonary | 1 | 30 | 0.70337 | 1.8135 | 38.2661
| Sub-total |  |  |  |  | 38.2661 | m3 | 11165.8445 | 427273.6343
7 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -for road | 200 | 29.9 | 0.88889 | 5315.5556 | 5.3156
| -For stirrups | 32 | 4.7671 | 0.88889 | 135.5979 | 0.1356
| Sub-total |  |  |  |  | 5.4512 | MT | 151731 | 827108.965
8 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia. | 12 | 2.5 |  |  | 30
| Sub-total |  |  |  |  | 30 | rm | 5916.704 | 177501.12
9 | Providing and laying Brick masonry work in superstructure/ sub-structure complete excluding pointing and plastering, as per drawing and Technical Specifications, Cement Mortar 1:6 (1 cement : 6 sand)
| -manhole | 1 | 0.96908 | 0.35 | 3.3526 | 3.5724
| -Deduction for opening | -3 | 0.6 | 0.35 | 0.6 | -0.29688
| -manhole | 1 | 0.70479 | 0.35 | 2.1335 | 1.6534
| -Deduction for opening | -2 | 0.6 | 0.35 | 0.6 | -0.19792
| Sub-total |  |  |  |  | 4.731 | m3 | 17546.88 | 83014.0447
10 | C.I. Manhole cover including frame
| -Rounded manhole cover medium duty 500mm (24") | 2 |  |  |  | 2
| Sub-total |  |  |  |  | 2 | set | 7063 | 14126
11 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 2033393.6593
| Total Estimated | 2033393.6593
| VAT 13% | 264341.1757
| Grand total | 2297734.835

## in nepali
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- Ukhutaar bhitri sadak | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने कार्य)
| -For stone masonary | 1 | 10 | 0.90674 | 1.8135 | 16.4434
|  | 1 | 20 | 0.90674 | 0.9 | 16.3212
| -for hume pipe | 2 | 30 | 0.5 | 2.7431 | 82.292
| Sub-total |  |  |  |  | 115.0566 | m3 | 74.3245 | 8551.5259
2 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod(without watering) (पुर्ने कार्य)
| -for road | 0.5 | 20 | 4.8671 | 1.5 | 73.0067
| Sub-total |  |  |  |  | 73.0067 | m3 | 464.922 | 33942.4234
3 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. (ढुंगा सोलिंग )
| -For stone masonary | 2 | 30 | 0.90674 | 0.15 | 8.1606
| -for road | 1 | 30 | 4.8671 | 0.15 | 21.902 |  |  |  |  | 1290916.94 | 1458736.1422
| -manhole | 2 | 1.8 | 1.8 | 0.15 | 0.76341 |  |  |  |  | 167819.2022
| Sub-total |  |  |  |  | 30.826 | m3 | 5099.698 | 157203.4964
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 20 (आर सी सी ढलान )
| -for road | 1 | 30 | 4.8671 | 0.15 | 21.902
| Sub-total |  |  |  |  | 21.902 | m3 | 13326.3955 | 291874.8686
5 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 (पी सी सी)
| -For stone masonary | 2 | 30 | 0.90674 | 0.075 | 4.0803
|  | 2 | 30 | 0.5 | 0.05 | 1.5
| -manhole | 2 | 1.8 | 1.8 | 0.08 | 0.40715
| Sub-total |  |  |  |  | 5.9875 | m3 | 12229.675 | 73224.7056
6 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications. (ढुंगा वाल )
| -For stone masonary | 2 | 30 | 0.70337 | 1.8135 | 76.5323
| Sub-total |  |  |  |  | 76.5323 | m3 | 11165.8445 | 854547.2686
7 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -for road | 200 | 29.9 | 0.88889 | 5315.5556 | 5.3156
| -For stirrups | 32 | 4.7671 | 0.88889 | 135.5979 | 0.1356
| Sub-total |  |  |  |  | 5.4512 | MT | 151731 | 827108.965
8 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia. (ह्युम पाइप) | 12 | 2.5 |  |  | 30
| Sub-total |  |  |  |  | 30 | rm | 5916.704 | 177501.12
9 | Providing and laying Brick masonry work in superstructure/ sub-structure complete excluding pointing and plastering, as per drawing and Technical Specifications, Cement Mortar 1:6 (1 cement : 6 sand) (मंगाल इट्टा वाल )
| -manhole | 1 | 0.96908 | 0.35 | 3.3526 | 3.5724
| -Deduction for opening | -3 | 0.6 | 0.35 | 0.6 | -0.29688
| -manhole | 1 | 0.70479 | 0.35 | 2.1335 | 1.6534
| -Deduction for opening | -2 | 0.6 | 0.35 | 0.6 | -0.19792
| Sub-total |  |  |  |  | 4.731 | m3 | 17546.88 | 83014.0447
10 | C.I. Manhole cover including frame (मंगाल को ढकनी)
| -Rounded manhole cover medium duty 500mm (24") | 2 |  |  |  | 2
| Sub-total |  |  |  |  | 2 | set | 7063 | 14126
11 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 2521594.4183
| Total Estimated | 2521594.4183
| VAT 13% | 327807.2744
| Grand total | 2849401.6927