## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | #REF! |  |  |  |  | Total Valuated Amount : |  | #REF!
Work Started : | [7 empty] | Work Finished:
#REF! | [7 empty] | F.Y:2079/80
#REF! | [7 empty] | Date:2079/06/13
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  |  | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total |  |  |  | #REF! |  |  | #REF! | #REF!

## bendol estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- बिन्ध्यबासिनी मन्दिर जाने सडक ढलान | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/07/14
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks | 45m
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | [9 empty] | 13m | ht=3'9"
| -Road | 1 | 15 | 4.267 | 0.15 | 9.6007
| Sub-total |  |  |  |  | 9.6007 | m3 | 64.63 | 620.4953
| VAT calculation | [7 empty] | 66.8563
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Road | 1 | 15 | 4.267 | 0.15 | 9.6007
| Sub-total |  |  |  |  | 9.6007 | m3 | 4561.53 | 43794.0247
| VAT calculation | [7 empty] | 3857.2628
3 | Providing and laying , fitting and placing HYSD bar reinforcement in sub-structure complete as per Drawing and Technical Specifications | No. | Length (m) | Unit Weight (kg/m) | Total Weight (Kg)
| -Road | 98 | 4.167 | 0.61728 | 252.0773 | 0.25208
|  | 27 | 14.7 | 0.39506 | 156.8 | 0.1568
| Sub-total |  |  |  |  | 0.40888 | m3 | 124140 | 50758.0255
| VAT calculation | [7 empty] | 5897.973
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 20
| -Road | 1 | 15 | 4.267 | 0.15 | 9.6007
| Sub-total |  |  |  |  | 9.6007 | m3 | 11588.17 | 111254.9086
| VAT calculation | [7 empty] | 11261.7867
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 228011.3329
| Total Estimated | 228011.3329 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 83.3292
| User Contribution | 38011.3329 |  | 16.6708
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2