## bendol estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- बेनडोल सडक नयाँबस्ती | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/07/11
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks | 45m
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | [9 empty] | 13m | ht=3'9"
| -Road | 1 | 18.4 | 4.267 | 0.15 | 11.7769
| Sub-total |  |  |  |  | 11.7769 | m3 | 64.63 | 761.1409
| VAT calculation | [7 empty] | 82.0104
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Road | 1 | 18.4 | 4.267 | 0.15 | 11.7769
| Sub-total |  |  |  |  | 11.7769 | m3 | 4561.53 | 53720.6703
| VAT calculation | [7 empty] | 4731.5758
3 | Providing and laying , fitting and placing HYSD bar reinforcement in sub-structure complete as per Drawing and Technical Specifications | No. | Length (m) | Unit Weight (kg/m) | Total Weight (Kg)
| -Road | 120 | 4.167 | 0.61728 | 308.6661 | 0.30867
|  | 27 | 18.1 | 0.39506 | 193.0667 | 0.19307
| Sub-total |  |  |  |  | 0.50173 | MT | 124140 | 62285.1003
| VAT calculation | [7 empty] | 7237.3942
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 20
| -Road | 1 | 18.4 | 4.267 | 0.15 | 11.7769
| Sub-total |  |  |  |  | 11.7769 | m3 | 11588.17 | 136472.6878
| VAT calculation | [7 empty] | 13814.4583
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 280105.038
| Total Estimated | 280105.038 |  | 100
| Budget allocated | 250000
| Municipal payment | 237500 |  | 84.7896
| User Contribution | 42605.038 |  | 15.2104
| Contingencies | 7500 |  | 3
| Maintanince | 5000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 280105.038 |  |  |  |  | Total Valuated Amount : |  | 280414.1529
Work Started : | [7 empty] | Work Finished:
Project:- बेनडोल सडक नयाँबस्ती | [7 empty] | F.Y:2081/82
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2081/08/03
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | m3 | 11.7769 | 64.63 | 761.1409 | 12.1751 | 64.63 | 786.8784 | 25.7376
| VAT calculation |  |  |  | 82.0104 |  |  | 84.7835 | 2.7731
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | m3 | 11.7769 | 4561.53 | 53720.6703 | 12.1757 | 4561.53 | 55539.9984 | 1819.3281
| VAT calculation |  |  |  | 4731.5758 |  |  | 4891.8174 | 160.2416
3 | Providing and laying , fitting and placing HYSD bar reinforcement in sub-structure complete as per Drawing and Technical Specifications | MT | 0.50173 | 124140 | 62285.1003 | 0.49182 | 124140 | 61053.9346 | -1231.1658
| VAT calculation |  |  |  | 7237.3942 |  |  | 7094.3354 | -143.0588
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 20 | m3 | 11.7769 | 11588.17 | 136472.6878 | 11.7514 | 11588.17 | 136177.7973 | -294.8906
| VAT calculation |  |  |  | 13814.4583 |  |  | 13784.608 | -29.8503
5 | Information board (सुचना पाटि) | no. | 1 | 1000 | 1000 | 1 | 1000 | 1000 | 0
| Total |  |  |  | 280105.038 |  |  | 280414.1529 | 309.115

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- बेनडोल सडक नयाँबस्ती | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/07/11
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks | 45m
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | [9 empty] | 13m | ht=3'9"
| -Road | 1 | 20.2 | 4.0182 | 0.15 | 12.1751
| Sub-total |  |  |  |  | 12.1751 | m3 | 64.63 | 786.8784 |  | 0 | 13.917 | 4.2419
| VAT calculation | [7 empty] | 84.7835 |  | 2 | 13.917 | 4.2419 | 4.2419
[11 empty] | 2 | 13.5 | 4.1148 | 4.1784
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | [9 empty] | 2 | 13.083 | 3.9877 | 4.0512
| Chainage 0+000 to 0+002 | 1 | 2 | 4.2419 | 0.15 | 1.2726 |  |  |  |  | 2 | 12.25 | 3.7338 | 3.8607
| Chainage 0+002 to 0+004 | 1 | 2 | 4.1784 | 0.15 | 1.2535 |  |  |  |  | 2 | 12.33 | 3.7582 | 3.746
| Chainage 0+004 to 0+006 | 1 | 2 | 4.0512 | 0.15 | 1.2154 |  |  |  |  | 2 | 12.917 | 3.9371 | 3.8476
| Chainage 0+006 to 0+008 | 1 | 2 | 3.8607 | 0.15 | 1.1582 |  |  |  |  | 2 | 13.5 | 4.1148 | 4.026
| Chainage 0+008 to 0+010 | 1 | 2 | 3.746 | 0.15 | 1.1238 |  |  |  |  | 2 | 13.5 | 4.1148 | 4.1148
| Chainage 0+010 to 0+012 | 1 | 2 | 3.8476 | 0.15 | 1.1543 |  |  |  |  | 2 | 13.25 | 4.0386 | 4.0767
| Chainage 0+012 to 0+014 | 1 | 2 | 4.026 | 0.15 | 1.2078 |  |  |  |  | 2.2 | 13.25 | 4.0386 | 4.0386
| Chainage 0+014 to 0+016 | 1 | 2 | 4.1148 | 0.15 | 1.2344
| Chainage 0+016 to 0+018 | 1 | 2 | 4.0767 | 0.15 | 1.223
| Chainage 0+018 to 0+020.2 | 1 | 2.2 | 4.0386 | 0.15 | 1.3327
| Sub-total |  |  |  |  | 12.1757 | m3 | 4561.53 | 55539.9984
| VAT calculation | [7 empty] | 4891.8174
3 | Providing and laying , fitting and placing HYSD bar reinforcement in sub-structure complete as per Drawing and Technical Specifications | No. | Length (m) | Unit Weight (kg/m) | Total Weight (Kg)
| -Road | 53 | 3.8098 | 0.61728 | 124.6421 | 0.12464
|  | 26 | 5.9189 | 0.39506 | 60.7969 | 0.060797
|  | 39 | 3.886 | 0.61728 | 93.5521 | 0.093552
|  | 25 | 5.9189 | 0.39506 | 58.4585 | 0.058459
|  | 39 | 3.9113 | 0.61728 | 94.1611 | 0.094161
|  | 25 | 6.0957 | 0.39506 | 60.2045 | 0.060204
| Sub-total |  |  |  |  | 0.49182 | MT | 124140 | 61053.9346
| VAT calculation | [7 empty] | 7094.3354
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 20
| Chainage 0+000 to 0+002 | 1 | 2 | 4.2419 | 0.14477 | 1.2282
| Chainage 0+002 to 0+004 | 1 | 2 | 4.1784 | 0.14477 | 1.2098
| Chainage 0+004 to 0+006 | 1 | 2 | 4.0512 | 0.14477 | 1.173
| Chainage 0+006 to 0+008 | 1 | 2 | 3.8607 | 0.14477 | 1.1179
| Chainage 0+008 to 0+010 | 1 | 2 | 3.746 | 0.14477 | 1.0846
| Chainage 0+010 to 0+012 | 1 | 2 | 3.8476 | 0.14477 | 1.1141
| Chainage 0+012 to 0+014 | 1 | 2 | 4.026 | 0.14477 | 1.1657
| Chainage 0+014 to 0+016 | 1 | 2 | 4.1148 | 0.14477 | 1.1914
| Chainage 0+016 to 0+018 | 1 | 2 | 4.0767 | 0.14477 | 1.1804
| Chainage 0+018 to 0+020.2 | 1 | 2.2 | 4.0386 | 0.14477 | 1.2863
| Sub-total |  |  |  |  | 11.7514 | m3 | 11588.17 | 136177.7973
| VAT calculation | [7 empty] | 13784.608
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 280414.1529
| Total Valuated | 280414.1529 |  | 100
| Budget allocated | 250000
| Municipal payment | 237500 |  | 84.6962
| User Contribution | 42914.1529 |  | 15.3038
| Contingencies | 7500 |  | 3
| Maintanince | 5000 |  | 2

## re-estimate (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- बेनडोल सडक नयाँबस्ती | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/07/11
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks | 45m
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | [9 empty] | 13m | ht=3'9"
| -Road | 1 | 19.85 | 3.9622 | 0.15 | 11.7975
| Sub-total |  |  |  |  | 11.7975 | m3 | 64.63 | 762.4705
| VAT calculation | [7 empty] | 82.1537
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Road | 1 | 19.85 | 3.9622 | 0.15 | 11.7975
| Sub-total |  |  |  |  | 11.7975 | m3 | 4561.53 | 53814.5146
| VAT calculation | [7 empty] | 4739.8413
3 | Providing and laying , fitting and placing HYSD bar reinforcement in sub-structure complete as per Drawing and Technical Specifications | No. | Length (m) | Unit Weight (kg/m) | Total Weight (Kg)
| -Road | 130 | 3.8622 | 0.61728 | 309.9302 | 0.30993
|  | 25 | 19.55 | 0.39506 | 193.0864 | 0.19309
| Sub-total |  |  |  |  | 0.50302 | m3 | 124140 | 62444.4786
| VAT calculation | [7 empty] | 7255.9136
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 20
| -Road | 1 | 19.85 | 3.9622 | 0.15 | 11.7975
| Sub-total |  |  |  |  | 11.7975 | m3 | 11588.17 | 136711.0912
| VAT calculation | [7 empty] | 13838.5907
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 280649.0542
| Total Estimated | 280649.0542 |  | 100
| Budget allocated | 250000
| Municipal payment | 237500 |  | 84.6253
| User Contribution | 43149.0542 |  | 15.3747
| Contingencies | 7500 |  | 3
| Maintanince | 5000 |  | 2