## Estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- दडुखेल पहिरो हटाउने तथा खुलालटार बाटो नाली सरसफाई कार्य | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/04/21
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Manual Means ., Roadway Excavation in all types of soil as per drawing and technical specification, including removal of stumps and other deleterious matter, with all lifts and lead as per Drawing and instruction of the Engineer.
| -River side Khulaltaar drain | 1 | 105 | 0.465 | 0.63441 | 30.9751
| -dadhukhel pahiro | 0.5 | 7.3 | 0.9 | 0.9 | 2.9565
| Sub-total |  |  |  |  | 33.9316 | cum | 736.88 | 25003.5027
2 | Information board | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 25503.5027
| Total Estimated | 25503.5027

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 25503.5027 |  |  |  |  | Total Valuated Amount : |  | 25003.5027
Work Started : | [7 empty] | Work Finished:
Project:- दडुखेल पहिरो हटाउने तथा खुलालटार बाटो नाली सरसफाई कार्य | [7 empty] | F.Y:2081/2082
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2081/04/25
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Manual Means ., Roadway Excavation in all types of soil as per drawing and technical specification, including removal of stumps and other deleterious matter, with all lifts and lead as per Drawing and instruction of the Engineer. | cum | 33.9316 | 736.88 | 25003.5027 | 33.9316 | 736.88 | 25003.5027 | 0
2 | Information board | no. | 1 | 500 | 500 | 0 | 500 | 0 | -500
| Total |  |  |  | 25503.5027 |  |  | 25003.5027 | -500

## valuated
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- दडुखेल पहिरो हटाउने तथा खुलालटार बाटो नाली सरसफाई कार्य | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/04/25
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Manual Means ., Roadway Excavation in all types of soil as per drawing and technical specification, including removal of stumps and other deleterious matter, with all lifts and lead as per Drawing and instruction of the Engineer.
| -River side Khulaltaar drain | 1 | 105 | 0.465 | 0.63441 | 30.9751
| -dadhukhel pahiro | 0.5 | 7.3 | 0.9 | 0.9 | 2.9565
| Sub-total |  |  |  |  | 33.9316 | cum | 736.88 | 25003.5027
2 | Information board | 0 |  |  |  | 0 | no. | 500 | 0
| Total | [7 empty] | 25003.5027
| Total Estimated | 25003.5027

## Measurement
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- दडुखेल पहिरो हटाउने तथा खुलालटार बाटो नाली सरसफाई कार्य | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/04/25
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Manual Means ., Roadway Excavation in all types of soil as per drawing and technical specification, including removal of stumps and other deleterious matter, with all lifts and lead as per Drawing and instruction of the Engineer.
| -River side Khulaltaar drain | 1 | 105 | 0.465 | 0.63441 | 30.9751
| -dadhukhel pahiro | 0.5 | 7.3 | 0.9 | 0.9 | 2.9565
| Sub-total |  |  |  |  | 33.9316 | cum | 736.88 | 25003.5027
2 | Information board | 0 |  |  |  | 0 | no. | 500 | 0
| Total | [7 empty] | 25003.5027
| Total Estimated | 25003.5027