## Estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- कुसुमथली पहिरो संरक्षण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
|  | 1 | 22.5 | 0.82 | 1.6 | 29.52 | [5 empty] | 0.76
| Sub-total |  |  |  |  | 29.52 | m3 | 663.31 | 19580.9112
2 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance
| -for empty bag filling | 30 | 22.5 | 0.38 | 60 | 1800 |  |  |  | labour cost only
| Sub-total |  |  |  |  | 1800 | sack | 92 | 165600
3 | Providing and laying Bamboo for the protection all complete
| -vertical post | 24 | 4 |  |  | 96
| -horizontal post | 8 | 22.5 |  |  | 180
| Sub-total |  |  |  |  | 47 | No. | 240 | 11280
| VAT calculation | [7 empty] | 1466.4
4 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod(without watering)
| -for back filling | 1 | 49.9957 | 0.95 | 0.9 | 42.7464
| Sub-total |  |  |  |  | 42.7464 | cum | 404.28 | 17281.4961
5 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 9000 | 9000
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 224708.8073 |  | 224711.9053
| Total Estimated | 224708.8073 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 84.5539
| User Contribution | 34708.8073 |  | 15.4461
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 224708.8073 |  |  |  |  | Total Valuated Amount : |  | 225347.3848
Work Started : | [7 empty] | Work Finished:
Project:- कुसुमथली पहिरो संरक्षण | [7 empty] | F.Y:2081/2082
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2082/03/03
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | m3 | 29.52 | 663.31 | 19580.9112 | 23.4037 | 663.31 | 15523.9133 | -4056.9979 |  |  | 24476.139
2 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance | sack | 1800 | 92 | 165600 | 1867 | 92 | 171764 | 6164 |  |  | 207000
3 | Providing and laying Bamboo for the protection all complete | No. | 47 | 240 | 11280 | 30 | 240 | 7200 | -4080 |  |  | 14100
| VAT calculation |  |  |  | 1466.4 |  |  | 936 | -530.4 |  |  | 1833
4 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod(without watering) | cum | 42.7464 | 404.28 | 17281.4961 | 50.5181 | 404.28 | 20423.4715 | 3141.9754 |  |  | 21601.8702
5 | Provisional sum for unforseen works | PS | 1 | 9000 | 9000 | 1 | 9000 | 9000 | 0 |  |  | 11250
6 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0 |  |  | 625
| Total |  |  |  | 224708.8073 |  |  | 225347.3848 | 638.5775
[10 empty] | 1070 | 70.2278 | 75143.7929

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- कुसुमथली पहिरो संरक्षण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2082/03/03
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
|  | 0.5 | 67.3575 | 0.38 | 1.8287 | 23.4037
| Sub-total |  |  |  |  | 23.4037 | m3 | 663.31 | 15523.9133
2 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance
| -for empty bag filling | 1867 |  |  |  | 1867 |  |  |  | labour cost only
| Sub-total |  |  |  |  | 1867 | sack | 92 | 171764
3 | Providing and laying Bamboo for the protection all complete
| -vertical post | 65 | 2.5 |  |  | 162.5
| -horizontal post | 1 | 377.9336 |  |  | 15.7472
| Sub-total |  |  |  |  | 30 | No. | 240 | 7200
| VAT calculation | [7 empty] | 936
4 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod(without watering)
| -for back filling | 1 | 67.3575 | 0.5 | 1.5 | 50.5181
| Sub-total |  |  |  |  | 50.5181 | cum | 404.28 | 20423.4715
5 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 9000 | 9000
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 225347.3848
| Total Valuated | 225347.3848 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 84.3143
| User Contribution | 35347.3848 |  | 15.6857
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2

## M
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- कुसुमथली पहिरो संरक्षण | [9 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [9 empty] | Date:2082/03/03
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
|  | 0.5 | 67.3575 | 0.38 | 1.8287 | 23.4037
| Sub-total |  |  |  |  | 23.4037 | m3 | 663.31 | 15523.9133
2 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance
| -for empty bag filling | 1867 |  |  |  | 1867 |  |  |  | labour cost only
| Sub-total |  |  |  |  | 1867 | sack | 92 | 171764
3 | Providing and laying Bamboo for the protection all complete
| -vertical post | 65 | 2.5 |  |  | 162.5
| -horizontal post | 1 | 377.9336 |  |  | 15.7472
| Sub-total |  |  |  |  | 30 | No. | 240 | 7200
| VAT calculation | [7 empty] | 936
4 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod(without watering)
| -for back filling | 1 | 67.3575 | 0.5 | 1.5 | 50.5181
| Sub-total |  |  |  |  | 50.5181 | cum | 404.28 | 20423.4715
5 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 9000 | 9000
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 225347.3848
| Total Valuated | 225347.3848 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 84.3143
| User Contribution | 35347.3848 |  | 15.6857
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2