## 200k
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- कुर्थली च्यानेपाखा माझगाउँ जोड्ने सडक | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/10/09
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks | 45m
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | [9 empty] | 13m | ht=3'9"
| -For wall | 0.5 | 5.5 | 2 | 3.5 | 19.25
| Sub-total |  |  |  |  | 19.25 | m3 | 64.63 | 1244.1275
| VAT calculation | [7 empty] | 134.0506
2 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod
| -Road | 0.5 | 5.5 | 1.5 | 1.75 | 7.2188
| Sub-total |  |  |  |  | 7.2188 | m3 | 404.28 | 2918.3962
3 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Road | 1 | 5.5 | 2 | 0.15 | 1.65
| Sub-total |  |  |  |  | 1.65 | m3 | 4434.52 | 7316.958
| VAT calculation | [7 empty] | 635.675
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For wall | 1 | 5.5 | 2 | 0.075 | 0.825
| Sub-total |  |  |  |  | 0.825 | m3 | 10634.5 | 8773.4625
| VAT calculation | [7 empty] | 865.4546
5 | Providing and laying Plum concrete ( Boulder mixed concrete) including form work and 110mm dia PN6 HDPE pipe for Weep hole as per Drawing and Specifications, 60% M 15 concrete and 40% boulders/stones, using Mechanical Aids
| -For wall | 1 | 5.5 | 1.25 | 4 | 27.5
| Sub-total |  |  |  |  | 27.5 | m3 | 9623.47 | 264645.425
| VAT calculation | [7 empty] | 22553.8385
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 309587.3879
| Total Estimated | 309587.3879 |  | 100
| Budget allocated | 250000
| Municipal payment | 237500 |  | 76.715
| User Contribution | 72087.3879 |  | 23.285
| Contingencies | 7500 |  | 3
| Maintanince | 5000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 309587.3879 |  |  |  |  | Total Valuated Amount : |  | 262421.8446
Work Started : | [7 empty] | Work Finished:
#REF! | [7 empty] | F.Y:2079/80
#REF! | [7 empty] | Date:2079/06/13
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | m3 | 19.25 | 64.63 | 1244.1275 | 14.7617 | 64.63 | 954.0479 | -290.0796
| VAT calculation |  |  |  | 134.0506 |  |  | 102.7955 | -31.2551
2 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod | m3 | 7.2188 | 404.28 | 2918.3962 | 0 | 404.28 | 0 | -2918.3962
3 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | m3 | 1.65 | 4434.52 | 7316.958 | 2.5306 | 4434.52 | 11221.8854 | 3904.9274 |  | 9146.1975
| VAT calculation |  |  |  | 635.675 |  |  | 974.9233 | 339.2482
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 | m3 | 0.825 | 10634.5 | 8773.4625 | 0 | 10634.5 | 0 | -8773.4625
| VAT calculation |  |  |  | 865.4546 |  |  | 0 | -865.4546
5 | Providing and laying Plum concrete ( Boulder mixed concrete) including form work and 110mm dia PN6 HDPE pipe for Weep hole as per Drawing and Specifications, 60% M 15 concrete and 40% boulders/stones, using Mechanical Aids | m3 | 27.5 | 9623.47 | 264645.425 | 23.8106 | 9623.47 | 229140.2098 | -35505.2152
| VAT calculation |  |  |  | 22553.8385 |  |  | 19527.9827 | -3025.8558
6 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0
| Total |  |  |  | 309587.3879 |  |  | 262421.8446 | -47165.5434

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- कुर्थली च्यानेपाखा माझगाउँ जोड्ने सडक | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2082/03/02
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks | 45m
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | [9 empty] | 13m | ht=3'9"
| -For wall | 0.5 | 14.67 | 1.15 | 1.75 | 14.7617
| Sub-total |  |  |  |  | 14.7617 | m3 | 64.63 | 954.0479
| VAT calculation | [7 empty] | 102.7955
2 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod
| -Road | 0 | 2.48 | 0.8625 | 0.875 | 0
| Sub-total |  |  |  |  | 0 | m3 | 404.28 | 0
3 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Road | 1 | 2.48 | 1.15 | 0.15 | 0.4278
|  |  | 2.48 | 1.15 | 0.15 | 0.4278
|  |  | 2.42 | 1.15 | 0.15 | 0.41745
|  |  | 2.44 | 1.15 | 0.15 | 0.4209
|  |  | 2.45 | 1.15 | 0.15 | 0.42262
|  |  | 2.4 | 1.15 | 0.15 | 0.414
| Sub-total |  |  |  |  | 2.5306 | m3 | 4434.52 | 11221.8854
| VAT calculation | [7 empty] | 974.9233
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For wall | 0 | 0 | 0 | 0 | 0
| Sub-total |  |  |  |  | 0 | m3 | 10634.5 | 0
| VAT calculation | [7 empty] | 0
5 | Providing and laying Plum concrete ( Boulder mixed concrete) including form work and 110mm dia PN6 HDPE pipe for Weep hole as per Drawing and Specifications, 60% M 15 concrete and 40% boulders/stones, using Mechanical Aids
| -For wall | 1 | 2.48 | 1.095 | 1.6 | 4.345
|  |  | 2.48 | 1.1225 | 1.6 | 4.4541
|  |  | 2.42 | 1.0775 | 1.6 | 4.1721
|  |  | 2.44 | 1.0425 | 1.6 | 4.0699
|  |  | 2.45 | 1 | 1.6 | 3.92
|  |  | 2.4 | 0.9575 | 1.24 | 2.8495
| Sub-total |  |  |  |  | 23.8106 | m3 | 9623.47 | 229140.2098
| VAT calculation | [7 empty] | 19527.9827
6 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 262421.8446
| Total Valuated | 262421.8446 |  | 100
| Budget allocated | 250000
| Municipal payment | 237500 |  | 90.5031
| User Contribution | 24921.8446 |  | 9.4969
| Contingencies | 7500 |  | 3
| Maintanince | 5000 |  | 2