## Estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- कुसुमथली पहिरो संरक्षण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
|  | 1 | 24 | 0.82 | 1.6 | 31.488
| Sub-total |  |  |  |  | 31.488 | m3 | 663.31 | 20886.3053
2 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance
| -for empty bag filling | 30 | 24 | 0.38 | 64 | 1920 |  |  |  | labour cost only
| Sub-total |  |  |  |  | 1920 | sack | 92 | 176640
3 | Providing and laying Bamboo for the protection all complete
| -vertical post | 34 | 4 |  |  | 136
| -horizontal post | 10 | 24 |  |  | 240
| Sub-total |  |  |  |  | 63 | No. | 240 | 15120
| VAT calculation | [7 empty] | 1965.6
4 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 9600 | 9600
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 224711.9053
| Total Estimated | 224711.9053 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 84.5527
| User Contribution | 34711.9053 |  | 15.4473
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 224711.9053 |  |  |  |  | Total Valuated Amount : |  | 224167.888
Work Started : | [7 empty] | Work Finished:
Project:- कुसुमथली पहिरो संरक्षण | [7 empty] | F.Y:2081/2082
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2082/03/03
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | m3 | 31.488 | 663.31 | 20886.3053 | 37.8886 | 663.31 | 25131.888 | 4245.5827 |  |  | 26107.8816
2 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance | sack | 1920 | 92 | 176640 | 1921 | 92 | 176732 | 92 |  |  | 220800
3 | Providing and laying Bamboo for the protection all complete | No. | 63 | 240 | 15120 | 45 | 240 | 10800 | -4320 |  |  | 18900
| VAT calculation |  |  |  | 1965.6 |  |  | 1404 | -561.6 |  |  | 2457
4 | Provisional sum for unforseen works | PS | 1 | 9600 | 9600 | 1 | 9600 | 9600 | 0 |  |  | 12000
5 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0 |  |  | 625
| Total |  |  |  | 224711.9053 |  |  | 224167.888 | -544.0173
[10 empty] | 1070 | 70.2278 | 75143.7929

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- कुसुमथली पहिरो संरक्षण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2082/03/03
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
|  | 1 | 67.3575 | 0.45 | 1.25 | 37.8886
| Sub-total |  |  |  |  | 37.8886 | m3 | 663.31 | 25131.888
2 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance
| -for empty bag filling | 1921 |  |  |  | 1921 |  |  |  | labour cost only
| Sub-total |  |  |  |  | 1921 | sack | 92 | 176732
3 | Providing and laying Bamboo for the protection all complete
| -vertical post | 70 | 3 |  |  | 210
| -horizontal post | 1 | 1334 |  |  | 55.5833
| Sub-total |  |  |  |  | 45 | No. | 240 | 10800
| VAT calculation | [7 empty] | 1404
4 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 9600 | 9600
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 224167.888
| Total Valuated | 224167.888 |  | 100
| Budget allocated | 200000
| Municipal payment | 190000 |  | 84.7579
| User Contribution | 34167.888 |  | 15.2421
| Contingencies | 6000 |  | 3
| Maintanince | 4000 |  | 2