## Measurement
Detail Measurement Sheet
Project:- | [11 empty] | F.Y.: 2081/82
Location:- | [11 empty] | Date:
S.N. | Description of work | No. | Length | Breadth |  |  |  |  | Height |  | Quantity | Unit | Remarks
32 | New Jhingati (8-3/4"*4") laying on roof with 3" clay
| -New Roof | 2 | 4.8639 |  |  | 3.2764 |  |  |  |  | 31.8726
| Sub-total | [9 empty] | 0 | sqm
VAT calculation
33 | Dhuri Chang (horizontal and vertical)works
| -New Roof | 4 | 4.8639 | [7 empty] | 19.4557
| Sub-total | [9 empty] | 0 | rm
VAT calculation
34 | Middle class Gongacha (Corner bird) fixing works
| -Gongacha | 4 | [8 empty] | 4
| Sub-total | [9 empty] | 0 | no.
VAT calculation
1 | Plum wall |  |  | Top width |  | Base Width
Section 1
| -Chainage 0+000 |  |  | 0.55 |  | 0.7 |  |  | 0.9
| -Chainage 0+000 to 0+003 | 1 | 3 | 0.57 | 0.56 | 0.7 | 0.7 | 0.63 | 0.9 | 0.9 | 1.701
| -Chainage 0+003 to 0+006 | 1 | 3 | 0.58 | 0.575 | 0.7 | 0.7 | 0.6375 | 0.85 | 0.875 | 1.6734
Section 2
| -Chainage 0+000 |  |  | 0.5 |  | 0.7 |  |  | 0.5
| -Chainage 0+000 to 0+011 |  | 11 | 0.5 | 0.5 | 0.7 | 0.7 | 0.6 | 0.41 | 0.455 | 3.003
Section 3
| -Chainage 0+000 |  |  | 0.58 |  | 0.7 |  |  | 0.9
| -Chainage 0+000 to 0+005.78 |  | 5.78 | 0.58 | 0.58 | 0.7 | 0.7 | 0.64 | 1.25 | 1.075 | 3.9766
| -Chainage 0+005.78 to 0+011.78 |  | 6 | 0.52 | 0.55 | 0.7 | 0.7 | 0.625 | 1.15 | 1.2 | 4.5
| -Chainage 0+011.78 to 0+018.28 |  | 6.5 | 0.54 | 0.53 | 0.7 | 0.7 | 0.615 | 0.9 | 1.025 | 4.0974
Section 4
| -Chainage 0+000 |  |  | 0.5 |  | 0.8 |  |  | 1.8
| -Chainage 0+000 to 0+005 |  | 5 | 0.5 | 0.5 | 0.8 | 0.8 | 0.65 | 1.8 | 1.8 | 5.85
| -Chainage 0+005 to 0+010 |  | 5 | 0.5 | 0.5 | 0.8 | 0.8 | 0.65 | 1.45 | 1.625 | 5.2813
| -Chainage 0+010 to 0+015 |  | 5 | 0.5 | 0.5 | 0.8 | 0.8 | 0.65 | 1.25 | 1.35 | 4.3875
| -Chainage 0+015 to 0+020 |  | 5 | 0.5 | 0.5 | 0.8 | 0.8 | 0.65 | 1.4 | 1.325 | 4.3062
| -Chainage 0+020 to 0+021.9 |  | 1.9 | 0.5 | 0.5 | 0.8 | 0.8 | 0.65 | 1.25 | 1.325 | 1.6364
Section 5
| -Chainage 0+000 |  |  | 0.4 |  | 1 |  |  | 2.1
| -Chainage 0+000 to 0+012.8 |  | 12.8 | 0.4 | 0.4 | 1 | 1 | 0.7 | 2.1 | 2.1 | 18.816
Section 6
| -Chainage 0+000 |  |  | 0.4 |  | 0.8 |  |  | 1.5
| -Chainage 0+000 to 0+005 |  | 5 | 0.4 | 0.4 | 0.8 | 0.8 | 0.6 | 1.55 | 1.525 | 4.575
| -Chainage 0+005 to 0+010 |  | 5 | 0.4 | 0.4 | 0.8 | 0.8 | 0.6 | 1.4 | 1.475 | 4.425
| -Chainage 0+010 to 0+014.6 |  | 4.6 | 0.4 | 0.4 | 0.8 | 0.8 | 0.6 | 1.2 | 1.3 | 3.588
Section 7
| -Chainage 0+000 |  |  | 0.4 |  | 0.7 |  |  | 1.2
| -Chainage 0+000 to 0+013.4 |  | 13.4 | 0.4 | 0.4 | 0.7 | 0.7 | 0.55 | 1.2 | 1.2 | 8.844
Section 8
| -Chainage 0+000 |  |  | 0.4 |  | 0.7 |  |  | 1
| -Chainage 0+000 to 0+001.8 |  | 1.8 | 0.47 | 0.435 | 0.7 | 0.7 | 0.5675 | 1 | 1 | 1.0215
Section 9
| -Chainage 0+000 |  |  | 0.4 |  | 0.7 |  |  | 1.2
| -Chainage 0+000 to 0+006.4 |  | 6.4 | 0.4 | 0.4 | 0.7 | 0.7 | 0.55 | 1.2 | 1.2 | 4.224
Total

## measure quantity
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Plum wall
|  | 1 | 3 | 0.63 | 0.9 | 1.701
|  | 1 | 3 | 0.6375 | 0.875 | 1.6734
|  | 1 | 11 | 0.6 | 0.455 | 3.003
|  | 1 | 5.78 | 0.64 | 1.075 | 3.9766
|  | 1 | 6 | 0.625 | 1.2 | 4.5
|  | 1 | 6.5 | 0.615 | 1.025 | 4.0974
|  | 1 | 5 | 0.65 | 1.8 | 5.85
|  | 1 | 5 | 0.65 | 1.625 | 5.2812
|  | 1 | 5 | 0.65 | 1.35 | 4.3875
|  | 1 | 5 | 0.65 | 1.325 | 4.3062
|  | 1 | 1.9 | 0.65 | 1.325 | 1.6364
|  | 1 | 12.8 | 0.55 | 2.1 | 14.784
|  | 1 | 5 | 0.6 | 1.525 | 4.575
|  | 1 | 5 | 0.6 | 1.475 | 4.425
|  | 1 | 4.6 | 0.6 | 1.3 | 3.588
|  | 1 | 13.4 | 0.55 | 1.2 | 8.844
|  | 1 | 1.8 | 0.5675 | 1 | 1.0215
|  | 1 | 6.4 | 0.55 | 1.2 | 4.224
| Grand Total | [7 empty] | 0

## measure quantity (2) (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Plum wall
|  | 1 | 3 | 1.5 | 0.75 | 3.375
|  | 1 | 3 | 1.5 | 1.5 | 6.75
|  | 1 | 11 | 5.5 | 2.75 | 166.375
|  | 1 | 5.78 | 2.89 | 1.445 | 24.1376
|  | 1 | 6 | 3 | 2.945 | 53.01
|  | 1 | 6.5 | 3.25 | 3.125 | 66.0156
|  | 1 | 5 | 2.5 | 1.25 | 15.625
|  | 1 | 5 | 2.5 | 2.5 | 31.25
|  | 1 | 5 | 2.5 | 2.5 | 31.25
|  | 1 | 5 | 2.5 | 2.5 | 31.25
|  | 1 | 1.9 | 0.95 | 1.725 | 3.1136
|  | 1 | 12.8 | 6.4 | 3.2 | 262.144
|  | 1 | 5 | 2.5 | 1.25 | 15.625
|  | 1 | 5 | 2.5 | 2.5 | 31.25
|  | 1 | 4.6 | 2.3 | 2.4 | 25.392
|  | 1 | 13.4 | 6.7 | 3.35 | 300.763
|  | 1 | 1.8 | 0.9 | 0.45 | 0.729
|  | 1 | 6.4 | 3.2 | 1.6 | 32.768
| Grand Total | [7 empty] | 0

## final
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Plum wall
|  | 1 | 3 | 0.63 | 0.9 | 1.701
|  | 1 | 3 | 0.6375 | 0.875 | 1.6734
|  | 1 | 11 | 0.6 | 0.455 | 3.003
|  | 1 | 5.78 | 0.64 | 1.075 | 3.9766
|  | 1 | 6 | 0.625 | 1.2 | 4.5
|  | 1 | 6.5 | 0.615 | 1.025 | 4.0974
|  | 1 | 5 | 0.65 | 1.8 | 5.85
|  | 1 | 5 | 0.65 | 1.625 | 5.2812
|  | 1 | 5 | 0.65 | 1.35 | 4.3875
|  | 1 | 5 | 0.65 | 1.325 | 4.3062
|  | 1 | 1.9 | 0.65 | 1.325 | 1.6364
|  | 1 | 12.8 | 0.7 | 2.1 | 18.816
|  | 1 | 5 | 0.6 | 1.525 | 4.575
|  | 1 | 5 | 0.6 | 1.475 | 4.425
|  | 1 | 4.6 | 0.6 | 1.3 | 3.588
|  | 1 | 13.4 | 0.55 | 1.2 | 8.844
|  | 1 | 1.8 | 0.5675 | 1 | 1.0215
|  | 1 | 6.4 | 0.55 | 1.2 | 4.224
| Grand Total |  |  |  |  | 85.9064 | m3