## Estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- पासीखेलमा भएको पाटी संरक्षण | [6 empty] | F.Y.: 2081/2082 |  |  |  |  | subservience
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/16
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks | 45m
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य) | [9 empty] | 13m | ht=3'9"
| -For wall | 0.5 | 13.6 | 1.7 | 3.4 | 39.304
| -for hume pipe | 4 | 2.5 | 0.6 | 0.9 | 5.4
| -for proposed road | 0 | 24.97 | 2.9 | 0.15 | 0
| -for steps | 0 | 11.8897 | 1.3 | 0.15 | 0
| Sub-total |  |  |  |  | 44.704 | m3 | 64.63 | 2889.2195
| VAT calculation | [7 empty] | 311.3038
2 | Providing suitable material and Back filling behind abutment, wing wall and return wall complete as per Drawing and Technical Specifications., locally available material including compaction by tamping rod
| -Road | 0.5 | 13.6 | 0.6 | 1 | 0
| Sub-total |  |  |  |  | 0 | m3 | 404.28 | 0
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Road | 1 | 13.6 | 1.7 | 0.15 | 3.468
| -For hume pipe base & road dhalaan | 1 | 10 | 0.45 | 0.15 | 0.675
|  | 1 | 10 | 0.6 | 0.15 | 0.9
| -for steps | 0 | 11.8897 | 1.3 | 0.15 | 0
| Sub-total |  |  |  |  | 5.043 | m3 | 4561.53 | 23003.7958
| VAT calculation | [7 empty] | 2026.114
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For wall | 1 | 13.6 | 1.7 | 0.075 | 1.734
|  | 1 | 13.6 | 0.5 | 0.05 | 0.34
| -for steps | 0 | 11.8897 | 1.3 | 0.05 | 0
| -for brick wall as a retaining structure | 1 | 3.886 | 0.23 | 0.05 | 0
| Sub-total |  |  |  |  | 2.074 | m3 | 10634.5 | 22055.953
| VAT calculation | [7 empty] | 2175.7004
4 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -For wall | 1 | 13.6 | 1.1 | 3.4 | 50.864
| Sub-total |  |  |  |  | 50.864 | m3 | 9709.43 | 493860.4475
| VAT calculation | [7 empty] | 35828.3269
5 | Providing and laying , fitting and placing HYSD bar reinforcement in sub-structure complete as per Drawing and Technical Specifications | No. | Length (m) | Unit Weight (kg/m) | Total Weight (Kg)
| Sub-total | 62 | 0.6 | 0.61728 | 22.963 | 0.022963
|  | 5 | 9.4 | 0.61728 | 29.0123 | 0.029012
| Sub-total |  |  |  |  | 0.051975 | MT | 124140 | 6452.2148
| VAT calculation | [7 empty] | 749.7334
6 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 20
| Sub-total | 1 | 10 | 0.6 | 0.15 | 0.9
| Sub-total |  |  |  |  | 0.9 | m3 | 11588.17 | 10429.353
| VAT calculation | [7 empty] | 1055.7121
7 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 300 mm internal dia. | 5 | 2.5 |  |  | 12.5
| Sub-total |  |  |  |  | 12.5 | rm | 3697.12 | 46214
| VAT calculation | [7 empty] | 7457.398
6 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -For wall | 1 | 11.915 | 0.23 | 0.45 | 1.2332
| -for steps | 31 | 1.07 | 0.15 | 0.15 | 0.74633
| -As a retaining wall | 1 | 3.886 | 0.23 | 0.6 | 0.53627
| Sub-total |  |  |  |  | 0 | m3 | 14362.76 | 0
| VAT calculation | [7 empty] | 0
7 | sfk]{6 b'jf]
| -for open spaces | 1 | 24.94 | 0.3 |  | 7.482
|  | 1 | 4.2417 | 15.5693 |  | 66.0404
|  | 1 | 6.7571 | 3.8098 |  | 25.7432
| Sub-total |  |  |  |  | 0 | m2 | 376.7365 | 0
| VAT calculation | [7 empty] | 0
8 | sfk]{6 b'jf]sf] nflu 6fKg] sfo{} Hofnf
| -for open spaces | 1 | 24.94 | 0.3 |  | 7.482
|  | 1 | 4.2417 | 15.5693 |  | 66.0404
|  | 1 | 6.7571 | 3.8098 |  | 25.7432
| Sub-total |  |  |  |  | 0 | m2 | 247.5697 | 0
9 | Provisional sum for small plants and other unforseen works | 1 |  |  |  | 0 | PS | 20000 | 0
8 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
7.8744
| Grand Total | [7 empty] | 655009.2722
| Total Estimated | 655009.2722 |  | 100
| Budget allocated | 586000
| Municipal payment | 556700 |  | 84.9912
| User Contribution | 98309.2722 |  | 15.0088
| Contingencies | 17580 |  | 3
| Maintanince | 11720 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 655009.2722 |  |  |  |  | Total Valuated Amount : |  | 608949.8577
Work Started : | [7 empty] | Work Finished:
Project:- पासीखेलमा भएको पाटी संरक्षण | [7 empty] | F.Y:2081/82
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2082/03/01
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य) | m3 | 44.704 | 64.63 | 2889.2195 | 9.3142 | 64.63 | 601.98 | -2287.2395
| VAT calculation |  |  |  | 311.3038 |  |  | 64.8613 | -246.4424
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | m3 | 5.043 | 4561.53 | 23003.7958 | 3.729 | 4434.52 | 16536.3251 | -6467.4707
| VAT calculation |  |  |  | 2026.114 |  |  | 1436.6256 | -589.4884
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 | m3 | 2.074 | 10634.5 | 22055.953 | 2.0282 | 10634.5 | 21569.4246 | -486.5284
| VAT calculation |  |  |  | 2175.7004 |  |  | 2127.707 | -47.9934
4 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications. | m3 | 50.864 | 9709.43 | 493860.4475 | 47.1818 | 9709.43 | 458107.8989 | -35752.5486
| VAT calculation |  |  |  | 35828.3269 |  |  | 33234.5699 | -2593.757
5 | Providing and laying , fitting and placing HYSD bar reinforcement in sub-structure complete as per Drawing and Technical Specifications | MT | 0.051975 | 124140 | 6452.2148 | 0.069383 | 124140 | 8613.1704 | 2160.9556
| VAT calculation |  |  |  | 749.7334 |  |  | 1000.8318 | 251.0984
6 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 20 | m3 | 0.9 | 11588.17 | 10429.353 | 0.9 | 11588.17 | 10429.353 | 0
| VAT calculation |  |  |  | 1055.7121 |  |  | 1055.7121 | 0
7 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 300 mm internal dia. | rm | 12.5 | 3697.12 | 46214 | 12.5 | 3697.12 | 46214 | 0
| VAT calculation |  |  |  | 7457.398 |  |  | 7457.398 | 0
8 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0
| Total |  |  |  | 655009.2722 |  |  | 608949.8577 | -46059.4146

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- पासीखेलमा भएको पाटी संरक्षण | [6 empty] | F.Y.: 2081/2082 |  |  |  |  | subservience
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/16
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks | 45m
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य) | [9 empty] | 13m | ht=3'9"
| -For wall | 0.5 | 13.3 | 1.7 | 0.6 | 6.783
| -for hume pipe | 5 | 2.5 | 0.45 | 0.45 | 2.5312
| Sub-total |  |  |  |  | 9.3142 | m3 | 64.63 | 601.98
| VAT calculation | [7 empty] | 64.8613
2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Road | 1 | 13.3 | 1.7 | 0.15 | 3.3915
| -For hume pipe base & road dhalaan | 1 | 10 | 0.45 | 0.075 | 0.3375
| Sub-total |  |  |  |  | 3.729 | m3 | 4434.52 | 16536.3251
| VAT calculation | [7 empty] | 1436.6256
3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For wall | 1 | 13.3 | 1.7 | 0.075 | 1.6957
|  | 1 | 13.3 | 0.5 | 0.05 | 0.3325
| Sub-total |  |  |  |  | 2.0282 | m3 | 10634.5 | 21569.4246
| VAT calculation | [7 empty] | 2127.707
4 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -For wall | 1 | 13.3 | 1.1 | 3.225 | 47.1818
| Sub-total |  |  |  |  | 47.1818 | m3 | 9709.43 | 458107.8989
| VAT calculation | [7 empty] | 33234.5699
5 | Providing and laying , fitting and placing HYSD bar reinforcement in sub-structure complete as per Drawing and Technical Specifications | No. | Length (m) | Unit Weight (kg/m) | Total Weight (Kg)
| Sub-total | 62 | 0.6 | 0.61728 | 22.963 | 0.022963
|  | 8 | 9.4 | 0.61728 | 46.4198 | 0.04642
| Sub-total |  |  |  |  | 0.069383 | MT | 124140 | 8613.1704
| VAT calculation | [7 empty] | 1000.8318
6 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 20
| Sub-total | 1 | 10 | 0.6 | 0.15 | 0.9
| Sub-total |  |  |  |  | 0.9 | m3 | 11588.17 | 10429.353
| VAT calculation | [7 empty] | 1055.7121
7 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 300 mm internal dia. | 5 | 2.5 |  |  | 12.5
| Sub-total |  |  |  |  | 12.5 | rm | 3697.12 | 46214
| VAT calculation | [7 empty] | 7457.398
8 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
7.8744
| Grand Total | [7 empty] | 608949.8577
| Total Valuated | 608949.8577 |  | 100
| Budget allocated | 586000
| Municipal payment | 556700 |  | 91.4197
| User Contribution | 52249.8577 |  | 8.5803
| Contingencies | 17580 |  | 3
| Maintanince | 11720 |  | 2