## backyard
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- परोपकार भवन मर्मत | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/28
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | df6f]df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdu¦L !) dL=;Dd
| -existing wall | 1 | 18 | 0.1 | 0.71106 | 1.2799 |  |  |  |  | 7.6
| Sub-total |  |  |  |  | 1.2799 | cum | 975.2 | 1248.1728
2 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -at roof | 1 | 18 | 0.23 | 0.71106 | 2.9438 |  |  |  |  | 7.6
| -at drain | 1 | 6.55 | 0.23 | 0.3 | 0.45195
| Sub-total |  |  |  |  | 3.3958 | cum | 14362.76 | 48772.3957
| VAT calculation | [7 empty] | 4552.0968
3 | dfn;fdfg pknAw u/L lh=cfO{=k¦m]ddf ;fwf/0f d]6fnfOH8 kf]lnP6/ nfldg]6]8 jf]8{sf] l;lnË nufpg] sfd -ss{t kftfsf] 5fgfd'lg_
| -false ceiling | 1 | 7.615 | 3.49 |  | 26.5764 |  |  |  |  | 7.6
|  | 1 | 5.74 | 2.33 |  | 13.3742 |  |  |  |  | 5.73
|  | 1 | 5.7 | 2.3 |  | 13.11
| Sub-total |  |  |  |  | 53.0605 | sqm | 817.76 | 43390.7954
| VAT calculation | [7 empty] | 5640.8034
4 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -at roof | 3 | 3.6574 | 1.0667 |  | 11.7046 |  |  |  |  | 7.6
| Sub-total |  |  |  |  | 11.7046 | sqm | 1070.9 | 12534.4997
| VAT calculation | [7 empty] | 1306.6966
5 | )=%) dL=dL= Kn]g zL6sf] !%) ld=ld= rf}8fO{, u6/ agfO{ jf;/
| -at roof | 1 | 13.4 |  |  | 13.4 |  |  |  |  | 7.6
| Sub-total |  |  |  |  | 13.4 | rm | 1108.01 | 14847.334
| VAT calculation | [7 empty] | 1232.7106
6 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -at drain wall | 2 | 9.7531 | 0.15 | 0.6 | 1.7556 |  |  |  |  | 7.6
| Sub-total |  |  |  |  | 1.7556 | cum | 1950.4 | 3424.0488
| VAT calculation | [7 empty] | 445.1263
7 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at drain wall base | 1 | 9.7531 | 0.4 | 0.125 | 0.48766
| Sub-total |  |  |  |  | 0.48766 | cum | 663.31 | 323.4672
8 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -at drain wall base | 1 | 9.7531 | 0.7 |  | 6.8272
| -at one side drain | 1 | 6.55 | 0.23 |  | 1.5065
| -at entrance | 1 | 1.95 | 1 |  | 1.95
| Sub-total |  |  |  |  | 10.2837 | sqm | 1014.97 | 10437.6336
| VAT calculation | [7 empty] | 1152.0156
9 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -at drain wall base | 1 | 9.7531 | 0.7 | 0.1 | 0.68272
| -at one side drain | 1 | 6.55 | 0.53 | 0.075 | 0.26036
| -at roof | 1 | 18 | 0.23 | 0.05 | 0.207
| Sub-total |  |  |  |  | 1.1501 | cum | 12983.1 | 14931.619
| VAT calculation | [7 empty] | 1207.7627
10 | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4) #) dL= ;Dd 9'jfgL ;d]t | [9 empty] | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4)
| -at drain wall | 2 | 9.7531 | 0.15 | 0.6 | 1.7556 |  |  |  |  | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| Sub-total |  |  |  |  | 1.7556 | cum | 8569.3 | 15043.9403
| VAT calculation | [7 empty] | 139.5787
13
11 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For slab cover | 5 | 0.75 | 0.39506 | 1.4815 | 0.0014815
|  | 65 | 0.7 | 0.39506 | 17.9753 | 0.017975
|  | 5 | 0.9 | 0.39506 | 1.7778 | 0.0017778
|  | 6 | 0.83816 | 0.39506 | 1.9867 | 0.0019867
| Sub-total |  |  |  |  | 0.023221 | MT | 131940 | 3063.8204
| VAT calculation | [7 empty] | 320.5935
12 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -at slab cover | 26 | 0.75 |  | 0.1 | 1.95 |  |  |  |  | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
|  | 26 | 0.7 |  | 0.1 | 1.82
|  | 2 | 0.9 |  | 0.1 | 0.18
|  | 2 | 0.83816 |  | 0.1 | 0.16763
| Sub-total |  |  |  |  | 4.1176 | sqm | 814.0427 | 3351.9281
| VAT calculation | [7 empty] | 196.4001
13 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_ | [9 empty] | 13
| -slab cover | 1 | 9.7531 | 0.7 | 0.1 | 0.68272 |  |  |  |  | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
|  | 1 | 0.9 | 0.83816 | 0.1 | 0.075434
| -at entrance | 1 | 1.95 | 1 | 0.1 | 0.195
| Sub-total |  |  |  |  | 0.95315 | cum | 13568.9 | 12933.2378
| VAT calculation | [7 empty] | 1180.1426
14 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (Kg)
| -MS Flats 20mm*5mm | 6 | 0.17779 | 0.8 | 0.8534 | 0.8534
|  | 2 | 7.2 | 0.8 | 11.52 | 11.52
| -MS flats for fencing | 482 | 0.15 | 0.8 | 57.84 | 57.84
| -MS square pipe of 2"*2" of 1.8mm thickness for vertical post | 4 | 2.2859 | 2.72 | 24.8705 | 24.8705
| -at compound | 5 | 2.1335 | 2.72 | 29.0155 | 29.0155
| -MS square pipe 1.5"*1.5" of 1.6mm thickness for horizontal member | 1 | 7.2 | 3.87 | 27.864 | 27.864
|  | 4 | 2.5398 | 3.87 | 39.3157 | 39.3157
| -at compound | 2 | 13.2 | 3.87 | 102.168 | 102.168
|  | 5 | 1.5 | 3.87 | 29.025 | 29.025
| -35*35*3mm Equal angles at windows | 1 | 7.2 | 1.52 | 10.944 | 10.944
| -equal angles for fencing | 2 | 48.2 | 1.52 | 146.528 | 146.528
| -MS square rod12mm *12mm size | 482 | 0.76196 | 1.13 | 415.0107 | 415.0107
| Sub-total |  |  |  |  | 894.9548 | Kg | 181.17 | 162138.9584
| VAT calculation | [7 empty] | 11495.7084
15 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 2 | 2.0691 |  | 1.6 | 6.6212
|  | 1 | 12.1 |  | 1.5167 | 18.3517
|  | 1 | 12.1 |  | 1.3 | 15.73
|  | 1 | 5.8 |  | 1.4 | 8.12
|  | 1 | 5.8 |  | 1.0972 | 6.3639
|  | 1 | 10.6 |  | 1.27 | 13.462
|  | 1 | 1.8287 |  | 0.91436 | 1.6721
|  | 1 | 1.5239 |  | 0.60957 | 0.92894
|  | 1 | 12.97 |  | 0.3 | 3.891
| -at one side drain | 1 | 6.55 |  | 0.23 | 1.5065
| -at roof | 1 | 18 |  | 0.71106 | 12.7991
| sub-total |  |  |  |  | 89.4465 | sqm | 405.86 | 36302.7596
| -VAT 13% for materials | [7 empty] | 1298.4109
16 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -as of plaster excluding drain | 1 |  |  |  | 87.94
| Sub-total |  |  |  |  | 87.94 | sqm | 251.77 | 22140.6557
| VAT calculation | [7 empty] | 1456.0051
17 | dfn;fdfg pknAw u/L UPVC sheet with PMMA Coating and mesh (Regular)5fgf 5fpg] sfd .
| -roof | 1 | 7.2 | 2.6922 |  | 19.3836
| -at compound | 1 | 13.2 | 1.5 |  | 19.8
| Sub-total |  |  |  |  | 39.1836 | sqm | 2271.55 | 89007.5124
| VAT calculation | [7 empty] | 10298.783
18 | sfk]{6 b'jf] |  |  |  | Area (m2)
| -for open spaces | 1 |  |  | 4.494 | 4.494
|  | 1 |  |  | 20.8359 | 20.8359
|  | 1 | 4.25 | 2.6 |  | 11.05
|  | 1 | 7 | 1.1048 |  | 7.7339 |  |  |  |  | ;km]{;nfO{ 8«]l;Ë ug]{ sfo{ vfN6f] k'g]{, p7]sf] df6f] sf6\g], ;tx ldnfpg]
|  | 1 | 6.55 | 2.6166 |  | 17.1386 |  |  |  |  | cflb sfo{ ;d]t -;le{;/f]8 cflb_
| Sub-total |  |  |  |  | 61.2525 | m2 | 376.7365 | 23076.0561
| VAT calculation | [7 empty] | 2999.8873
19 | ;km]{;nfO{ 8«]l;Ë ug]{ sfo{ vfN6f] k'g]{, p7]sf] df6f] sf6\g], ;tx ldnfpg] cflb sfo{ ;d]t -;le{;/f]8 cflb_
| -as of item no. 15 |  |  |  |  | 61.2525
| -at entrance | 1 | 1.95 | 1 |  | 1.95
| Sub-total |  |  |  |  | 63.2025 | m2 | 9.2 | 581.4631
20 | Provisional sum for unforeseen works | 1 |  |  |  | 1 | PS | 2000 | 2000
21 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 564973.0195
| Total Estimated | 564973.0195 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 84.0748
| User Contribution | 89973.0195 |  | 15.9252
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 564973.0195 |  |  |  |  | Total Valuated Amount : |  | 450558.5023
Work Started : | [7 empty] | Work Finished:
#REF! | [7 empty] | F.Y:2079/80
#REF! | [7 empty] | Date:2079/06/13
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | df6f]df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdu¦L !) dL=;Dd | cum | 1.2799 | 975.2 | 1248.1728 | 2.9002 | 975.2 | 2828.3044 | 1580.1316
2 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | cum | 3.3958 | 14362.76 | 48772.3957 | 4.3859 | 14362.76 | 62993.661 | 14221.2653
| VAT calculation |  |  |  | 4552.0968 |  |  | 5879.4168 | 1327.32
3 | dfn;fdfg pknAw u/L lh=cfO{=k¦m]ddf ;fwf/0f d]6fnfOH8 kf]lnP6/ nfldg]6]8 jf]8{sf] l;lnË nufpg] sfd -ss{t kftfsf] 5fgfd'lg_ | sqm | 53.0605 | 817.76 | 43390.7954 | 53.0605 | 817.76 | 43390.7954 | 0
| VAT calculation |  |  |  | 5640.8034 |  |  | 5640.8034 | 0
4 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd | sqm | 11.7046 | 1070.9 | 12534.4997 | 7.8031 | 1070.9 | 8356.3331 | -4178.1666
| VAT calculation |  |  |  | 1306.6966 |  |  | 871.1311 | -435.5655
5 | )=%) dL=dL= Kn]g zL6sf] !%) ld=ld= rf}8fO{, u6/ agfO{ jf;/ | rm | 13.4 | 1108.01 | 14847.334 | 0 | 1108.01 | 0 | -14847.334
| VAT calculation |  |  |  | 1232.7106 |  |  | 0 | -1232.7106
6 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd . | cum | 1.7556 | 1950.4 | 3424.0488 | 1.8927 | 1950.4 | 3691.5526 | 267.5038
| VAT calculation |  |  |  | 445.1263 |  |  | 479.9018 | 34.7755
7 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | cum | 0.48766 | 663.31 | 323.4672 | 0.78863 | 663.31 | 523.1072 | 199.6399
8 | ;'Vvf O{6f RofK6f] 5fKg] sfd | sqm | 10.2837 | 1014.97 | 10437.6336 | 12.7404 | 1014.97 | 12931.1633 | 2493.5296
| VAT calculation |  |  |  | 1152.0156 |  |  | 1427.2298 | 275.2142
9 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_ | cum | 1.1501 | 12983.1 | 14931.619 | 1.283 | 12983.1 | 16657.8893 | 1726.2703
| VAT calculation |  |  |  | 1207.7627 |  |  | 1347.3942 | 139.6315
10 | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4) #) dL= ;Dd 9'jfgL ;d]t | cum | 1.7556 | 8569.3 | 15043.9403 | 1.6808 | 8569.3 | 14402.9626 | -640.9776
| VAT calculation |  |  |  | 139.5787 |  |  | 133.6317 | -5.947
11 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | MT | 0.023221 | 131940 | 3063.8204 | 0.02961 | 131940 | 3906.7271 | 842.9068
| VAT calculation |  |  |  | 320.5935 |  |  | 408.794 | 88.2005
12 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd | sqm | 4.1176 | 814.0427 | 3351.9281 | 3.616 | 814.0427 | 2943.5784 | -408.3497
| VAT calculation |  |  |  | 196.4001 |  |  | 172.4736 | -23.9265
13 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_ | cum | 0.95315 | 13568.9 | 12933.2378 | 0.93358 | 13568.9 | 12667.6537 | -265.5841
| VAT calculation |  |  |  | 1180.1426 |  |  | 1155.9083 | -24.2342
14 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | Kg | 894.9548 | 181.17 | 162138.9584 | 345.1231 | 181.17 | 62525.9541 | -99613.0042
| VAT calculation |  |  |  | 11495.7084 |  |  | 4433.1118 | -7062.5966
15 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/ | sqm | 89.4465 | 405.86 | 36302.7596 | 187.8859 | 405.86 | 76255.3663 | 39952.6067
| -VAT 13% for materials |  |  |  | 1298.4109 |  |  | 2727.3628 | 1428.9519
16 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd | sqm | 87.94 | 251.77 | 22140.6557 | 0 | 251.77 | 0 | -22140.6557
| VAT calculation |  |  |  | 1456.0051 |  |  | 0 | -1456.0051
17 | dfn;fdfg pknAw u/L UPVC sheet with PMMA Coating and mesh (Regular)5fgf 5fpg] sfd . | sqm | 39.1836 | 2271.55 | 89007.5124 | 39.1836 | 2271.55 | 89007.5115 | -0.00090959
[5 empty] | 10298.783 |  |  | 10298.7829 | -0.00010525
18 | sfk]{6 b'jf] | m2 | 61.2525 | 376.7365 | 23076.0561 | 0 | 376.7365 | 0 | -23076.0561
| VAT calculation |  |  |  | 2999.8873 |  |  | 0 | -2999.8873
19 | ;km]{;nfO{ 8«]l;Ë ug]{ sfo{ vfN6f] k'g]{, p7]sf] df6f] sf6\g], ;tx ldnfpg] cflb sfo{ ;d]t -;le{;/f]8 cflb_ | m2 | 63.2025 | 9.2 | 581.4631 | 0 | 9.2 | 0 | -581.4631
20 | Provisional sum for unforeseen works | PS | 1 | 2000 | 2000 | 1 | 2000 | 2000 | 0
21 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0
| Total |  |  |  | 564973.0195 |  |  | 450558.5023 | -114414.5172

## rate analysis (hidden)
#REF!
हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4)
C13 | #) dL= ;Dd 9'jfgL ;d]t
b/ ljZn]if0fsf] nflu ९ j=ld= lnOPsf]
| ;¦f]t ;fwg | tx÷lsl;d | kl/df0f | PsfO{ | b/ k¦lt PsfO{ | /sd | k¦To]s ;¦f]t ;fwgsf] hDdf
| >lds | s_ l;kfn' | 1 | hjfg | 1225 | 1225
|  | v_ HofdL | 2 | hjfg | 920 | 1840 | 3065
| lgdf{0f ;fdu¦L | 300X150X100 Pd=Pd=sf] हयाबिटेक ब्रिक | 0 | j6f | 58 | 0
|  | l;d]G6 | 0.1028 | d]=6= | 12131 | 1247.06
|  | afn'jf | 0.1715 | 3=dL= | 3177 | 544.85 |  | 99000
|  | :6f]g 8:6 | 0.1516 | 3=dL= | 1234.8 | 187.19
|  | !) ld ld 8l08 | 35 | s].lh | 100 | 3500 |  | 21.7
|  | kfgL | 90 | nL6/ | 0.28 | 25.2 | 5504.3
[5 empty] | jf:tljs b//]6 |  | 8569.3
| b/ k¦lt 3=dL=sf] |  |  |  | !%Ü 7]s]bf/ cf]e/x]8 |  | 1285.39
?= | 9854.69 | k}= |  |  | hDdf b/ /]6 |  | 9854.69
[5 empty] | b/ /]6 k¦lt ju{ ld |  | 1094.9656
[5 empty] | cf]e/x]8 afx]s |  | 952.144
Block Size
1
E2 | kmnfdsf] kfOk (Prop), KnfOjf]8{ k¦of]u u/L km;{ / :nfjsf] nflu kmdf{ agfpg] sfd .
b/ ljZn]if0fsf] nflu !)) j=ld= lnOPsf]
| ;¦f]t ;fwg | tx÷lsl;d | kl/df0f | PsfO{ | b/ k¦lt PsfO{ | /sd | k¦To]s ;¦f]t ;fwgsf] hDdf
| >lds | s_ l;kfn' | 17.2 | hjfg | 1225 | 21070
|  | v_ HofdL | 25.7 | hjfg | 920 | 23644 | 44714
| lgdf{0f ;fdu¦L | !% dL=dL= jf]8{ | 16.5 | j=dL= | 1215.88 | 20062.02
|  | :yfgLo s'–sf7 | 0.232 | 3=dL= | 57449.37 | 13328.25
|  | kmnfd] kfO{k (NMB 50-M) | 0 | ;+Vof | 2304 | 0
|  | lsnf sfF6L | 25 | s]=hL= | 132 | 3300 | 36690.27
[5 empty] | jf:tljs b//]6 |  | 81404.27
| b/ k¦lt j=dL=sf] |  |  |  | !%Ü 7]s]bf/ cf]e/x]8 |  | 12210.64
| 93614.91 | ?= | 936.14 | k}= | hDdf b/ /]6 |  | 93614.91
100
gf]6 M sf7 M ^ k6s;dd k¦of]u ug{ ;lsg] To;kl5 @%Ü d"No afFsL /xg] lx;fan] ul/Psf]
1.6875x1.1x0.7516= 0.232
M KNffO{ M ^ k6s;dd k¦of]u ug{ ;lsg] To;kl5 !)Ü d"No afFsL /xg] lx;fan] ul/Psf]
100x1.1x0.9/6=16.5
M kfO{k M !% k6s;Dd k¦of]u ug{ ;lsg] To;kl5 @%Ü d"No afFsL /xg] lx;fan] ul/Psf]
88/15x0.75 =4.4
=

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- परोपकार भवन मर्मत | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/28
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | df6f]df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdu¦L !) dL=;Dd
| -existing wall | 1 | 18 | 0.1 | 0.71106 | 1.2799 | [5 empty] | 7.6
| -left | 1 | 2.8 | 0.35 | 0.40689 | 0.39875
| -right | 1 | 2.8 | 0.35 | 0.47044 | 0.46103
| Wing part 1 upto mid length | 2 | 1.5 | 0.35 | 0.31743 | 0.33331
| Wing part 1 upto end length from mid | 2 | 1.5 | 0.35 | 0.40689 | 0.42723
| Sub-total |  |  |  |  | 2.9002 | cum | 975.2 | 2828.3044
2 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -at roof | 1 | 2.3368 | 0.23 | 0.99 | 0.53209 | [5 empty] | 7.6
|  | 1 | 2.9717 | 0.23 | 0.67 | 0.45793
|  | 1 | 0.87 | 0.23 | 0.13 | 0.026013
|  | 1 | 4.2161 | 0.23 | 0.625 | 0.60606
|  | 1 | 2.8711 | 0.23 | 0.355 | 0.23442
|  | 1 | 1.04 | 0.23 | 0.04 | 0.009568
|  | 1 | 2.8711 | 0.23 | 0.345 | 0.22782
|  | 1 | 1.09 | 0.23 | 0.06 | 0.015042
|  | 1 | 2.235 | 0.23 | 1 | 0.51405
|  | 1 | 3.97 | 0.23 | 0.625 | 0.57069
|  | 1 | 2.8955 | 0.23 | 0.3 | 0.19979
|  | 1 | 1.6254 | 0.23 | 0.06 | 0.022431
|  | 1 | 7.6714 | 0.23 | 0.23 | 0.40582
|  | 1 | 7.6714 | 0.1 | 0.22 | 0.16877
| -at drain | 1 | 7.1116 | 0.23 | 0.15 | 0.24535
|  | 1 | 1.25 | 0.23 | 0.25 | 0.071875
|  | 1 | 0.10149 | 0.23 | 0.55 | 0.012839
|  | 1 | 0.10149 | 0.23 | 0.35 | 0.0081702
|  | 1 | 0.32 | 0.23 | 0.23 | 0.016928
|  | 1 | 0.5 | 0.23 | 0.35 | 0.04025
| Sub-total |  |  |  |  | 4.3859 | cum | 14362.76 | 62993.661
| VAT calculation | [7 empty] | 5879.4168
3 | dfn;fdfg pknAw u/L lh=cfO{=k¦m]ddf ;fwf/0f d]6fnfOH8 kf]lnP6/ nfldg]6]8 jf]8{sf] l;lnË nufpg] sfd -ss{t kftfsf] 5fgfd'lg_
| -false ceiling | 1 | 7.615 | 3.49 |  | 26.5764 | [5 empty] | 7.6
|  | 1 | 5.74 | 2.33 |  | 13.3742 | [5 empty] | 5.73
|  | 1 | 5.7 | 2.3 |  | 13.11
| Sub-total |  |  |  |  | 53.0605 | sqm | 817.76 | 43390.7954
| VAT calculation | [7 empty] | 5640.8034
4 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -at roof | 2 | 3.6574 | 1.0667 |  | 7.8031 | [5 empty] | 7.6
| Sub-total |  |  |  |  | 7.8031 | sqm | 1070.9 | 8356.3331
| VAT calculation | [7 empty] | 871.1311
5 | )=%) dL=dL= Kn]g zL6sf] !%) ld=ld= rf}8fO{, u6/ agfO{ jf;/
| -at roof | 1 | 13.4 |  |  | 13.4 | [5 empty] | 7.6
| Sub-total |  |  |  |  | 0 | rm | 1108.01 | 0
| VAT calculation | [7 empty] | 0
6 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -at drain wall | 2 | 10.5151 | 0.15 | 0.6 | 1.8927 | [5 empty] | 7.6
| Sub-total |  |  |  |  | 1.8927 | cum | 1950.4 | 3691.5526
| VAT calculation | [7 empty] | 479.9018
7 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at drain wall base | 1 | 10.5151 | 0.6 | 0.125 | 0.78863
| Sub-total |  |  |  |  | 0.78863 | cum | 663.31 | 523.1072
8 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -at drain wall base | 1 | 10.5151 | 0.67 |  | 7.0451
| -at one side drain | 1 | 7.0101 | 0.53 |  | 3.7153
| -at entrance | 1 | 2.2 | 0.9 |  | 1.98
| Sub-total |  |  |  |  | 12.7404 | sqm | 1014.97 | 12931.1633
| VAT calculation | [7 empty] | 1427.2298
9 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -at drain wall base | 1 | 10.5151 | 0.67 | 0.075 | 0.52838
| -at one side drain | 1 | 7.0101 | 0.83 | 0.075 | 0.43638
| -at roof | 1 | 24.3415 | 0.23 | 0.05 | 0.27993
|  | 1 | 7.6714 | 0.1 | 0.05 | 0.038357
| Sub-total |  |  |  |  | 1.283 | cum | 12983.1 | 16657.8893
| VAT calculation | [7 empty] | 1347.3942
10 | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4) #) dL= ;Dd 9'jfgL ;d]t | [10 empty] | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4)
| -at drain wall | 2 | 10.5151 | 0.15 | 0.5 | 1.5773 | [5 empty] | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
|  | 2 | 1.15 | 0.15 | 0.3 | 0.1035
| Sub-total |  |  |  |  | 1.6808 | cum | 8569.3 | 14402.9626
| VAT calculation | [7 empty] | 133.6317
13
11 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For slab cover | 40 | 0.56 | 0.39506 | 8.8494 | 0.0088494
|  | 32 | 0.82 | 0.39506 | 10.3664 | 0.010366
|  | 3 | 0.56 | 0.39506 | 0.6637 | 0.0006637
|  | 4 | 0.47 | 0.39506 | 0.74272 | 0.00074272
|  | 5 | 1.55 | 0.39506 | 3.0617 | 0.0030617
|  | 10 | 0.74 | 0.39506 | 2.9235 | 0.0029235
|  | 5 | 0.82 | 0.39506 | 1.6198 | 0.0016198
|  | 5 | 0.7 | 0.39506 | 1.3827 | 0.0013827
| Sub-total |  |  |  |  | 0.02961 | MT | 131940 | 3906.7271
| VAT calculation | [7 empty] | 408.794
12 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -at slab cover | 16 | 0.66 |  | 0.1 | 1.056
|  | 16 | 0.92 |  | 0.1 | 1.472
|  | 2 | 0.66 |  | 0.1 | 0.132
|  | 2 | 0.57 |  | 0.1 | 0.114
|  | 2 | 1.65 |  | 0.1 | 0.33
|  | 2 | 0.84 |  | 0.1 | 0.168
|  | 2 | 0.92 |  | 0.1 | 0.184
|  | 2 | 0.8 |  | 0.1 | 0.16
| Sub-total |  |  |  |  | 3.616 | sqm | 814.0427 | 2943.5784
| VAT calculation | [7 empty] | 172.4736
13 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -slab cover | 8 | 0.66 | 0.92 | 0.1 | 0.48576
|  | 1 | 0.66 | 0.57 | 0.1 | 0.03762 |  |  |  |  | 10.5
|  | 1 | 1.65 | 0.84 | 0.1 | 0.1386
|  | 1 | 0.92 | 0.8 | 0.1 | 0.0736
| -at entrance | 1 | 2.2 | 0.9 | 0.1 | 0.198
| Sub-total |  |  |  |  | 0.93358 | cum | 13568.9 | 12667.6537
| VAT calculation | [7 empty] | 1155.9083
14 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (Kg)
| -MS Flats 20mm*5mm | 0 | 0.17779 | 0.8 | 0 | 0
|  | 0 | 7.2 | 0.8 | 0 | 0
| -MS flats for fencing | 0 | 0.15 | 0.8 | 0 | 0
| -MS square pipe of 2"*2" of 1.8mm thickness for vertical post | 4 | 2.64 | 2.72 | 28.7232 | 28.7232
|  | 4 | 0.45 | 3.72 | 6.696 | 6.696
|  | 2 | 2.3 | 4.72 | 21.712 | 21.712
| -at compound | 4 | 1.75 | 2.72 | 19.04 | 19.04
|  | 4 | 1.39 | 2.72 | 15.1232 | 15.1232
| -MS square pipe 1.5"*1.5" of 1.6mm thickness for horizontal member | 1 | 13.3343 | 3.87 | 51.6039 | 51.6039
|  | 1 | 9.9343 | 3.87 | 38.4459 | 38.4459
|  | 1 | 11.6343 | 3.87 | 45.0249 | 45.0249
|  | 4 | 7.6714 | 3.87 | 118.7539 | 118.7539
| -35*35*3mm Equal angles at windows | 0 | 7.2 | 1.52 | 0 | 0
| -equal angles for fencing | 0 | 48.2 | 1.52 | 0 | 0
| -MS square rod12mm *12mm size | 0 | 0.76196 | 1.13 | 0 | 0
| Sub-total |  |  |  |  | 345.1231 | Kg | 181.17 | 62525.9541
| VAT calculation | [7 empty] | 4433.1118
15 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -at roof | 2 | 2.3368 |  | 1.04 | 4.8605 | [5 empty] | 7.6
|  | 2 | 2.9717 |  | 0.72 | 4.2792
|  | 2 | 0.87 |  | 0.18 | 0.3132
|  | 2 | 4.2161 |  | 0.675 | 5.6917
|  | 2 | 2.8711 |  | 0.405 | 2.3256
|  | 2 | 1.04 |  | 0.09 | 0.1872
|  | 2 | 2.8711 |  | 0.395 | 2.2681
|  | 2 | 1.09 |  | 0.11 | 0.2398
|  | 2 | 2.235 |  | 1.05 | 4.6935
|  | 2 | 3.97 |  | 0.675 | 5.3595
|  | 2 | 2.8955 |  | 0.35 | 2.0268
|  | 2 | 1.6254 |  | 0.11 | 0.35759
|  | 2 | 7.6714 |  | 0.5 | 7.6714
| -at one side drain | 2 | 7.1116 |  | 0.2 | 2.8446
| at compound | 2 | 2.1 |  | 1.1 | 4.62
|  | 2 | 4.267 |  | 1.7 | 14.5078
|  | 2 | 6.8577 |  | 1.3 | 17.8299
|  | 2 | 5.7909 |  | 1.155 | 13.377
|  | 2 | 10.5151 |  | 0.725 | 15.2469
|  | 2 | 10.5913 |  | 1.3 | 27.5373
|  | 2 | 2.82 |  | 1.9 | 10.716
|  | 2 | 6.883 |  | 0.57 | 7.8466
|  | 2 | 3.9622 |  | 0.57 | 4.5169
|  | 2 | 6.883 |  | 0.3 | 4.1298
|  | 2 | 2.1 |  | 0.58 | 2.436
|  | 2 | 1.5 |  | 0.39 | 1.17
|  | 18 | 0.125 |  | 0.94 | 2.115
|  | 2 | 5.5623 |  | 1.435 | 15.9639
|  | 34 | 0.1 |  | 0.81 | 2.754
| sub-total |  |  |  |  | 187.8859 | sqm | 405.86 | 76255.3663
| -VAT 13% for materials | [7 empty] | 2727.3628 |  |  | ;km]{;nfO{ 8«]l;Ë ug]{ sfo{ vfN6f] k'g]{, p7]sf] df6f] sf6\g], ;tx ldnfpg]
cflb sfo{ ;d]t -;le{;/f]8 cflb_
16 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -as of plaster excluding drain | 1 |  |  |  | 183.2659
| Sub-total |  |  |  |  | 0 | sqm | 251.77 | 0
| VAT calculation | [7 empty] | 0
17 | dfn;fdfg pknAw u/L UPVC sheet with PMMA Coating and mesh (Regular)5fgf 5fpg] sfd .
| -roof | 1 | 7.6714 | 2.8 |  | 21.48
| #REF! | 1 | 9.8811 | 1.53 |  | 15.1181
|  | 1 | 3.4 | 3.9 | 1.5328 | 2.5854 |  |  |  |  | 4.4164
| Sub-total |  |  |  |  | 39.1836 | sqm | 2271.55 | 89007.5115
| VAT calculation | [7 empty] | 10298.7829
18 | sfk]{6 b'jf] |  |  |  | Area (m2)
| -for open spaces | 1 |  |  | 4.494 | 4.494
|  | 1 |  |  | 20.8359 | 20.8359
|  | 1 | 4.25 | 2.6 |  | 11.05
|  | 1 | 7 | 1.1048 |  | 7.7339
|  | 1 | 6.55 | 2.6166 |  | 17.1386
| Sub-total |  |  |  |  | 0 | m2 | 376.7365 | 0
| VAT calculation | [7 empty] | 0
19 | ;km]{;nfO{ 8«]l;Ë ug]{ sfo{ vfN6f] k'g]{, p7]sf] df6f] sf6\g], ;tx ldnfpg] cflb sfo{ ;d]t -;le{;/f]8 cflb_
| -as of item no. 15 |  |  |  |  | 0
| -at entrance | 1 | 2.2 | 0.9 |  | 1.98
| Sub-total |  |  |  |  | 0 | m2 | 9.2 | 0
20 | Provisional sum for unforeseen works | 1 |  |  |  | 1 | PS | 2000 | 2000
21 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 450558.5023
| Total Estimated | 450558.5023 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 105.4247
| User Contribution | -24441.4977 |  | -5.4247
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on B156: DELL: 1 section
Note on G181: DELL: Quantity=sqrt(s(s-a)(s-b)(s-c))