## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- परोपकार भवन मर्मत | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/28
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | df6f]df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdu¦L !) dL=;Dd
| -existing wall | 1 | 18 | 0.23 | 0.71106 | 2.9438
| -left | 1 | 2.8 | 0.35 | 0.40689 | 0.39875
| -right | 1 | 2.8 | 0.35 | 0.47044 | 0.46103
| -Wing part upto mid length | 2 | 1.5239 | 0.35 | 0.31743 | 0.33862
| -Wing part upto end length from mid | 2 | 1.5239 | 0.35 | 0.41908 | 0.44705
| Sub-total |  |  |  |  | 4.5893 | cum | 975.2 | 4475.4417
2 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -at roof | 1 | 2.3368 | 0.23 | 0.99 | 0.53209
|  | 1 | 2.9717 | 0.23 | 0.67 | 0.45793
|  | 1 | 0.87 | 0.23 | 0.13 | 0.026013
|  | 1 | 4.2161 | 0.23 | 0.625 | 0.60606
|  | 1 | 2.8711 | 0.23 | 0.355 | 0.23442
|  | 1 | 1.04 | 0.23 | 0.04 | 0.009568
|  | 1 | 2.8711 | 0.23 | 0.345 | 0.22782
|  | 1 | 1.09 | 0.23 | 0.06 | 0.015042
|  | 1 | 2.235 | 0.23 | 1 | 0.51405
|  | 1 | 3.97 | 0.23 | 0.625 | 0.57069
|  | 1 | 2.8955 | 0.23 | 0.3 | 0.19979
|  | 1 | 1.6254 | 0.23 | 0.06 | 0.022431
|  | 1 | 7.6714 | 0.23 | 0.23 | 0.40582
|  | 1 | 7.6714 | 0.1 | 0.22 | 0.16877
| -at drain | 1 | 7.1116 | 0.23 | 0.15 | 0.24535
|  | 1 | 1.25 | 0.23 | 0.25 | 0.071875
|  | 1 | 0.10149 | 0.23 | 0.55 | 0.012839
|  | 1 | 0.10149 | 0.23 | 0.35 | 0.0081702
|  | 1 | 0.32 | 0.23 | 0.23 | 0.016928
|  | 1 | 0.5 | 0.23 | 0.35 | 0.04025
| Sub-total |  |  |  |  | 4.3859 | cum | 14362.76 | 62993.661
| VAT calculation | [7 empty] | 5879.4168
3 | dfn;fdfg pknAw u/L lh=cfO{=k¦m]ddf ;fwf/0f d]6fnfOH8 kf]lnP6/ nfldg]6]8 jf]8{sf] l;lnË nufpg] sfd -ss{t kftfsf] 5fgfd'lg_
| -false ceiling | 1 | 7.615 | 3.49 |  | 26.5764
|  | 1 | 5.74 | 2.33 |  | 13.3742
|  | 1 | 5.7 | 2.3 |  | 13.11
| Sub-total |  |  |  |  | 53.0605 | sqm | 817.76 | 43390.7954
| VAT calculation | [7 empty] | 5640.8034
4 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -at roof | 2 | 3.6574 | 1.0667 |  | 7.8031
| Sub-total |  |  |  |  | 7.8031 | sqm | 1070.9 | 8356.3331
| VAT calculation | [7 empty] | 832.9885
5 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -at drain wall | 2 | 10.5151 | 0.15 | 0.6 | 1.8927
| -at backyard | 1 | 12 | 0.23 | 0.3 | 0.828 | [5 empty] | 3691.5526
|  | 1 | 12 | 0.23 | 0.5 | 1.38
| Sub-total |  |  |  |  | 4.1007 | cum | 1950.4 | 7998.0358
6 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at drain wall base | 1 | 10.5151 | 0.6 | 0.125 | 0.78863
| -for plaster | 1 | 13.53 | 0.45 | 0.4 | 2.4354
|  | 1 | 4.5 | 0.5 | 0.4 | 0.9
|  | 0.5 | 2 | 1.5 | 0.5 | 0.75
| -for one side drain | 1 | 6.5 | 0.53 | 0.23 | 0.79235
| Sub-total |  |  |  |  | 5.6664 | cum | 663.31 | 3758.5675
7 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -at drain wall base | 1 | 10.5151 | 0.67 |  | 7.0451
| -at one side drain | 1 | 7.0101 | 0.53 |  | 3.7153
| -at entrance | 1 | 2.2 | 0.91 |  | 2.002
| -at backyard | 1 | 12.9 | 0.35 |  | 4.515
| Sub-total |  |  |  |  | 17.2774 | sqm | 1014.97 | 17536.0822
| VAT calculation | [7 empty] | 1935.4809
8 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -at drain wall base | 1 | 10.5151 | 0.67 | 0.075 | 0.52838
| -at one side drain | 1 | 7.0101 | 0.83 | 0.075 | 0.43638
| -at roof | 1 | 24.3415 | 0.23 | 0.05 | 0.27993
|  | 1 | 7.6714 | 0.1 | 0.05 | 0.038357
| -at room | 4 | 0.9 | 0.15 | 0.05 | 0.027
| -at backyard | 1 | 12.9 | 0.35 | 0.05 | 0.22575
| Sub-total |  |  |  |  | 1.5358 | cum | 12983.1 | 19939.3678
| VAT calculation | [7 empty] | 1612.8207
9 | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4) #) dL= ;Dd 9'jfgL ;d]t
| -at drain wall | 2 | 10.5151 |  | 0.5 | 10.5151
|  | 2 | 1.15 |  | 0.3 | 0.69
| Sub-total |  |  |  |  | 11.2051 | sqm | 563.26 | 6311.3772
| VAT calculation | [7 empty] | 324.3985
10 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For slab cover | 40 | 0.56 | 0.39506 | 8.8494 | 0.0088494
|  | 32 | 0.82 | 0.39506 | 10.3664 | 0.010366
|  | 3 | 0.56 | 0.39506 | 0.6637 | 0.0006637
|  | 4 | 0.47 | 0.39506 | 0.74272 | 0.00074272
|  | 5 | 1.55 | 0.39506 | 3.0617 | 0.0030617
|  | 10 | 0.74 | 0.39506 | 2.9235 | 0.0029235
|  | 5 | 0.82 | 0.39506 | 1.6198 | 0.0016198
|  | 5 | 0.7 | 0.39506 | 1.3827 | 0.0013827
| Sub-total |  |  |  |  | 0.02961 | MT | 131940 | 3906.7271
| VAT calculation | [7 empty] | 408.794
11 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -at slab cover | 16 | 0.66 |  | 0.1 | 1.056
|  | 16 | 0.92 |  | 0.1 | 1.472
|  | 2 | 0.66 |  | 0.1 | 0.132
|  | 2 | 0.57 |  | 0.1 | 0.114
|  | 2 | 1.65 |  | 0.1 | 0.33
|  | 2 | 0.84 |  | 0.1 | 0.168
|  | 2 | 0.92 |  | 0.1 | 0.184
|  | 2 | 0.8 |  | 0.1 | 0.16
| -at entrance | 2 | 0.9 |  | 0.1 | 0.18
| Sub-total |  |  |  |  | 3.796 | sqm | 814.0427 | 3090.1061
| VAT calculation | [7 empty] | 181.0591
12 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -slab cover | 8 | 0.66 | 0.92 | 0.1 | 0.48576
|  | 1 | 0.66 | 0.57 | 0.1 | 0.03762
|  | 1 | 1.65 | 0.84 | 0.1 | 0.1386
|  | 1 | 0.92 | 0.8 | 0.1 | 0.0736
| -at entrance | 1 | 2.2 | 0.91 | 0.1 | 0.2002
| Sub-total |  |  |  |  | 0.93578 | cum | 13568.9 | 12697.5052
| VAT calculation | [7 empty] | 1158.6323
13 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (Kg)
| -MS flats for fencing | 616 | 0.135 | 0.738 | 61.3721 | 61.3721
| -MS square pipe of 2"*2" of 1.8mm thickness for vertical post | 4 | 2.64 | 2.72 | 28.7232 | 28.7232
|  | 4 | 0.45 | 2.72 | 4.896 | 4.896
|  | 2 | 2.3 | 2.72 | 12.512 | 12.512
| -at compound | 4 | 1.75 | 2.72 | 19.04 | 19.04
|  | 4 | 1.39 | 2.72 | 15.1232 | 15.1232
| -MS square pipe 1.5"*1.5" of 1.6mm thickness for horizontal member | 1 | 13.3343 | 3.87 | 51.6039 | 51.6039
|  | 1 | 9.9343 | 3.87 | 38.4459 | 38.4459
|  | 1 | 11.6343 | 3.87 | 45.0249 | 45.0249
|  | 4 | 7.6714 | 3.87 | 118.7539 | 118.7539
| -1"*1"*2mm Equal angles at windows | 2 | 32.7 | 1.2 | 78.48 | 78.48
| -equal angles for fencing | 34 | 0.75 | 1.2 | 30.6 | 30.6
| -MS square rod10mm *10mm size | 274 | 0.76196 | 0.706 | 147.3971 | 147.3971
| MS black pipe of 2" *2" of 1.6mm thickness for vertical post | 1 | 8.09 | 2.32 | 18.7688 | 18.7688
| Sub-total |  |  |  |  | 670.7411 | Kg | 181.17 | 121518.1699
| VAT calculation | [7 empty] | 8615.6804
14 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -at roof | 2 | 2.3368 |  | 1.04 | 4.8605
|  | 2 | 2.9717 |  | 0.72 | 4.2792
|  | 2 | 0.87 |  | 0.18 | 0.3132
|  | 2 | 4.2161 |  | 0.675 | 5.6917
|  | 2 | 2.8711 |  | 0.405 | 2.3256
|  | 2 | 1.04 |  | 0.09 | 0.1872
|  | 2 | 2.8711 |  | 0.395 | 2.2681
|  | 2 | 1.09 |  | 0.11 | 0.2398
|  | 2 | 2.235 |  | 1.05 | 4.6935
|  | 2 | 3.97 |  | 0.675 | 5.3595
|  | 2 | 2.8955 |  | 0.35 | 2.0268
|  | 2 | 1.6254 |  | 0.11 | 0.35759
|  | 2 | 7.6714 |  | 0.5 | 7.6714
| -at one side drain | 2 | 7.1116 |  | 0.2 | 2.8446
| at compound | 2 | 2.1 |  | 1.1 | 4.62
|  | 1 | 4.267 |  | 1.7 | 7.2539
|  | 1 | 6.8577 |  | 1.3 | 8.915
|  | 1 | 5.7909 |  | 1.155 | 6.6885
|  | 1 | 10.5151 |  | 0.725 | 7.6234
|  | 1 | 10.5913 |  | 1.3 | 13.7687
|  | 1 | 3.12 |  | 1.9 | 5.928
|  | 1 | 6.883 |  | 0.57 | 3.9233
|  | 1 | 3.9622 |  | 0.57 | 2.2585
|  | 1 | 6.883 |  | 0.3 | 2.0649
|  | 1 | 2.1 |  | 0.58 | 1.218
|  | 1 | 1.5 |  | 0.39 | 0.585
|  | 18 | 0.125 |  | 0.94 | 2.115
|  | 2 | 5.5623 |  | 1.435 | 15.9639
|  | 1 | 12 |  | 0.6 | 7.2
| -deduction for plaster near gate | -1 | 0.9 |  | 0.9 | -0.81
| sub-total |  |  |  |  | 132.4348 | sqm | 405.86 | 53749.9821
| -VAT 13% for materials | [7 empty] | 1922.4313
15 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -as of plaster excluding drain | 1 |  |  |  | 129.5902
|  | -2 | 26.1914 |  | 0.45 | -23.5723
| Sub-total |  |  |  |  | 106.0179 | sqm | 251.77 | 26692.1268
| VAT calculation | [7 empty] | 1755.3172
16 | dfn;fdfg pknAw u/L UPVC sheet with PMMA Coating and mesh (Regular)5fgf 5fpg] sfd .
| -roof | 1 | 7.6714 | 2.8 |  | 21.48
| -compound | 1 | 9.8811 | 1.53 |  | 15.1181
|  | 1 | 3.4 | 3.9 | 1.5328 | 2.5854 |  |  |  |  | 4.4164
| Sub-total |  |  |  |  | 39.1836 | sqm | 2271.55 | 89007.5115
| VAT calculation | [7 empty] | 10298.7829
17 | sfk]{6 b'jf]
| -for open spaces | 1 | 1.15 | 2.5 |  | 2.875
|  | 1 | 1.7 | 2.4 |  | 4.08
|  | 1 | 1.35 | 1.4 |  | 1.89
|  | 1 | 1.575 | 3.2 |  | 5.04
|  | 1 | 1.6 | 0.65 |  | 1.04
| Sub-total |  |  |  |  | 14.925 | sqm | 376.7365 | 5622.7923
| VAT calculation | [7 empty] | 730.963
18 | ;km]{;nfO{ 8«]l;Ë ug]{ sfo{ vfN6f] k'g]{, p7]sf] df6f] sf6\g], ;tx ldnfpg] cflb sfo{ ;d]t -;le{;/f]8 cflb_
| -near compound wall | 1 | 6.55 | 2.62 |  | 17.161
|  | 1 | 8 | 3 |  | 24
| -at entrance | 1 | 2.2 | 0.91 |  | 2.002
| -as of 18 | 1 |  |  |  | 14.925
| Sub-total |  |  |  |  | 58.088 | sqm | 9.2 | 534.4096
19 | Provisional sum for unforeseen work | 1 |  |  |  | 1 | PS | 25000 | 25000
20 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 558876.5613
| Total Estimated | 558876.5613 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 84.9919
| User Contribution | 83876.5613 |  | 15.0081
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on B136: Windows User: by measurement in field by weight balance
Note on E138: Windows User: weight by measurement in field
Note on B159: DELL: 1 section
Note on G186: DELL: Quantity=sqrt(s(s-a)(s-b)(s-c))
Note on D201: DELL: at roof

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 558876.5613 |  |  |  |  | Total Valuated Amount : |  | 559505.7136
Work Started : | [7 empty] | Work Finished:
Project:- परोपकार भवन मर्मत | [7 empty] | F.Y:2081/2082
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2081/12/06
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | df6f]df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdu¦L !) dL=;Dd | cum | 4.5893 | 975.2 | 4475.4417 | 4.5893 | 975.2 | 4475.4417 | 0
2 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | cum | 4.3859 | 14362.76 | 62993.661 | 4.3859 | 14362.76 | 62993.661 | 0
| VAT calculation |  |  |  | 5879.4168 |  |  | 5879.4168 | 0
3 | dfn;fdfg pknAw u/L lh=cfO{=k¦m]ddf ;fwf/0f d]6fnfOH8 kf]lnP6/ nfldg]6]8 jf]8{sf] l;lnË nufpg] sfd -ss{t kftfsf] 5fgfd'lg_ | sqm | 53.0605 | 817.76 | 43390.7954 | 53.7414 | 817.76 | 43947.5673 | 556.7719 |  | 54238.4942
| VAT calculation |  |  |  | 5640.8034 |  |  | 5713.1837 | 72.3803
4 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd | sqm | 7.8031 | 1070.9 | 8356.3331 | 7.8031 | 1070.9 | 8356.3331 | 0
| VAT calculation |  |  |  | 832.9885 |  |  | 832.9885 | 0
5 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd . | cum | 4.1007 | 1950.4 | 7998.0358 | 4.1007 | 1950.4 | 7998.0358 | 0 |  | 9997.5447
6 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | cum | 5.6664 | 663.31 | 3758.5675 | 5.6664 | 663.31 | 3758.5675 | 0
7 | ;'Vvf O{6f RofK6f] 5fKg] sfd | sqm | 17.2774 | 1014.97 | 17536.0822 | 17.2774 | 1014.97 | 17536.0822 | 0
| VAT calculation |  |  |  | 1935.4809 |  |  | 1935.4809 | 0
8 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_ | cum | 1.5358 | 12983.1 | 19939.3678 | 1.5358 | 12983.1 | 19939.3678 | 0
| VAT calculation |  |  |  | 1612.8207 |  |  | 1612.8207 | 0
9 | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4) #) dL= ;Dd 9'jfgL ;d]t | sqm | 11.2051 | 563.26 | 6311.3772 | 11.2051 | 563.26 | 6311.3772 | 0 |  | 9821.28
| VAT calculation |  |  |  | 324.3985 |  |  | 324.3985 | 0
10 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | MT | 0.02961 | 131940 | 3906.7271 | 0.02961 | 131940 | 3906.7271 | 0
| VAT calculation |  |  |  | 408.794 |  |  | 408.794 | 0
11 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd | sqm | 3.796 | 814.0427 | 3090.1061 | 3.796 | 814.0427 | 3090.1061 | 0
| VAT calculation |  |  |  | 181.0591 |  |  | 181.0591 | 0
12 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_ | cum | 0.93578 | 13568.9 | 12697.5052 | 0.93578 | 13568.9 | 12697.5052 | 0
| VAT calculation |  |  |  | 1158.6323 |  |  | 1158.6323 | 0
13 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | Kg | 670.7411 | 181.17 | 121518.1699 | 670.7411 | 181.17 | 121518.1699 | 0 |  |  | Description | Amount w/o VAT | VAT
| VAT calculation |  |  |  | 8615.6804 |  |  | 8615.6804 | 0 |  |  | Skilled | 77342.8708
[12 empty] | Unskilled | 96111.4557
14 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/ | sqm | 132.4348 | 405.86 | 53749.9821 | 132.4348 | 405.86 | 53749.9821 | 0 |  |  | Brick | 48187.72 | 6264.4036
| -VAT 13% for materials |  |  |  | 1922.4313 |  |  | 1922.4313 | 0 |  |  | Sand | 18338.3791 | 2383.9893
[12 empty] | Cement | 24422.9034 | 3174.9774
15 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd | sqm | 106.0179 | 251.77 | 26692.1268 | 106.0179 | 251.77 | 26692.1268 | 0 |  |  | Water | 271.0865 | 35.2412
| VAT calculation |  |  |  | 1755.3172 |  |  | 1755.3172 | 0 |  |  | false ceiling | 43947.5673 | 5713.1837
[12 empty] | Color CGI sheet | 5208.2998 | 677.079
16 | dfn;fdfg pknAw u/L UPVC sheet with PMMA Coating and mesh (Regular)5fgf 5fpg] sfd . | sqm | 39.1836 | 2271.55 | 89007.5115 | 39.1836 | 2271.55 | 89007.5115 | 0 |  |  | 7mm bolt nut | 798.8417 | 103.8494
| VAT calculation |  |  |  | 10298.7829 |  |  | 10298.7829 | 0 |  |  | 8mm J hook | 271.7115 | 35.3225
[12 empty] | bitumen washer | 128.751 | 16.7376
17 | sfk]{6 b'jf] | sqm | 14.925 | 376.7365 | 5622.7923 | 14.925 | 376.7365 | 5622.7923 | 0 |  |  | aggregate | 6859.7667 | 891.7697
| VAT calculation |  |  |  | 730.963 |  |  | 730.963 | 0 |  |  | stone dust | 233.0534 | 30.2969
[12 empty] | steel rod | 3109.037 | 404.1748
18 | ;km]{;nfO{ 8«]l;Ë ug]{ sfo{ vfN6f] k'g]{, p7]sf] df6f] sf6\g], ;tx ldnfpg] cflb sfo{ ;d]t -;le{;/f]8 cflb_ | sqm | 58.088 | 9.2 | 534.4096 | 58.088 | 9.2 | 534.4096 | 0 |  |  | binding wire | 35.5319 | 4.6191
[12 empty] | 15mm ply board | 761.5543 | 99.0021
19 | Provisional sum for unforeseen work | PS | 1 | 25000 | 25000 | 1 | 25000 | 25000 | 0 |  |  | local wood Bead | 505.9404 | 65.7722
[12 empty] | killa nails | 125.268 | 16.2848
20 | Information board (सुचना पाटि) | no. | 1 | 1000 | 1000 | 1 | 1000 | 1000 | 0 |  |  | diesel | 390.0425 | 50.7055
[12 empty] | petrol | 13.8215 | 1.7968
| Total |  |  |  | 558876.5613 |  |  | 559505.7136 | 629.1522 |  |  | MS steel pipe,angle | 62378.9248 | 8109.2602
[12 empty] | red oxide primer paint | 3895.5398 | 506.4202
[12 empty] | अस्टर Primer | 2442.6524 | 317.5448
[12 empty] | weather coat | 11059.7874 | 1437.7724
[12 empty] | UPVC sheet | 74339.13 | 9664.0869
[12 empty] | self tapping screw 3" | 3401.1367 | 442.1478
[12 empty] | clip | 1481.1402 | 192.5482
[12 empty] | sfk]{6 b'jf] | 5622.7923 | 730.963
[12 empty] | gutter all materials | 25000
[12 empty] | Information board (सुचना पाटि) | 1000
[12 empty] | Total | 517684.706 | 41369.9493
[12 empty] | difference | -451.0582

## rate analysis
#REF!
हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4)
C13 | #) dL= ;Dd 9'jfgL ;d]t
b/ ljZn]if0fsf] nflu ९ j=ld= lnOPsf]
| ;¦f]t ;fwg | tx÷lsl;d | kl/df0f | PsfO{ | b/ k¦lt PsfO{ | /sd | k¦To]s ;¦f]t ;fwgsf] hDdf
| >lds | s_ l;kfn' | 1 | hjfg | 1225 | 1225
|  | v_ HofdL | 2 | hjfg | 920 | 1840 | 3065
| lgdf{0f ;fdu¦L | 300X150X100 Pd=Pd=sf] हयाबिटेक ब्रिक | 0 | j6f | 58 | 0
|  | l;d]G6 | 0.1028 | d]=6= | 12131 | 1247.06
|  | afn'jf | 0.1715 | 3=dL= | 3177 | 544.85 |  | 99000
|  | :6f]g 8:6 | 0.1516 | 3=dL= | 1234.8 | 187.19
|  | !) ld ld 8l08 | 0 | s].lh | 100 | 0 |  | 21.7
|  | kfgL | 90 | nL6/ | 0.28 | 25.2 | 2004.3
[5 empty] | jf:tljs b//]6 |  | 5069.3
| b/ k¦lt 3=dL=sf] |  |  |  | !%Ü 7]s]bf/ cf]e/x]8 |  | 760.39 | 647.7433
?= | 5829.69 | k}= |  |  | hDdf b/ /]6 |  | 5829.69 | 563.2556
[5 empty] | b/ /]6 k¦lt ju{ ld |  | 647.7433
[5 empty] | cf]e/x]8 afx]s |  | 563.2551
Block Size
1
E2 | kmnfdsf] kfOk (Prop), KnfOjf]8{ k¦of]u u/L km;{ / :nfjsf] nflu kmdf{ agfpg] sfd .
b/ ljZn]if0fsf] nflu !)) j=ld= lnOPsf]
| ;¦f]t ;fwg | tx÷lsl;d | kl/df0f | PsfO{ | b/ k¦lt PsfO{ | /sd | k¦To]s ;¦f]t ;fwgsf] hDdf
| >lds | s_ l;kfn' | 17.2 | hjfg | 1225 | 21070
|  | v_ HofdL | 25.7 | hjfg | 920 | 23644 | 44714
| lgdf{0f ;fdu¦L | !% dL=dL= jf]8{ | 16.5 | j=dL= | 1215.88 | 20062.02
|  | :yfgLo s'–sf7 | 0.232 | 3=dL= | 57449.37 | 13328.25
|  | kmnfd] kfO{k (NMB 50-M) | 0 | ;+Vof | 2304 | 0
|  | lsnf sfF6L | 25 | s]=hL= | 132 | 3300 | 36690.27
[5 empty] | jf:tljs b//]6 |  | 81404.27
| b/ k¦lt j=dL=sf] |  |  |  | !%Ü 7]s]bf/ cf]e/x]8 |  | 12210.64
| 93614.91 | ?= | 936.14 | k}= | hDdf b/ /]6 |  | 93614.91
100
gf]6 M sf7 M ^ k6s;dd k¦of]u ug{ ;lsg] To;kl5 @%Ü d"No afFsL /xg] lx;fan] ul/Psf]
1.6875x1.1x0.7516= 0.232
M KNffO{ M ^ k6s;dd k¦of]u ug{ ;lsg] To;kl5 !)Ü d"No afFsL /xg] lx;fan] ul/Psf]
100x1.1x0.9/6=16.5
M kfO{k M !% k6s;Dd k¦of]u ug{ ;lsg] To;kl5 @%Ü d"No afFsL /xg] lx;fan] ul/Psf]
88/15x0.75 =4.4
=

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- परोपकार भवन मर्मत | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/12/06
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | df6f]df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdu¦L !) dL=;Dd
| -existing wall | 1 | 18 | 0.23 | 0.71106 | 2.9438 | [5 empty] | 7.6
| -left | 1 | 2.8 | 0.35 | 0.40689 | 0.39875
| -right | 1 | 2.8 | 0.35 | 0.47044 | 0.46103
| Wing part 1 upto mid length | 2 | 1.5239 | 0.35 | 0.31743 | 0.33862
| Wing part 1 upto end length from mid | 2 | 1.5239 | 0.35 | 0.41908 | 0.44705
| Sub-total |  |  |  |  | 4.5893 | cum | 975.2 | 4475.4417
2 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -at roof | 1 | 2.3368 | 0.23 | 0.99 | 0.53209 | [5 empty] | 7.6
|  | 1 | 2.9717 | 0.23 | 0.67 | 0.45793
|  | 1 | 0.87 | 0.23 | 0.13 | 0.026013
|  | 1 | 4.2161 | 0.23 | 0.625 | 0.60606
|  | 1 | 2.8711 | 0.23 | 0.355 | 0.23442
|  | 1 | 1.04 | 0.23 | 0.04 | 0.009568
|  | 1 | 2.8711 | 0.23 | 0.345 | 0.22782
|  | 1 | 1.09 | 0.23 | 0.06 | 0.015042
|  | 1 | 2.235 | 0.23 | 1 | 0.51405
|  | 1 | 3.97 | 0.23 | 0.625 | 0.57069
|  | 1 | 2.8955 | 0.23 | 0.3 | 0.19979
|  | 1 | 1.6254 | 0.23 | 0.06 | 0.022431
|  | 1 | 7.6714 | 0.23 | 0.23 | 0.40582
|  | 1 | 7.6714 | 0.1 | 0.22 | 0.16877
| -at drain | 1 | 7.1116 | 0.23 | 0.15 | 0.24535
|  | 1 | 1.25 | 0.23 | 0.25 | 0.071875
|  | 1 | 0.10149 | 0.23 | 0.55 | 0.012839
|  | 1 | 0.10149 | 0.23 | 0.35 | 0.0081702
|  | 1 | 0.32 | 0.23 | 0.23 | 0.016928
|  | 1 | 0.5 | 0.23 | 0.35 | 0.04025
| Sub-total |  |  |  |  | 4.3859 | cum | 14362.76 | 62993.661
| VAT calculation | [7 empty] | 5879.4168
3 | dfn;fdfg pknAw u/L lh=cfO{=k¦m]ddf ;fwf/0f d]6fnfOH8 kf]lnP6/ nfldg]6]8 jf]8{sf] l;lnË nufpg] sfd -ss{t kftfsf] 5fgfd'lg_
| -false ceiling | 1 | 7.62 | 3.5 |  | 26.67 | [5 empty] | 7.6
|  | 1 | 5.75 | 2.38 |  | 13.685 | [5 empty] | 5.73
|  | 1 | 5.77 | 2.32 |  | 13.3864
| Sub-total |  |  |  |  | 53.7414 | sqm | 817.76 | 43947.5673
| VAT calculation | [7 empty] | 5713.1837
4 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -at roof | 2 | 3.6574 | 1.0667 |  | 7.8031 | [5 empty] | 7.6
| Sub-total |  |  |  |  | 7.8031 | sqm | 1070.9 | 8356.3331
| VAT calculation | [7 empty] | 832.9885
5 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -at drain wall | 2 | 10.5151 | 0.15 | 0.6 | 1.8927 | [5 empty] | 7.6
| -at backyard | 1 | 12 | 0.23 | 0.3 | 0.828
|  | 1 | 12 | 0.23 | 0.5 | 1.38
| Sub-total |  |  |  |  | 4.1007 | cum | 1950.4 | 7998.0358
6 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at drain wall base | 1 | 10.5151 | 0.6 | 0.125 | 0.78863
| -for plaster | 1 | 13.53 | 0.45 | 0.4 | 2.4354
|  | 1 | 4.5 | 0.5 | 0.4 | 0.9
|  | 0.5 | 2 | 1.5 | 0.5 | 0.75
| -for one side drain | 1 | 6.5 | 0.53 | 0.23 | 0.79235
| Sub-total |  |  |  |  | 5.6664 | cum | 663.31 | 3758.5675
7 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -at drain wall base | 1 | 10.5151 | 0.67 |  | 7.0451
| -at one side drain | 1 | 7.0101 | 0.53 |  | 3.7153
| -at entrance | 1 | 2.2 | 0.91 |  | 2.002
| -at backyard | 1 | 12.9 | 0.35 |  | 4.515
| Sub-total |  |  |  |  | 17.2774 | sqm | 1014.97 | 17536.0822
| VAT calculation | [7 empty] | 1935.4809
8 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -at drain wall base | 1 | 10.5151 | 0.67 | 0.075 | 0.52838
| -at one side drain | 1 | 7.0101 | 0.83 | 0.075 | 0.43638
| -at roof | 1 | 24.3415 | 0.23 | 0.05 | 0.27993
|  | 1 | 7.6714 | 0.1 | 0.05 | 0.038357
| -at room | 4 | 0.9 | 0.15 | 0.05 | 0.027
| -at backyard | 1 | 12.9 | 0.35 | 0.05 | 0.22575
| Sub-total |  |  |  |  | 1.5358 | cum | 12983.1 | 19939.3678
| VAT calculation | [7 empty] | 1612.8207
9 | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4) #) dL= ;Dd 9'jfgL ;d]t | [10 empty] | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4)
| -at drain wall | 2 | 10.5151 |  | 0.5 | 10.5151 | [5 empty] | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
|  | 2 | 1.15 |  | 0.3 | 0.69
| Sub-total |  |  |  |  | 11.2051 | sqm | 563.26 | 6311.3772
| VAT calculation | [7 empty] | 324.3985
13
10 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For slab cover | 40 | 0.56 | 0.39506 | 8.8494 | 0.0088494
|  | 32 | 0.82 | 0.39506 | 10.3664 | 0.010366
|  | 3 | 0.56 | 0.39506 | 0.6637 | 0.0006637
|  | 4 | 0.47 | 0.39506 | 0.74272 | 0.00074272
|  | 5 | 1.55 | 0.39506 | 3.0617 | 0.0030617
|  | 10 | 0.74 | 0.39506 | 2.9235 | 0.0029235
|  | 5 | 0.82 | 0.39506 | 1.6198 | 0.0016198
|  | 5 | 0.7 | 0.39506 | 1.3827 | 0.0013827
| Sub-total |  |  |  |  | 0.02961 | MT | 131940 | 3906.7271
| VAT calculation | [7 empty] | 408.794
11 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -at slab cover | 16 | 0.66 |  | 0.1 | 1.056
|  | 16 | 0.92 |  | 0.1 | 1.472
|  | 2 | 0.66 |  | 0.1 | 0.132
|  | 2 | 0.57 |  | 0.1 | 0.114
|  | 2 | 1.65 |  | 0.1 | 0.33
|  | 2 | 0.84 |  | 0.1 | 0.168
|  | 2 | 0.92 |  | 0.1 | 0.184
|  | 2 | 0.8 |  | 0.1 | 0.16
| -at entrance | 2 | 0.9 |  | 0.1 | 0.18
| Sub-total |  |  |  |  | 3.796 | sqm | 814.0427 | 3090.1061
| VAT calculation | [7 empty] | 181.0591
12 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -slab cover | 8 | 0.66 | 0.92 | 0.1 | 0.48576
|  | 1 | 0.66 | 0.57 | 0.1 | 0.03762 |  |  |  |  | 10.5
|  | 1 | 1.65 | 0.84 | 0.1 | 0.1386
|  | 1 | 0.92 | 0.8 | 0.1 | 0.0736
| -at entrance | 1 | 2.2 | 0.91 | 0.1 | 0.2002
| Sub-total |  |  |  |  | 0.93578 | cum | 13568.9 | 12697.5052
| VAT calculation | [7 empty] | 1158.6323
13 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (Kg)
| -MS flats for fencing | 616 | 0.135 | 0.738 | 61.3721 | 61.3721 |  |  |  |  | 616
| -MS square pipe of 2"*2" of 1.8mm thickness for vertical post | 4 | 2.64 | 2.72 | 28.7232 | 28.7232
|  | 4 | 0.45 | 2.72 | 4.896 | 4.896
|  | 2 | 2.3 | 2.72 | 12.512 | 12.512
| -at compound | 4 | 1.75 | 2.72 | 19.04 | 19.04
|  | 4 | 1.39 | 2.72 | 15.1232 | 15.1232
| -MS square pipe 1.5"*1.5" of 1.6mm thickness for horizontal member | 1 | 13.3343 | 3.87 | 51.6039 | 51.6039
|  | 1 | 9.9343 | 3.87 | 38.4459 | 38.4459
|  | 1 | 11.6343 | 3.87 | 45.0249 | 45.0249
|  | 4 | 7.6714 | 3.87 | 118.7539 | 118.7539
| -1"*1"*2mm Equal angles at windows | 2 | 32.7 | 1.2 | 78.48 | 78.48
| -equal angles for fencing | 34 | 0.75 | 1.2 | 30.6 | 30.6
| -MS square rod10mm *10mm size | 274 | 0.76196 | 0.706 | 147.3971 | 147.3971 |  |  |  |  | #REF!
| MS black pipe of 2" *2" of 1.6mm thickness for vertical post | 1 | 8.09 | 2.32 | 18.7688 | 18.7688
| Sub-total |  |  |  |  | 670.7411 | Kg | 181.17 | 121518.1699
| VAT calculation | [7 empty] | 8615.6804
14 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -at roof | 2 | 2.3368 |  | 1.04 | 4.8605 | [5 empty] | 7.6
|  | 2 | 2.9717 |  | 0.72 | 4.2792
|  | 2 | 0.87 |  | 0.18 | 0.3132
|  | 2 | 4.2161 |  | 0.675 | 5.6917
|  | 2 | 2.8711 |  | 0.405 | 2.3256
|  | 2 | 1.04 |  | 0.09 | 0.1872
|  | 2 | 2.8711 |  | 0.395 | 2.2681
|  | 2 | 1.09 |  | 0.11 | 0.2398
|  | 2 | 2.235 |  | 1.05 | 4.6935
|  | 2 | 3.97 |  | 0.675 | 5.3595
|  | 2 | 2.8955 |  | 0.35 | 2.0268
|  | 2 | 1.6254 |  | 0.11 | 0.35759
|  | 2 | 7.6714 |  | 0.5 | 7.6714
| -at one side drain | 2 | 7.1116 |  | 0.2 | 2.8446
| at compound | 2 | 2.1 |  | 1.1 | 4.62
|  | 1 | 4.267 |  | 1.7 | 7.2539
|  | 1 | 6.8577 |  | 1.3 | 8.915
|  | 1 | 5.7909 |  | 1.155 | 6.6885
|  | 1 | 10.5151 |  | 0.725 | 7.6234
|  | 1 | 10.5913 |  | 1.3 | 13.7687
|  | 1 | 3.12 |  | 1.9 | 5.928
|  | 1 | 6.883 |  | 0.57 | 3.9233
|  | 1 | 3.9622 |  | 0.57 | 2.2585
|  | 1 | 6.883 |  | 0.3 | 2.0649
|  | 1 | 2.1 |  | 0.58 | 1.218
|  | 1 | 1.5 |  | 0.39 | 0.585
|  | 18 | 0.125 |  | 0.94 | 2.115
|  | 2 | 5.5623 |  | 1.435 | 15.9639
|  | 1 | 12 |  | 0.6 | 7.2
| -deduction for plaster near gate | -1 | 0.9 |  | 0.9 | -0.81
| sub-total |  |  |  |  | 132.4348 | sqm | 405.86 | 53749.9821
| -VAT 13% for materials | [7 empty] | 1922.4313 |  |  | ;km]{;nfO{ 8«]l;Ë ug]{ sfo{ vfN6f] k'g]{, p7]sf] df6f] sf6\g], ;tx ldnfpg]
cflb sfo{ ;d]t -;le{;/f]8 cflb_
15 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -as of plaster excluding drain | 1 |  |  |  | 129.5902
|  | -2 | 26.1914 |  | 0.45 | -23.5723
| Sub-total |  |  |  |  | 106.0179 | sqm | 251.77 | 26692.1268
| VAT calculation | [7 empty] | 1755.3172
16 | dfn;fdfg pknAw u/L UPVC sheet with PMMA Coating and mesh (Regular)5fgf 5fpg] sfd .
| -roof | 1 | 7.6714 | 2.8 |  | 21.48
| -compound | 1 | 9.8811 | 1.53 |  | 15.1181
|  | 1 | 3.4 | 3.9 | 1.5328 | 2.5854 |  |  |  |  | 4.4164
| Sub-total |  |  |  |  | 39.1836 | sqm | 2271.55 | 89007.5115
| VAT calculation | [7 empty] | 10298.7829
17 | sfk]{6 b'jf]
| -for open spaces | 1 | 1.15 | 2.5 |  | 2.875
|  | 1 | 1.7 | 2.4 |  | 4.08
|  | 1 | 1.35 | 1.4 |  | 1.89
|  | 1 | 1.575 | 3.2 |  | 5.04
|  | 1 | 1.6 | 0.65 |  | 1.04
| Sub-total |  |  |  |  | 14.925 | sqm | 376.7365 | 5622.7923
| VAT calculation | [7 empty] | 730.963
18 | ;km]{;nfO{ 8«]l;Ë ug]{ sfo{ vfN6f] k'g]{, p7]sf] df6f] sf6\g], ;tx ldnfpg] cflb sfo{ ;d]t -;le{;/f]8 cflb_
| -near compound wall | 1 | 6.55 | 2.62 |  | 17.161
|  | 1 | 8 | 3 |  | 24
| -at entrance | 1 | 2.2 | 0.91 |  | 2.002
| -as of 18 | 1 |  |  |  | 14.925
| Sub-total |  |  |  |  | 58.088 | sqm | 9.2 | 534.4096
19 | Provisional sum for unforeseen work | 1 |  |  |  | 1 | PS | 25000 | 25000
20 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 559505.7136
| Total Valuated | 559505.7136 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 84.8964
| User Contribution | 84505.7136 |  | 15.1036
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on B136: Windows User: by measurement in field by weight balance
Note on E138: Windows User: weight by measurement in field
Note on B159: DELL: 1 section
Note on G186: DELL: Quantity=sqrt(s(s-a)(s-b)(s-c))
Note on D201: DELL: at roof

## measurement
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- परोपकार भवन मर्मत | [9 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [9 empty] | Date:2081/12/06
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | df6f]df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdu¦L !) dL=;Dd
| -existing wall | 1 | 18 | 0.23 | 0.71106 | 2.9438 | [5 empty] | 7.6
| -left | 1 | 2.8 | 0.35 | 0.40689 | 0.39875
| -right | 1 | 2.8 | 0.35 | 0.47044 | 0.46103
| Wing part 1 upto mid length | 2 | 1.5239 | 0.35 | 0.31743 | 0.33862
| Wing part 1 upto end length from mid | 2 | 1.5239 | 0.35 | 0.41908 | 0.44705
| Sub-total |  |  |  |  | 4.5893 | cum | 975.2 | 4475.4417
2 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -at roof | 1 | 2.3368 | 0.23 | 0.99 | 0.53209 | [5 empty] | 7.6
|  | 1 | 2.9717 | 0.23 | 0.67 | 0.45793
|  | 1 | 0.87 | 0.23 | 0.13 | 0.026013
|  | 1 | 4.2161 | 0.23 | 0.625 | 0.60606
|  | 1 | 2.8711 | 0.23 | 0.355 | 0.23442
|  | 1 | 1.04 | 0.23 | 0.04 | 0.009568
|  | 1 | 2.8711 | 0.23 | 0.345 | 0.22782
|  | 1 | 1.09 | 0.23 | 0.06 | 0.015042
|  | 1 | 2.235 | 0.23 | 1 | 0.51405
|  | 1 | 3.97 | 0.23 | 0.625 | 0.57069
|  | 1 | 2.8955 | 0.23 | 0.3 | 0.19979
|  | 1 | 1.6254 | 0.23 | 0.06 | 0.022431
|  | 1 | 7.6714 | 0.23 | 0.23 | 0.40582
|  | 1 | 7.6714 | 0.1 | 0.22 | 0.16877
| -at drain | 1 | 7.1116 | 0.23 | 0.15 | 0.24535
|  | 1 | 1.25 | 0.23 | 0.25 | 0.071875
|  | 1 | 0.10149 | 0.23 | 0.55 | 0.012839
|  | 1 | 0.10149 | 0.23 | 0.35 | 0.0081702
|  | 1 | 0.32 | 0.23 | 0.23 | 0.016928
|  | 1 | 0.5 | 0.23 | 0.35 | 0.04025
| Sub-total |  |  |  |  | 4.3859 | cum | 14362.76 | 62993.661
| VAT calculation | [7 empty] | 5879.4168
3 | dfn;fdfg pknAw u/L lh=cfO{=k¦m]ddf ;fwf/0f d]6fnfOH8 kf]lnP6/ nfldg]6]8 jf]8{sf] l;lnË nufpg] sfd -ss{t kftfsf] 5fgfd'lg_
| -false ceiling | 1 | 7.62 | 3.5 |  | 26.67 | [5 empty] | 7.6
|  | 1 | 5.75 | 2.38 |  | 13.685 | [5 empty] | 5.73
|  | 1 | 5.77 | 2.32 |  | 13.3864
| Sub-total |  |  |  |  | 53.7414 | sqm | 817.76 | 43947.5673
| VAT calculation | [7 empty] | 5713.1837
4 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -at roof | 2 | 3.6574 | 1.0667 |  | 7.8031 | [5 empty] | 7.6
| Sub-total |  |  |  |  | 7.8031 | sqm | 1070.9 | 8356.3331
| VAT calculation | [7 empty] | 832.9885
5 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -at drain wall | 2 | 10.5151 | 0.15 | 0.6 | 1.8927 | [5 empty] | 7.6
| -at backyard | 1 | 12 | 0.23 | 0.3 | 0.828
|  | 1 | 12 | 0.23 | 0.5 | 1.38
| Sub-total |  |  |  |  | 4.1007 | cum | 1950.4 | 7998.0358
6 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at drain wall base | 1 | 10.5151 | 0.6 | 0.125 | 0.78863
| -for plaster | 1 | 13.53 | 0.45 | 0.4 | 2.4354
|  | 1 | 4.5 | 0.5 | 0.4 | 0.9
|  | 0.5 | 2 | 1.5 | 0.5 | 0.75
| -for one side drain | 1 | 6.5 | 0.53 | 0.23 | 0.79235
| Sub-total |  |  |  |  | 5.6664 | cum | 663.31 | 3758.5675
7 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -at drain wall base | 1 | 10.5151 | 0.67 |  | 7.0451
| -at one side drain | 1 | 7.0101 | 0.53 |  | 3.7153
| -at entrance | 1 | 2.2 | 0.91 |  | 2.002
| -at backyard | 1 | 12.9 | 0.35 |  | 4.515
| Sub-total |  |  |  |  | 17.2774 | sqm | 1014.97 | 17536.0822
| VAT calculation | [7 empty] | 1935.4809
8 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -at drain wall base | 1 | 10.5151 | 0.67 | 0.075 | 0.52838
| -at one side drain | 1 | 7.0101 | 0.83 | 0.075 | 0.43638
| -at roof | 1 | 24.3415 | 0.23 | 0.05 | 0.27993
|  | 1 | 7.6714 | 0.1 | 0.05 | 0.038357
| -at room | 4 | 0.9 | 0.15 | 0.05 | 0.027
| -at backyard | 1 | 12.9 | 0.35 | 0.05 | 0.22575
| Sub-total |  |  |  |  | 1.5358 | cum | 12983.1 | 19939.3678
| VAT calculation | [7 empty] | 1612.8207
9 | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4) #) dL= ;Dd 9'jfgL ;d]t | [10 empty] | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4)
| -at drain wall | 2 | 10.5151 |  | 0.5 | 10.5151 | [5 empty] | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
|  | 2 | 1.15 |  | 0.3 | 0.69
| Sub-total |  |  |  |  | 11.2051 | sqm | 563.26 | 6311.3772
| VAT calculation | [7 empty] | 324.3985
13
10 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For slab cover | 40 | 0.56 | 0.39506 | 8.8494 | 0.0088494
|  | 32 | 0.82 | 0.39506 | 10.3664 | 0.010366
|  | 3 | 0.56 | 0.39506 | 0.6637 | 0.0006637
|  | 4 | 0.47 | 0.39506 | 0.74272 | 0.00074272
|  | 5 | 1.55 | 0.39506 | 3.0617 | 0.0030617
|  | 10 | 0.74 | 0.39506 | 2.9235 | 0.0029235
|  | 5 | 0.82 | 0.39506 | 1.6198 | 0.0016198
|  | 5 | 0.7 | 0.39506 | 1.3827 | 0.0013827
| Sub-total |  |  |  |  | 0.02961 | MT | 131940 | 3906.7271
| VAT calculation | [7 empty] | 408.794
11 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -at slab cover | 16 | 0.66 |  | 0.1 | 1.056
|  | 16 | 0.92 |  | 0.1 | 1.472
|  | 2 | 0.66 |  | 0.1 | 0.132
|  | 2 | 0.57 |  | 0.1 | 0.114
|  | 2 | 1.65 |  | 0.1 | 0.33
|  | 2 | 0.84 |  | 0.1 | 0.168
|  | 2 | 0.92 |  | 0.1 | 0.184
|  | 2 | 0.8 |  | 0.1 | 0.16
| -at entrance | 2 | 0.9 |  | 0.1 | 0.18
| Sub-total |  |  |  |  | 3.796 | sqm | 814.0427 | 3090.1061
| VAT calculation | [7 empty] | 181.0591
12 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -slab cover | 8 | 0.66 | 0.92 | 0.1 | 0.48576
|  | 1 | 0.66 | 0.57 | 0.1 | 0.03762 |  |  |  |  | 10.5
|  | 1 | 1.65 | 0.84 | 0.1 | 0.1386
|  | 1 | 0.92 | 0.8 | 0.1 | 0.0736
| -at entrance | 1 | 2.2 | 0.91 | 0.1 | 0.2002
| Sub-total |  |  |  |  | 0.93578 | cum | 13568.9 | 12697.5052
| VAT calculation | [7 empty] | 1158.6323
13 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (Kg)
| -MS flats for fencing | 616 | 0.135 | 0.738 | 61.3721 | 61.3721 |  |  |  |  | 616
| -MS square pipe of 2"*2" of 1.8mm thickness for vertical post | 4 | 2.64 | 2.72 | 28.7232 | 28.7232
|  | 4 | 0.45 | 2.72 | 4.896 | 4.896
|  | 2 | 2.3 | 2.72 | 12.512 | 12.512
| -at compound | 4 | 1.75 | 2.72 | 19.04 | 19.04
|  | 4 | 1.39 | 2.72 | 15.1232 | 15.1232
| -MS square pipe 1.5"*1.5" of 1.6mm thickness for horizontal member | 1 | 13.3343 | 3.87 | 51.6039 | 51.6039
|  | 1 | 9.9343 | 3.87 | 38.4459 | 38.4459
|  | 1 | 11.6343 | 3.87 | 45.0249 | 45.0249
|  | 4 | 7.6714 | 3.87 | 118.7539 | 118.7539
| -1"*1"*2mm Equal angles at windows | 2 | 32.7 | 1.2 | 78.48 | 78.48
| -equal angles for fencing | 34 | 0.75 | 1.2 | 30.6 | 30.6
| -MS square rod10mm *10mm size | 274 | 0.76196 | 0.706 | 147.3971 | 147.3971 |  |  |  |  | #REF!
| MS black pipe of 2" *2" of 1.6mm thickness for vertical post | 1 | 8.09 | 2.32 | 18.7688 | 18.7688
| Sub-total |  |  |  |  | 670.7411 | Kg | 181.17 | 121518.1699
| VAT calculation | [7 empty] | 8615.6804
14 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -at roof | 2 | 2.3368 |  | 1.04 | 4.8605 | [5 empty] | 7.6
|  | 2 | 2.9717 |  | 0.72 | 4.2792
|  | 2 | 0.87 |  | 0.18 | 0.3132
|  | 2 | 4.2161 |  | 0.675 | 5.6917
|  | 2 | 2.8711 |  | 0.405 | 2.3256
|  | 2 | 1.04 |  | 0.09 | 0.1872
|  | 2 | 2.8711 |  | 0.395 | 2.2681
|  | 2 | 1.09 |  | 0.11 | 0.2398
|  | 2 | 2.235 |  | 1.05 | 4.6935
|  | 2 | 3.97 |  | 0.675 | 5.3595
|  | 2 | 2.8955 |  | 0.35 | 2.0268
|  | 2 | 1.6254 |  | 0.11 | 0.35759
|  | 2 | 7.6714 |  | 0.5 | 7.6714
| -at one side drain | 2 | 7.1116 |  | 0.2 | 2.8446
| at compound | 2 | 2.1 |  | 1.1 | 4.62
|  | 1 | 4.267 |  | 1.7 | 7.2539
|  | 1 | 6.8577 |  | 1.3 | 8.915
|  | 1 | 5.7909 |  | 1.155 | 6.6885
|  | 1 | 10.5151 |  | 0.725 | 7.6234
|  | 1 | 10.5913 |  | 1.3 | 13.7687
|  | 1 | 3.12 |  | 1.9 | 5.928
|  | 1 | 6.883 |  | 0.57 | 3.9233
|  | 1 | 3.9622 |  | 0.57 | 2.2585
|  | 1 | 6.883 |  | 0.3 | 2.0649
|  | 1 | 2.1 |  | 0.58 | 1.218
|  | 1 | 1.5 |  | 0.39 | 0.585
|  | 18 | 0.125 |  | 0.94 | 2.115
|  | 2 | 5.5623 |  | 1.435 | 15.9639
|  | 1 | 12 |  | 0.6 | 7.2
| -deduction for plaster near gate | -1 | 0.9 |  | 0.9 | -0.81
| sub-total |  |  |  |  | 132.4348 | sqm | 405.86 | 53749.9821
| -VAT 13% for materials | [7 empty] | 1922.4313 |  |  | ;km]{;nfO{ 8«]l;Ë ug]{ sfo{ vfN6f] k'g]{, p7]sf] df6f] sf6\g], ;tx ldnfpg]
cflb sfo{ ;d]t -;le{;/f]8 cflb_
15 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -as of plaster excluding drain | 1 |  |  |  | 129.5902
|  | -2 | 26.1914 |  | 0.45 | -23.5723
| Sub-total |  |  |  |  | 106.0179 | sqm | 251.77 | 26692.1268
| VAT calculation | [7 empty] | 1755.3172
16 | dfn;fdfg pknAw u/L UPVC sheet with PMMA Coating and mesh (Regular)5fgf 5fpg] sfd .
| -roof | 1 | 7.6714 | 2.8 |  | 21.48
| -compound | 1 | 9.8811 | 1.53 |  | 15.1181
|  | 1 | 3.4 | 3.9 | 1.5328 | 2.5854 |  |  |  |  | 4.4164
| Sub-total |  |  |  |  | 39.1836 | sqm | 2271.55 | 89007.5115
| VAT calculation | [7 empty] | 10298.7829
17 | sfk]{6 b'jf]
| -for open spaces | 1 | 1.15 | 2.5 |  | 2.875
|  | 1 | 1.7 | 2.4 |  | 4.08
|  | 1 | 1.35 | 1.4 |  | 1.89
|  | 1 | 1.575 | 3.2 |  | 5.04
|  | 1 | 1.6 | 0.65 |  | 1.04
| Sub-total |  |  |  |  | 14.925 | sqm | 376.7365 | 5622.7923
| VAT calculation | [7 empty] | 730.963
18 | ;km]{;nfO{ 8«]l;Ë ug]{ sfo{ vfN6f] k'g]{, p7]sf] df6f] sf6\g], ;tx ldnfpg] cflb sfo{ ;d]t -;le{;/f]8 cflb_
| -near compound wall | 1 | 6.55 | 2.62 |  | 17.161
|  | 1 | 8 | 3 |  | 24
| -at entrance | 1 | 2.2 | 0.91 |  | 2.002
| -as of 18 | 1 |  |  |  | 14.925
| Sub-total |  |  |  |  | 58.088 | sqm | 9.2 | 534.4096
19 | Provisional sum for unforeseen work | 1 |  |  |  | 1 | PS | 25000 | 25000
20 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 559505.7136
| Total Valuated | 559505.7136 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 84.8964
| User Contribution | 84505.7136 |  | 15.1036
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on B136: Windows User: by measurement in field by weight balance
Note on E138: Windows User: weight by measurement in field
Note on B159: DELL: 1 section
Note on G186: DELL: Quantity=sqrt(s(s-a)(s-b)(s-c))
Note on D201: DELL: at roof