## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | #REF! |  |  |  |  | Total Valuated Amount : |  | #REF!
Work Started : | [7 empty] | Work Finished:
#REF! | [7 empty] | F.Y:2079/80
#REF! | [7 empty] | Date:2079/06/13
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  |  | #REF! |  |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total |  |  |  | #REF! |  |  | #REF! | #REF!

## Sheet4 (2)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- परोपकार भवन मर्मत | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/29
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | dfn;fdfg pknAw u/L lh=cfO{=k¦m]ddf ;fwf/0f d]6fnfOH8 kf]lnP6/ nfldg]6]8 jf]8{sf] l;lnË nufpg] sfd -ss{t kftfsf] 5fgfd'lg_
| -false ceiling | 1 | 7.615 | 3.49 |  | 26.5764 |  |  |  |  | 7.6
|  | 1 | 5.74 | 2.33 |  | 13.3742 |  |  |  |  | 5.73
|  | 1 | 5.7 | 2.3 |  | 13.11
| Sub-total |  |  |  |  | 53.0605 | sqm | 817.76 | 43390.7954
| VAT calculation | [7 empty] | 5640.8034
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -at roof | 2 | 3.6574 | 1.0667 |  | 7.8031 |  |  |  |  | 7.6
| Sub-total |  |  |  |  | 7.8031 | sqm | 1070.9 | 8356.3331
| VAT calculation | [7 empty] | 111.6392
3 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -at drain wall | 2 | 9.7531 | 0.15 | 0.6 | 1.7556 |  |  |  |  | 7.6
| Sub-total |  |  |  |  | 1.7556 | cum | 1950.4 | 3424.0488
| VAT calculation | [7 empty] | 445.1263
4 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at drain wall base | 1 | 9.7531 | 0.4 | 0.125 | 0.48766
| Sub-total |  |  |  |  | 0.48766 | cum | 663.31 | 323.4672
5 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -at drain wall base | 1 | 9.7531 | 0.7 |  | 6.8272
| Sub-total |  |  |  |  | 6.8272 | sqm | 1014.97 | 6929.3898
| VAT calculation | [7 empty] | 764.806
6 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -at drain wall base | 1 | 9.7531 | 0.7 | 0.1 | 0.68272
| Sub-total |  |  |  |  | 0.68272 | cum | 1014.97 | 692.939
| VAT calculation | [7 empty] | 76.4806
7 | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4) #) dL= ;Dd 9'jfgL ;d]t | [9 empty] | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4)
| -at drain wall | 2 | 9.7531 | 0.15 | 0.6 | 1.7556 |  |  |  |  | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| Sub-total |  |  |  |  | 1.7556 | cum | 8569.3 | 15043.9403
| VAT calculation | [7 empty] | 79.5066
13
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For slab cover | 5 | 0.75 | 0.39506 | 1.4815 | 0.0014815
|  | 65 | 0.7 | 0.39506 | 17.9753 | 0.017975
|  | 5 | 0.9 | 0.39506 | 1.7778 | 0.0017778
|  | 6 | 0.83816 | 0.39506 | 1.9867 | 0.0019867
| Sub-total |  |  |  |  | 0.023221 | MT | 131940 | 3063.8204
| VAT calculation | [7 empty] | 320.5935
9 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -at slab cover | 26 | 0.75 |  | 0.1 | 1.95 |  |  |  |  | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
|  | 26 | 0.7 |  | 0.1 | 1.82
|  | 2 | 0.9 |  | 0.1 | 0.18
|  | 2 | 0.83816 |  | 0.1 | 0.16763
| Sub-total |  |  |  |  | 4.1176 | sqm | 814.0427 | 3351.9281
| VAT calculation | [7 empty] | 47.6974
10 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_ | [9 empty] | 13
| -slab cover | 1 | 9.7531 | 0.7 | 0.1 | 0.68272 |  |  |  |  | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
|  | 1 | 0.9 | 0.83816 | 0.1 | 0.075434
| Sub-total |  |  |  |  | 0.75815 | cum | 814.0427 | 617.1689
| VAT calculation | [7 empty] | 47.6974
11 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (Kg)
| -MS Flats 20mm*5mm | 6 | 0.17779 | 0.8 | 0.8534 | 0.8534
|  | 2 | 7.2 | 0.8 | 11.52 | 11.52
| -MS flats for fencing | 482 | 0.15 | 0.8 | 57.84 | 57.84
| -MS square pipe of 2"*2" of 1.8mm thickness for vertical post | 4 | 2.2859 | 2.72 | 24.8705 | 24.8705
| -MS square pipe 1.5"*1.5" of 1.6mm thickness for horizontal member | 1 | 7.2 | 3.87 | 27.864 | 27.864
|  | 4 | 2.5398 | 3.87 | 39.3157 | 39.3157
| -35*35*3mm Equal angles at windows | 1 | 7.2 | 1.52 | 10.944 | 10.944
| -equal angles for fencing | 2 | 48.2 | 1.52 | 146.528 | 146.528
| -MS square rod12mm *12mm size | 482 | 0.76196 | 1.13 | 415.0107 | 415.0107
| Sub-total |  |  |  |  | 734.7462 | Kg | 181.17 | 133113.9764
| VAT calculation | [7 empty] | 9437.8271
12 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 2 | 2.0691 |  | 1.6 | 6.6212
|  | 1 | 12.1 |  | 1.5167 | 18.3517
|  | 1 | 12.1 |  | 1.3 | 15.73
|  | 1 | 5.8 |  | 1.4 | 8.12
|  | 1 | 5.8 |  | 1.0972 | 6.3639
|  | 1 | 10.6 |  | 1.27 | 13.462
|  | 1 | 1.8287 |  | 0.91436 | 1.6721
|  | 1 | 1.5239 |  | 0.60957 | 0.92894
|  | 1 | 12.97 |  | 0.3 | 3.891
| sub-total |  |  |  |  | 75.1409 | sqm | 405.86 | 30496.6698
| -VAT 13% for materials | [7 empty] | 1090.7492
13 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -as of plaster | 1 |  |  |  | 75.1409
| Sub-total |  |  |  |  | 75.1409 | sqm | 251.77 | 18918.2146
| VAT calculation | [7 empty] | 1244.0922
14 | !=@ ld=ld= Kn]g kmfO{j/ Unf; kftfn] 5fgf 5fpg] sfd
| -roof | 1 | 7.2 | 2.6922 |  | 19.3836
| Sub-total |  |  |  |  | 19.3836 | sqm | 2146.57 | 41608.2597
| VAT calculation | [7 empty] | 4779.7266
15 | Provisional sum for unforeseen works | 1 |  |  |  | 1 | PS | 3000 | 3000
16 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 336917.697
| Total Estimated | 336917.697 |  | 100
| Budget allocated | 300000
| Municipal payment | 285000 |  | 84.5904
| User Contribution | 51917.697 |  | 15.4096
| Contingencies | 9000 |  | 3
| Maintanince | 6000 |  | 2

## rate analysis
#REF!
हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4)
C13 | #) dL= ;Dd 9'jfgL ;d]t
b/ ljZn]if0fsf] nflu ९ j=ld= lnOPsf]
| ;¦f]t ;fwg | tx÷lsl;d | kl/df0f | PsfO{ | b/ k¦lt PsfO{ | /sd | k¦To]s ;¦f]t ;fwgsf] hDdf
| >lds | s_ l;kfn' | 1 | hjfg | 1225 | 1225
|  | v_ HofdL | 2 | hjfg | 920 | 1840 | 3065
| lgdf{0f ;fdu¦L | 300X150X100 Pd=Pd=sf] हयाबिटेक ब्रिक | 0 | j6f | 58 | 0
|  | l;d]G6 | 0.1028 | d]=6= | 12131 | 1247.06
|  | afn'jf | 0.1715 | 3=dL= | 3177 | 544.85 |  | 99000
|  | :6f]g 8:6 | 0.1516 | 3=dL= | 1234.8 | 187.19
|  | !) ld ld 8l08 | 35 | s].lh | 100 | 3500 |  | 21.7
|  | kfgL | 90 | nL6/ | 0.28 | 25.2 | 5504.3
[5 empty] | jf:tljs b//]6 |  | 8569.3
| b/ k¦lt 3=dL=sf] |  |  |  | !%Ü 7]s]bf/ cf]e/x]8 |  | 1285.39
?= | 9854.69 | k}= |  |  | hDdf b/ /]6 |  | 9854.69
[5 empty] | b/ /]6 k¦lt ju{ ld |  | 1094.9656
[5 empty] | cf]e/x]8 afx]s |  | 952.144
Block Size
1
E2 | kmnfdsf] kfOk (Prop), KnfOjf]8{ k¦of]u u/L km;{ / :nfjsf] nflu kmdf{ agfpg] sfd .
b/ ljZn]if0fsf] nflu !)) j=ld= lnOPsf]
| ;¦f]t ;fwg | tx÷lsl;d | kl/df0f | PsfO{ | b/ k¦lt PsfO{ | /sd | k¦To]s ;¦f]t ;fwgsf] hDdf
| >lds | s_ l;kfn' | 17.2 | hjfg | 1225 | 21070
|  | v_ HofdL | 25.7 | hjfg | 920 | 23644 | 44714
| lgdf{0f ;fdu¦L | !% dL=dL= jf]8{ | 16.5 | j=dL= | 1215.88 | 20062.02
|  | :yfgLo s'–sf7 | 0.232 | 3=dL= | 57449.37 | 13328.25
|  | kmnfd] kfO{k (NMB 50-M) | 0 | ;+Vof | 2304 | 0
|  | lsnf sfF6L | 25 | s]=hL= | 132 | 3300 | 36690.27
[5 empty] | jf:tljs b//]6 |  | 81404.27
| b/ k¦lt j=dL=sf] |  |  |  | !%Ü 7]s]bf/ cf]e/x]8 |  | 12210.64
| 93614.91 | ?= | 936.14 | k}= | hDdf b/ /]6 |  | 93614.91
100
gf]6 M sf7 M ^ k6s;dd k¦of]u ug{ ;lsg] To;kl5 @%Ü d"No afFsL /xg] lx;fan] ul/Psf]
1.6875x1.1x0.7516= 0.232
M KNffO{ M ^ k6s;dd k¦of]u ug{ ;lsg] To;kl5 !)Ü d"No afFsL /xg] lx;fan] ul/Psf]
100x1.1x0.9/6=16.5
M kfO{k M !% k6s;Dd k¦of]u ug{ ;lsg] To;kl5 @%Ü d"No afFsL /xg] lx;fan] ul/Psf]
88/15x0.75 =4.4
=

## upvc
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- परोपकार भवन मर्मत | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/29
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | df6f]df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdu¦L !) dL=;Dd
| -existing wall | 1 | 18 | 0.1 | 0.71106 | 1.2799 |  |  |  |  | 7.6
| Sub-total |  |  |  |  | 1.2799 | cum | 975.2 | 1248.1728
2 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -at roof | 1 | 18 | 0.23 | 0.71106 | 2.9438 |  |  |  |  | 7.6
| -at drain | 1 | 6.55 | 0.23 | 0.3 | 0.45195
| Sub-total |  |  |  |  | 3.3958 | cum | 14362.76 | 48772.3957
| VAT calculation | [7 empty] | 4552.0968
3 | dfn;fdfg pknAw u/L lh=cfO{=k¦m]ddf ;fwf/0f d]6fnfOH8 kf]lnP6/ nfldg]6]8 jf]8{sf] l;lnË nufpg] sfd -ss{t kftfsf] 5fgfd'lg_
| -false ceiling | 1 | 7.615 | 3.49 |  | 26.5764 |  |  |  |  | 7.6
|  | 1 | 5.74 | 2.33 |  | 13.3742 |  |  |  |  | 5.73
|  | 1 | 5.7 | 2.3 |  | 13.11
| Sub-total |  |  |  |  | 53.0605 | sqm | 817.76 | 43390.7954
| VAT calculation | [7 empty] | 5640.8034
4 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -at roof | 3 | 3.6574 | 1.0667 |  | 11.7046 |  |  |  |  | 7.6
| Sub-total |  |  |  |  | 11.7046 | sqm | 1070.9 | 12534.4997
| VAT calculation | [7 empty] | 1306.6966
5 | )=%) dL=dL= Kn]g zL6sf] !%) ld=ld= rf}8fO{, u6/ agfO{ jf;/
| -at roof | 1 | 13.4 |  |  | 13.4 |  |  |  |  | 7.6
| Sub-total |  |  |  |  | 13.4 | rm | 1108.01 | 14847.334
| VAT calculation | [7 empty] | 1232.7106
6 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -at drain wall | 2 | 9.7531 | 0.15 | 0.6 | 1.7556 |  |  |  |  | 7.6
| Sub-total |  |  |  |  | 1.7556 | cum | 1950.4 | 3424.0488
| VAT calculation | [7 empty] | 445.1263
7 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at drain wall base | 1 | 9.7531 | 0.4 | 0.125 | 0.48766
| Sub-total |  |  |  |  | 0.48766 | cum | 663.31 | 323.4672
8 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -at drain wall base | 1 | 9.7531 | 0.7 |  | 6.8272
| -at one side drain | 1 | 6.55 | 0.23 |  | 1.5065
| -at entrance | 1 | 1.95 | 1 |  | 1.95
| Sub-total |  |  |  |  | 10.2837 | sqm | 1014.97 | 10437.6336
| VAT calculation | [7 empty] | 1152.0156
9 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -at drain wall base | 1 | 9.7531 | 0.7 | 0.1 | 0.68272
| -at one side drain | 1 | 6.55 | 0.53 | 0.075 | 0.26036
| -at roof | 1 | 18 | 0.23 | 0.05 | 0.207
| Sub-total |  |  |  |  | 1.1501 | cum | 12983.1 | 14931.619
| VAT calculation | [7 empty] | 1207.7627
10 | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4) #) dL= ;Dd 9'jfgL ;d]t | [9 empty] | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4)
| -at drain wall | 2 | 9.7531 | 0.15 | 0.6 | 1.7556 |  |  |  |  | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| Sub-total |  |  |  |  | 1.7556 | cum | 8569.3 | 15043.9403
| VAT calculation | [7 empty] | 139.5787
13
11 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For slab cover | 5 | 0.75 | 0.39506 | 1.4815 | 0.0014815
|  | 65 | 0.7 | 0.39506 | 17.9753 | 0.017975
|  | 5 | 0.9 | 0.39506 | 1.7778 | 0.0017778
|  | 6 | 0.83816 | 0.39506 | 1.9867 | 0.0019867
| Sub-total |  |  |  |  | 0.023221 | MT | 131940 | 3063.8204
| VAT calculation | [7 empty] | 320.5935
12 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -at slab cover | 26 | 0.75 |  | 0.1 | 1.95 |  |  |  |  | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
|  | 26 | 0.7 |  | 0.1 | 1.82
|  | 2 | 0.9 |  | 0.1 | 0.18
|  | 2 | 0.83816 |  | 0.1 | 0.16763
| Sub-total |  |  |  |  | 4.1176 | sqm | 814.0427 | 3351.9281
| VAT calculation | [7 empty] | 196.4001
13 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_ | [9 empty] | 13
| -slab cover | 1 | 9.7531 | 0.7 | 0.1 | 0.68272 |  |  |  |  | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
|  | 1 | 0.9 | 0.83816 | 0.1 | 0.075434
| -at entrance | 1 | 1.95 | 1 | 0.1 | 0.195
| Sub-total |  |  |  |  | 0.95315 | cum | 13568.9 | 12933.2378
| VAT calculation | [7 empty] | 1180.1426
14 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (Kg)
| -MS Flats 20mm*5mm | 6 | 0.17779 | 0.8 | 0.8534 | 0.8534
|  | 2 | 7.2 | 0.8 | 11.52 | 11.52
| -MS flats for fencing | 482 | 0.15 | 0.8 | 57.84 | 57.84
| -MS square pipe of 2"*2" of 1.8mm thickness for vertical post | 4 | 2.2859 | 2.72 | 24.8705 | 24.8705
| -MS square pipe 1.5"*1.5" of 1.6mm thickness for horizontal member | 1 | 7.2 | 3.87 | 27.864 | 27.864
|  | 4 | 2.5398 | 3.87 | 39.3157 | 39.3157
| -35*35*3mm Equal angles at windows | 1 | 7.2 | 1.52 | 10.944 | 10.944
| -equal angles for fencing | 2 | 48.2 | 1.52 | 146.528 | 146.528
| -MS square rod12mm *12mm size | 482 | 0.76196 | 1.13 | 415.0107 | 415.0107
| Sub-total |  |  |  |  | 734.7462 | Kg | 181.17 | 133113.9764
| VAT calculation | [7 empty] | 9437.8271
15 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 2 | 2.0691 |  | 1.6 | 6.6212
|  | 1 | 12.1 |  | 1.5167 | 18.3517
|  | 1 | 12.1 |  | 1.3 | 15.73
|  | 1 | 5.8 |  | 1.4 | 8.12
|  | 1 | 5.8 |  | 1.0972 | 6.3639
|  | 1 | 10.6 |  | 1.27 | 13.462
|  | 1 | 1.8287 |  | 0.91436 | 1.6721
|  | 1 | 1.5239 |  | 0.60957 | 0.92894
|  | 1 | 12.97 |  | 0.3 | 3.891
| -at one side drain | 1 | 6.55 |  | 0.23 | 1.5065
| -at roof | 1 | 18 |  | 0.71106 | 12.7991
| sub-total |  |  |  |  | 89.4465 | sqm | 405.86 | 36302.7596
| -VAT 13% for materials | [7 empty] | 1298.4109
16 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -as of plaster excluding drain | 1 |  |  |  | 87.94
| Sub-total |  |  |  |  | 87.94 | sqm | 251.77 | 22140.6557
| VAT calculation | [7 empty] | 1456.0051
17 | dfn;fdfg pknAw u/L UPVC sheet with PMMA Coating and mesh (Regular)5fgf 5fpg] sfd .
| -roof | 1 | 7.2 | 2.6922 |  | 19.3836
| Sub-total |  |  |  |  | 19.3836 | sqm | 2271.55 | 44030.8224
| VAT calculation | [7 empty] | 5094.6698
18 | sfk]{6 b'jf] |  |  |  | Area (m2)
| -for open spaces | 1 |  |  | 4.494 | 4.494
|  | 1 |  |  | 20.8359 | 20.8359
|  | 1 | 4.25 | 2.6 |  | 11.05
|  | 1 | 7 | 1.1048 |  | 7.7339 |  |  |  |  | ;km]{;nfO{ 8«]l;Ë ug]{ sfo{ vfN6f] k'g]{, p7]sf] df6f] sf6\g], ;tx ldnfpg]
|  | 1 | 6.55 | 2.6166 |  | 17.1386 |  |  |  |  | cflb sfo{ ;d]t -;le{;/f]8 cflb_
| Sub-total |  |  |  |  | 61.2525 | m2 | 376.7365 | 23076.0561
| VAT calculation | [7 empty] | 2999.8873
19 | ;km]{;nfO{ 8«]l;Ë ug]{ sfo{ vfN6f] k'g]{, p7]sf] df6f] sf6\g], ;tx ldnfpg] cflb sfo{ ;d]t -;le{;/f]8 cflb_
| -as of item no. 15 |  |  |  |  | 61.2525
| -at entrance | 1 | 1.95 | 1 |  | 1.95
| Sub-total |  |  |  |  | 63.2025 | m2 | 9.2 | 581.4631
20 | Provisional sum for unforeseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
21 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 487209.3531
| Total Estimated | 487209.3531 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 97.494
| User Contribution | 12209.3531 |  | 2.506
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2

## upvc (2)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- परोपकार भवन मर्मत | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/29
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | df6f]df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdu¦L !) dL=;Dd
| -existing wall | 1 | 18 | 0.1 | 0.71106 | 1.2799 |  |  |  |  | 7.6
| Sub-total |  |  |  |  | 1.2799 | cum | 975.2 | 1248.1728
2 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -at roof | 1 | 18 | 0.23 | 0.71106 | 2.9438 |  |  |  |  | 7.6
| -at drain | 1 | 6.55 | 0.23 | 0.3 | 0.45195
| Sub-total |  |  |  |  | 3.3958 | cum | 14362.76 | 48772.3957
| VAT calculation | [7 empty] | 4552.0968
3 | dfn;fdfg pknAw u/L lh=cfO{=k¦m]ddf ;fwf/0f d]6fnfOH8 kf]lnP6/ nfldg]6]8 jf]8{sf] l;lnË nufpg] sfd -ss{t kftfsf] 5fgfd'lg_
| -false ceiling | 1 | 7.615 | 3.49 |  | 26.5764 |  |  |  |  | 7.6
|  | 1 | 5.74 | 2.33 |  | 13.3742 |  |  |  |  | 5.73
|  | 1 | 5.7 | 2.3 |  | 13.11
| Sub-total |  |  |  |  | 53.0605 | sqm | 817.76 | 43390.7954
| VAT calculation | [7 empty] | 5640.8034
4 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -at roof | 1 | 13.93 | 6.55 |  | 91.2415 |  |  |  |  | 7.6
| -deduction | -1 | 7.2 | 2.6922 |  | -19.3836
| Sub-total |  |  |  |  | 71.8579 | sqm | 1070.9 | 76952.6224
| VAT calculation | [7 empty] | 8022.1575
5 | )=%) dL=dL= Kn]g zL6sf] !%) ld=ld= rf}8fO{, u6/ agfO{ jf;/
| -at roof | 1 | 13.4 |  |  | 13.4 |  |  |  |  | 7.6
| Sub-total |  |  |  |  | 13.4 | rm | 1108.01 | 14847.334
| VAT calculation | [7 empty] | 1232.7106
6 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -at drain wall | 2 | 9.7531 | 0.15 | 0.6 | 1.7556 |  |  |  |  | 7.6
| Sub-total |  |  |  |  | 1.7556 | cum | 1950.4 | 3424.0488
| VAT calculation | [7 empty] | 445.1263
7 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at drain wall base | 1 | 9.7531 | 0.4 | 0.125 | 0.48766
| Sub-total |  |  |  |  | 0.48766 | cum | 663.31 | 323.4672
8 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -at drain wall base | 1 | 9.7531 | 0.7 |  | 6.8272
| -at one side drain | 1 | 6.55 | 0.23 |  | 1.5065
| -at entrance | 1 | 1.95 | 1 |  | 1.95
| Sub-total |  |  |  |  | 10.2837 | sqm | 1014.97 | 10437.6336
| VAT calculation | [7 empty] | 1152.0156
9 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -at drain wall base | 1 | 9.7531 | 0.7 | 0.1 | 0.68272
| -at one side drain | 1 | 6.55 | 0.53 | 0.075 | 0.26036
| -at roof | 1 | 18 | 0.23 | 0.05 | 0.207
| Sub-total |  |  |  |  | 1.1501 | cum | 12983.1 | 14931.619
| VAT calculation | [7 empty] | 1207.7627
10 | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4) #) dL= ;Dd 9'jfgL ;d]t | [9 empty] | हयाबिटेक ईन्टरलक ब्रिकको गारो सिमेन्ट , बालुवा, र स्टोन डष्ट ( 1 2 4)
| -at drain wall | 2 | 9.7531 | 0.15 | 0.6 | 1.7556 |  |  |  |  | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| Sub-total |  |  |  |  | 1.7556 | cum | 8569.3 | 15043.9403
| VAT calculation | [7 empty] | 139.5787
13
11 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For slab cover | 5 | 0.75 | 0.39506 | 1.4815 | 0.0014815
|  | 65 | 0.7 | 0.39506 | 17.9753 | 0.017975
|  | 5 | 0.9 | 0.39506 | 1.7778 | 0.0017778
|  | 6 | 0.83816 | 0.39506 | 1.9867 | 0.0019867
| Sub-total |  |  |  |  | 0.023221 | MT | 131940 | 3063.8204
| VAT calculation | [7 empty] | 320.5935
12 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -at slab cover | 26 | 0.75 |  | 0.1 | 1.95 |  |  |  |  | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
|  | 26 | 0.7 |  | 0.1 | 1.82
|  | 2 | 0.9 |  | 0.1 | 0.18
|  | 2 | 0.83816 |  | 0.1 | 0.16763
| Sub-total |  |  |  |  | 4.1176 | sqm | 814.0427 | 3351.9281
| VAT calculation | [7 empty] | 196.4001
13 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_ | [9 empty] | 13
| -slab cover | 1 | 9.7531 | 0.7 | 0.1 | 0.68272 |  |  |  |  | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
|  | 1 | 0.9 | 0.83816 | 0.1 | 0.075434
| -at entrance | 1 | 1.95 | 1 | 0.1 | 0.195
| Sub-total |  |  |  |  | 0.95315 | cum | 13568.9 | 12933.2378
| VAT calculation | [7 empty] | 1180.1426
14 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (Kg)
| -MS Flats 20mm*5mm | 6 | 0.17779 | 0.8 | 0.8534 | 0.8534
|  | 2 | 7.2 | 0.8 | 11.52 | 11.52
| -MS flats for fencing | 482 | 0.15 | 0.8 | 57.84 | 57.84
| -MS square pipe of 2"*2" of 1.8mm thickness for vertical post | 4 | 2.2859 | 2.72 | 24.8705 | 24.8705
| -MS square pipe 1.5"*1.5" of 1.6mm thickness for horizontal member | 1 | 7.2 | 3.87 | 27.864 | 27.864
|  | 4 | 2.5398 | 3.87 | 39.3157 | 39.3157
| -35*35*3mm Equal angles at windows | 1 | 7.2 | 1.52 | 10.944 | 10.944
| -equal angles for fencing | 2 | 48.2 | 1.52 | 146.528 | 146.528
| -MS square rod12mm *12mm size | 482 | 0.76196 | 1.13 | 415.0107 | 415.0107
| Sub-total |  |  |  |  | 734.7462 | Kg | 181.17 | 133113.9764
| VAT calculation | [7 empty] | 9437.8271
15 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 2 | 2.0691 |  | 1.6 | 6.6212
|  | 1 | 12.1 |  | 1.5167 | 18.3517
|  | 1 | 12.1 |  | 1.3 | 15.73
|  | 1 | 5.8 |  | 1.4 | 8.12
|  | 1 | 5.8 |  | 1.0972 | 6.3639
|  | 1 | 10.6 |  | 1.27 | 13.462
|  | 1 | 1.8287 |  | 0.91436 | 1.6721
|  | 1 | 1.5239 |  | 0.60957 | 0.92894
|  | 1 | 12.97 |  | 0.3 | 3.891
| -at one side drain | 1 | 6.55 |  | 0.23 | 1.5065
| -at roof | 1 | 18 |  | 0.71106 | 12.7991
| sub-total |  |  |  |  | 89.4465 | sqm | 405.86 | 36302.7596
| -VAT 13% for materials | [7 empty] | 1298.4109
16 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -as of plaster excluding drain | 1 |  |  |  | 87.94
| Sub-total |  |  |  |  | 87.94 | sqm | 251.77 | 22140.6557
| VAT calculation | [7 empty] | 1456.0051
17 | dfn;fdfg pknAw u/L UPVC sheet with PMMA Coating and mesh (Regular)5fgf 5fpg] sfd .
| -roof | 1 | 7.2 | 2.6922 |  | 19.3836
| Sub-total |  |  |  |  | 19.3836 | sqm | 2271.55 | 44030.8224
| VAT calculation | [7 empty] | 5094.6698
18 | sfk]{6 b'jf] |  |  |  | Area (m2)
| -for open spaces | 1 |  |  | 4.494 | 4.494
|  | 1 |  |  | 20.8359 | 20.8359
|  | 1 | 4.25 | 2.6 |  | 11.05
|  | 1 | 7 | 1.1048 |  | 7.7339 |  |  |  |  | ;km]{;nfO{ 8«]l;Ë ug]{ sfo{ vfN6f] k'g]{, p7]sf] df6f] sf6\g], ;tx ldnfpg]
|  | 1 | 6.55 | 2.6166 |  | 17.1386 |  |  |  |  | cflb sfo{ ;d]t -;le{;/f]8 cflb_
| Sub-total |  |  |  |  | 61.2525 | m2 | 376.7365 | 23076.0561
| VAT calculation | [7 empty] | 2999.8873
19 | ;km]{;nfO{ 8«]l;Ë ug]{ sfo{ vfN6f] k'g]{, p7]sf] df6f] sf6\g], ;tx ldnfpg] cflb sfo{ ;d]t -;le{;/f]8 cflb_
| -as of item no. 15 |  |  |  |  | 61.2525
| -at entrance | 1 | 1.95 | 1 |  | 1.95
| Sub-total |  |  |  |  | 63.2025 | m2 | 9.2 | 581.4631
20 | Provisional sum for unforeseen works | 1 |  |  |  | 1 | PS | 6000 | 6000
21 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 559342.9367
| Total Estimated | 559342.9367 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 84.9211
| User Contribution | 84342.9367 |  | 15.0789
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2