## estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- लकिल्ला गणेश मन्दिर | [6 empty] | F.Y.: 2081/82
Location:- Shankharapur Municipality 9 | [6 empty] | Date: 2081/12/14
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Traditional Brick (Small Dachhi Appa) size 210*55*97 mm work in (1:1:2) lime, surkhi, sand mortar
-1st floor
| -outer face wall | 2 | 2.97 |  | 1.81 | 10.7514
|  | 2 | 2.97 |  | 1.81 | 10.7514
| -deduction for base for placement of things | 0 | 0.53337 |  | 0.75 | 0
| -Deduction for window | -2 | 0.7 |  | 0.7 | -0.98
| -Deduction for door | -1 | 1.55 |  | 2.4383 | -3.7793
| -base for placement of things | 0 | 2.08 |  | 0.15 | 0
-2nd floor
| -Wall | 4 | 1.9303 |  | 0.50798 | 3.9222
| -deduction for tika jhyal | -4 | 0.26669 |  | 0.30479 | -0.32513
|  | -4 | 0.66037 |  | 0.12699 | -0.33545
|  | -4 | 0.60957 |  | 0.076196 | -0.18579
| Sub-total |  |  |  |  | 19.8193 | sqm | 5357.6609 | 106185.019
| -VAT 13% for materials only | [7 empty] | 8761.5621
2 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -inner wall | 2 | 2.07 | 0.1 | 2.4383 | 1.0094
|  | 2 | 2.07 | 0.1 | 2.4383 | 1.0094
| -deduction for window | -2 | 0.7 | 0.1 | 0.7 | -0.098
| -deduction for door | -1 | 1.2 | 0.1 | 2.4383 | -0.29259
| -base for placement of things | 0 | 2.08 | 0.1 | 0.15 | 0
|  | 0 | 0.53337 | 0.1 | 0.75 | 0
| -2nd floor | 1 | 1.8541 | 0.1 | 0.1 | 0.018541
| Sub-total |  |  |  |  | 1.6468 | cum | 14362.76 | 23653.2259
| -VAT 13% for materials only | [7 empty] | 2207.6376
3 | Traditional Nago Brick work in (1:1:2) lime, surkhi, sand mortar
| -wall | 1 | 12.24 |  |  | 12.24
| Sub-total |  |  |  |  | 12.24 | m | 404.8957 | 4955.9228
| -VAT 13% for materials only | [7 empty] | 442.4507
4 | Traditional Kassimo Brick work in (1:1:2) lime, surkhi, sand mortar
| -wall | 1 | 12.24 |  |  | 12.24
| Sub-total |  |  |  |  | 12.24 | m | 345.0957 | 4223.9708
| -VAT 13% for materials only | [7 empty] | 347.2969
5 | Traditional Nagbeli Brick work in (1:1:2) lime, surkhi, sand mortar
| -wall | 1 | 10.61 |  |  | 10.61
| Sub-total |  |  |  |  | 10.61 | m | 388.8957 | 4126.1829
| -VAT 13% for materials only | [7 empty] | 361.4607
6 | Traditional Tinkune pali Brick work in (1:1:2) lime, surkhi, sand mortar
| -wall | 2 | 11.3904 |  |  | 22.7809
| Sub-total |  |  |  |  | 22.7809 | m | 353.6957 | 8057.491
| -VAT 13% for materials only | [7 empty] | 671.8515
7 | Traditional Sinkhwo 2" with astamangal or full butta Brick work in (1:1:2) lime, surkhi, sand mortar
| -wall | 1 | 10.81 |  |  | 10.81
| -2nd floor | 4 | 2.0319 |  |  | 8.1276
| Sub-total |  |  |  |  | 18.9376 | m | 516.3913 | 9779.2137
| -VAT 13% for materials only | [7 empty] | 959.0557
8 | Traditional Fya Brick work in (1:1:2) lime, surkhi, sand mortar
| -wall | 4 | 2.0573 |  |  | 8.2292
| Sub-total |  |  |  |  | 8.2292 | m | 404.8957 | 3331.9667
| -VAT 13% for materials only | [7 empty] | 297.4685
9 | Sal timber work for chaukhat frame (upto 8'-0")
| -For Door | 1 | 5.3148 | 0.1 | 0.1 | 0.053148
| -For window | 4 | 0.55 | 0.1016 | 0.1016 | 0.022707 |  |  |  |  | 442.3913
|  | 2 | 0.91436 | 0.076196 | 0.1016 | 0.014156 |  |  |  |  | 134.8783 | 741.8304
|  | 2 | 0.91436 | 0.12699 | 0.076196 | 0.017695
| -2nd floor window | 4 | 0.60957 | 0.1016 | 0.076196 | 0.018875
|  | 4 | 0.58417 | 0.076196 | 0.1016 | 0.018089
|  | 8 | 0.45718 | 0.1016 | 0.076196 | 0.028313
| Sub-total |  |  |  |  | 0.17298 | cum | 307586.0696 | 53207.3871
| -VAT 13% for materials only | [7 empty] | 5909.9978
10 | Sal timber work for joist beam, column, etc. (upto 8'-0")
| -mikha fushi | 1 | 1.6763 | 0.15 | 0.076196 | 0.019159
| -Pali butta | 1 | 5.3652 | 0.025399 | 0.025399 | 0.0034611
| -thaam | 2 | 2.1335 | 0.15 | 0.038098 | 0.024385 |  |  |  |  | 5893.159
|  | 2 | 2.1335 | 0.076196 | 0.076196 | 0.024774
| -for window | 2 | 0.96 | 0.025399 | 0.12699 | 0.0061929
|  | 2 | 0.91436 | 0.025399 | 0.1016 | 0.0047188
|  | 2 | 0.83 | 0.025399 | 0.076196 | 0.0032126
| -tika jhyal | 4 | 0.66037 | 0.025399 | 0.1016 | 0.006816
|  | 4 | 0.71117 | 0.12 | 0.025399 | 0.0086701
| -twaka | 4 | 0.30479 | 0.1016 | 0.076196 | 0.0094376
|  | 8 | 0.25399 | 0.1016 | 0.076196 | 0.015729
|  | 2 | 0.23 | 0.15 | 0.038098 | 0.0026288
| Sub-total |  |  |  |  | 0.12918 | cum | 249128.2174 | 32183.5727
| -VAT 13% for materials only | [7 empty] | 4183.8645
13 | #* dL=dL= afSnf] lr/fg cu¦fv sf7sf] k¦m]d xfnL l8nfvfkf agfO
| -door | 2 | 1.0667 |  | 2.0319 | 4.3351
| Sub-total |  |  |  |  | 4.3351 | sqm | 15859.11 | 68750.0679
| -VAT 13% for materials only | [7 empty] | 5426.6145
11 | Carved Door works excluding wood
| -door | 1 | 1.2 |  | 2.1335 | 2.5602
| Sub-total |  |  |  |  | 2.5602 | sqm | 40498.2609 | 103683.4475
12 | Window carving (except lattice jali) excluding wood
| -window | 4 |  | 0.12699 | 0.55 | 0.27939
|  | 2 | 0.91436 |  | 0.076196 | 0.13934
|  | 2 | 0.91436 |  | 0.076196 | 0.13934
|  | 2 | 0.96 |  | 0.025399 | 0.048766
|  | 2 | 0.91436 |  | 0.025399 | 0.046447
|  | 2 | 0.83 |  | 0.025399 | 0.042162
| -2nd floor window | 4 | 0.60957 |  | 0.076196 | 0.18579
|  | 8 | 0.30479 |  | 0.076196 | 0.18579
|  | 4 | 0.58417 |  | 0.076196 | 0.17805
|  | 4 | 7.9244 |  | 0.025399 | 0.80508
|  | 4 | 0.71117 |  | 0.025399 | 0.072251
| Sub-total |  |  |  |  | 2.1224 | sqm | 44198.6435 | 93807.0896
13 | Carved salwood Lattice (jali) of Carved Window highly carving including wood
| -tika jhyal | 4 | 0.25399 |  | 0.30479 | 0.30965
| Sub-total |  |  |  |  | 0.30965 | sqm | 60504.2783 | 18734.9427
| -VAT 13% for materials only | [7 empty] | 432.6847
14 | Provisional sum for fittings works & other unforseen works/items | 0 |  |  |  | 0 | PS | 20000 | 0
15 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 565181.4453
| Total Estimated | 565181.4453 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 84.0438
| User Contribution | 90181.4453 |  | 15.9562
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 565181.4453 |  |  |  |  | Total Valuated Amount : |  | 565181.4453
Work Started : | [7 empty] | Work Finished:
#REF! | [7 empty] | F.Y:2079/80
#REF! | [7 empty] | Date:2079/ /
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Traditional Brick (Small Dachhi Appa) size 210*55*97 mm work in (1:1:2) lime, surkhi, sand mortar | sqm | 19.8193 | 5357.6609 | 106185.019 | 19.8193 | 5357.6609 | 106185.019 | 0
| -VAT 13% for materials only |  |  |  | 8761.5621 |  |  | 8761.5621 | 0
2 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | cum | 1.6468 | 14362.76 | 23653.2259 | 1.6468 | 14362.76 | 23653.2259 | 0
| -VAT 13% for materials only |  |  |  | 2207.6376 |  |  | 2207.6376 | 0
3 | Traditional Nago Brick work in (1:1:2) lime, surkhi, sand mortar | m | 12.24 | 404.8957 | 4955.9228 | 12.24 | 404.8957 | 4955.9228 | 0
| -VAT 13% for materials only |  |  |  | 442.4507 |  |  | 442.4507 | 0
4 | Traditional Kassimo Brick work in (1:1:2) lime, surkhi, sand mortar | m | 12.24 | 345.0957 | 4223.9708 | 12.24 | 345.0957 | 4223.9708 | 0
| -VAT 13% for materials only |  |  |  | 347.2969 |  |  | 347.2969 | 0
5 | Traditional Nagbeli Brick work in (1:1:2) lime, surkhi, sand mortar | m | 10.61 | 388.8957 | 4126.1829 | 10.61 | 388.8957 | 4126.1829 | 0
| -VAT 13% for materials only |  |  |  | 361.4607 |  |  | 361.4607 | 0
6 | Traditional Tinkune pali Brick work in (1:1:2) lime, surkhi, sand mortar | m | 22.7809 | 353.6957 | 8057.491 | 22.7809 | 353.6957 | 8057.491 | 0
| -VAT 13% for materials only |  |  |  | 671.8515 |  |  | 671.8515 | 0
7 | Traditional Sinkhwo 2" with astamangal or full butta Brick work in (1:1:2) lime, surkhi, sand mortar | m | 18.9376 | 516.3913 | 9779.2137 | 18.9376 | 516.3913 | 9779.2137 | 0
| -VAT 13% for materials only |  |  |  | 959.0557 |  |  | 959.0557 | 0
8 | Traditional Fya Brick work in (1:1:2) lime, surkhi, sand mortar | m | 8.2292 | 404.8957 | 3331.9667 | 8.2292 | 404.8957 | 3331.9667 | 0
| -VAT 13% for materials only |  |  |  | 297.4685 |  |  | 297.4685 | 0
9 | Sal timber work for chaukhat frame (upto 8'-0") | cum | 0.17298 | 307586.0696 | 53207.3871 | 0.17298 | 307586.0696 | 53207.3871 | 0
| -VAT 13% for materials only |  |  |  | 5909.9978 |  |  | 5909.9978 | 0
10 | Sal timber work for joist beam, column, etc. (upto 8'-0") | cum | 0.12918 | 249128.2174 | 32183.5727 | 0.12918 | 249128.2174 | 32183.5727 | 0
| -VAT 13% for materials only |  |  |  | 4183.8645 |  |  | 4183.8645 | 0
13 | #* dL=dL= afSnf] lr/fg cu¦fv sf7sf] k¦m]d xfnL l8nfvfkf agfO | sqm | 4.3351 | 15859.11 | 68750.0679 | 4.3351 | 15859.11 | 68750.0679 | 0
| -VAT 13% for materials only |  |  |  | 5426.6145 |  |  | 5426.6145 | 0
11 | Carved Door works excluding wood | sqm | 2.5602 | 40498.2609 | 103683.4475 | 2.5602 | 40498.2609 | 103683.4475 | 0
12 | Window carving (except lattice jali) excluding wood | sqm | 2.1224 | 44198.6435 | 93807.0896 | 2.1224 | 44198.6435 | 93807.0896 | 0
13 | Carved salwood Lattice (jali) of Carved Window highly carving including wood | sqm | 0.30965 | 60504.2783 | 18734.9427 | 0.30965 | 60504.2783 | 18734.9427 | 0
| -VAT 13% for materials only |  |  |  | 432.6847 |  |  | 432.6847 | 0
14 | Provisional sum for fittings works & other unforseen works/items | PS | 0 | 20000 | 0 | 0 | 20000 | 0 | 0
15 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0
| Total |  |  |  | 565181.4453 |  |  | 565181.4453 | 0

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- लकिल्ला गणेश मन्दिर | [6 empty] | F.Y.: 2081/82
Location:- Shankharapur Municipality 9 | [6 empty] | Date: 2081/12/14
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Traditional Brick (Small Dachhi Appa) size 210*55*97 mm work in (1:1:2) lime, surkhi, sand mortar
-1st floor
| -outer face wall | 2 | 2.97 |  | 1.81 | 10.7514
|  | 2 | 2.97 |  | 1.81 | 10.7514
| -deduction for base for placement of things | 0 | 0.53337 |  | 0.75 | 0
| -Deduction for window | -2 | 0.7 |  | 0.7 | -0.98
| -Deduction for door | -1 | 1.55 |  | 2.4383 | -3.7793
| -base for placement of things | 0 | 2.08 |  | 0.15 | 0
-2nd floor
| -Wall | 4 | 1.9303 |  | 0.50798 | 3.9222
| -deduction for tika jhyal | -4 | 0.26669 |  | 0.30479 | -0.32513
|  | -4 | 0.66037 |  | 0.12699 | -0.33545
|  | -4 | 0.60957 |  | 0.076196 | -0.18579
| Sub-total |  |  |  |  | 19.8193 | sqm | 5357.6609 | 106185.019
| -VAT 13% for materials only | [7 empty] | 8761.5621
2 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -inner wall | 2 | 2.07 | 0.1 | 2.4383 | 1.0094
|  | 2 | 2.07 | 0.1 | 2.4383 | 1.0094
| -deduction for window | -2 | 0.7 | 0.1 | 0.7 | -0.098
| -deduction for door | -1 | 1.2 | 0.1 | 2.4383 | -0.29259
| -base for placement of things | 0 | 2.08 | 0.1 | 0.15 | 0
|  | 0 | 0.53337 | 0.1 | 0.75 | 0
| -2nd floor | 1 | 1.8541 | 0.1 | 0.1 | 0.018541
| Sub-total |  |  |  |  | 1.6468 | cum | 14362.76 | 23653.2259
| -VAT 13% for materials only | [7 empty] | 2207.6376
3 | Traditional Nago Brick work in (1:1:2) lime, surkhi, sand mortar
| -wall | 1 | 12.24 |  |  | 12.24
| Sub-total |  |  |  |  | 12.24 | m | 404.8957 | 4955.9228
| -VAT 13% for materials only | [7 empty] | 442.4507
4 | Traditional Kassimo Brick work in (1:1:2) lime, surkhi, sand mortar
| -wall | 1 | 12.24 |  |  | 12.24
| Sub-total |  |  |  |  | 12.24 | m | 345.0957 | 4223.9708
| -VAT 13% for materials only | [7 empty] | 347.2969
5 | Traditional Nagbeli Brick work in (1:1:2) lime, surkhi, sand mortar
| -wall | 1 | 10.61 |  |  | 10.61
| Sub-total |  |  |  |  | 10.61 | m | 388.8957 | 4126.1829
| -VAT 13% for materials only | [7 empty] | 361.4607
6 | Traditional Tinkune pali Brick work in (1:1:2) lime, surkhi, sand mortar
| -wall | 2 | 11.3904 |  |  | 22.7809
| Sub-total |  |  |  |  | 22.7809 | m | 353.6957 | 8057.491
| -VAT 13% for materials only | [7 empty] | 671.8515
7 | Traditional Sinkhwo 2" with astamangal or full butta Brick work in (1:1:2) lime, surkhi, sand mortar
| -wall | 1 | 10.81 |  |  | 10.81
| -2nd floor | 4 | 2.0319 |  |  | 8.1276
| Sub-total |  |  |  |  | 18.9376 | m | 516.3913 | 9779.2137
| -VAT 13% for materials only | [7 empty] | 959.0557
8 | Traditional Fya Brick work in (1:1:2) lime, surkhi, sand mortar
| -wall | 4 | 2.0573 |  |  | 8.2292
| Sub-total |  |  |  |  | 8.2292 | m | 404.8957 | 3331.9667
| -VAT 13% for materials only | [7 empty] | 297.4685
9 | Sal timber work for chaukhat frame (upto 8'-0")
| -For Door | 1 | 5.3148 | 0.1 | 0.1 | 0.053148
| -For window | 4 | 0.55 | 0.1016 | 0.1016 | 0.022707 |  |  |  |  | 442.3913
|  | 2 | 0.91436 | 0.076196 | 0.1016 | 0.014156 |  |  |  |  | 134.8783 | 741.8304
|  | 2 | 0.91436 | 0.12699 | 0.076196 | 0.017695
| -2nd floor window | 4 | 0.60957 | 0.1016 | 0.076196 | 0.018875
|  | 4 | 0.58417 | 0.076196 | 0.1016 | 0.018089
|  | 8 | 0.45718 | 0.1016 | 0.076196 | 0.028313
| Sub-total |  |  |  |  | 0.17298 | cum | 307586.0696 | 53207.3871
| -VAT 13% for materials only | [7 empty] | 5909.9978
10 | Sal timber work for joist beam, column, etc. (upto 8'-0")
| -mikha fushi | 1 | 1.6763 | 0.15 | 0.076196 | 0.019159
| -Pali butta | 1 | 5.3652 | 0.025399 | 0.025399 | 0.0034611
| -thaam | 2 | 2.1335 | 0.15 | 0.038098 | 0.024385 |  |  |  |  | 5893.159
|  | 2 | 2.1335 | 0.076196 | 0.076196 | 0.024774
| -for window | 2 | 0.96 | 0.025399 | 0.12699 | 0.0061929
|  | 2 | 0.91436 | 0.025399 | 0.1016 | 0.0047188
|  | 2 | 0.83 | 0.025399 | 0.076196 | 0.0032126
| -tika jhyal | 4 | 0.66037 | 0.025399 | 0.1016 | 0.006816
|  | 4 | 0.71117 | 0.12 | 0.025399 | 0.0086701
| -twaka | 4 | 0.30479 | 0.1016 | 0.076196 | 0.0094376
|  | 8 | 0.25399 | 0.1016 | 0.076196 | 0.015729
|  | 2 | 0.23 | 0.15 | 0.038098 | 0.0026288
| Sub-total |  |  |  |  | 0.12918 | cum | 249128.2174 | 32183.5727
| -VAT 13% for materials only | [7 empty] | 4183.8645
13 | #* dL=dL= afSnf] lr/fg cu¦fv sf7sf] k¦m]d xfnL l8nfvfkf agfO
| -door | 2 | 1.0667 |  | 2.0319 | 4.3351
| Sub-total |  |  |  |  | 4.3351 | sqm | 15859.11 | 68750.0679
| -VAT 13% for materials only | [7 empty] | 5426.6145
11 | Carved Door works excluding wood
| -door | 1 | 1.2 |  | 2.1335 | 2.5602
| Sub-total |  |  |  |  | 2.5602 | sqm | 40498.2609 | 103683.4475
12 | Window carving (except lattice jali) excluding wood
| -window | 4 |  | 0.12699 | 0.55 | 0.27939
|  | 2 | 0.91436 |  | 0.076196 | 0.13934
|  | 2 | 0.91436 |  | 0.076196 | 0.13934
|  | 2 | 0.96 |  | 0.025399 | 0.048766
|  | 2 | 0.91436 |  | 0.025399 | 0.046447
|  | 2 | 0.83 |  | 0.025399 | 0.042162
| -2nd floor window | 4 | 0.60957 |  | 0.076196 | 0.18579
|  | 8 | 0.30479 |  | 0.076196 | 0.18579
|  | 4 | 0.58417 |  | 0.076196 | 0.17805
|  | 4 | 7.9244 |  | 0.025399 | 0.80508
|  | 4 | 0.71117 |  | 0.025399 | 0.072251
| Sub-total |  |  |  |  | 2.1224 | sqm | 44198.6435 | 93807.0896
13 | Carved salwood Lattice (jali) of Carved Window highly carving including wood
| -tika jhyal | 4 | 0.25399 |  | 0.30479 | 0.30965
| Sub-total |  |  |  |  | 0.30965 | sqm | 60504.2783 | 18734.9427
| -VAT 13% for materials only | [7 empty] | 432.6847
14 | Provisional sum for fittings works & other unforseen works/items | 0 |  |  |  | 0 | PS | 20000 | 0
15 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Total | [7 empty] | 565181.4453
| Total Estimated | 565181.4453 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 84.0438
| User Contribution | 90181.4453 |  | 15.9562
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2