## re-estimate (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- बेनडोल सडक नयाँबस्ती | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/07/11
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -White wall | 1 | 3.88 | 0.1 | 2.2859 | 0.88692
|  | 3 | 0.3566 | 0.3566 | 2.2859 | 0.87204 |  |  |  |  | kmnfd] sfd -Rofgn PËn 6L cflb_ x6fpg] sfo{ lemSg], 5'6\ofpg] / /fd¦/L yGsfpg] ;d]t
|  | 1 | 0.6 | 0.6 | 1.15 | 0.414
| Sub-total |  |  |  |  | 2.173 | m3 | 1950 | 4237.2778
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -White wall | 1 | 10.53 | 0.46 | 0.75 | 3.6329
| Sub-total |  |  |  |  | 3.6329 | m3 | 64.63 | 234.7911
| VAT calculation | [7 empty] | 25.298
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at backyard | 1 | 0.6 | 0.6 | 0.9 | 0.324
| Sub-total |  |  |  |  | 0.324 | m3 | 663.31 | 214.9124
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing | 1 | 10.53 | 0.46 |  | 4.8438
|  | 1 | 0.6 | 0.6 |  | 0.36
| Sub-total |  |  |  |  | 5.2038 | sqm | 1014.97 | 5281.7009
| VAT calculation | [7 empty] | 582.9484
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for footing | 1 | 10.53 | 0.46 | 0.05 | 0.24219
|  | 1 | 0.6 | 0.6 | 0.05 | 0.018
| Sub-total |  |  |  |  | 0.26019 | m3 | 12983.1 | 3378.0728
| VAT calculation | [7 empty] | 273.2396
6 | ;'k/ :6«Sr/, 8]s :n]a ljdx?df l;d]G6 s+lqm6 ug]{ sfd -!M!.%M#_
| -for footing | 1 | 0.6 | 0.6 | 0.225 | 0.081
|  | 1 | 0.23 | 0.23 | 2.475 | 0.13093
| -sill/lintel/DPC bands | 2 | 11.48 | 0.23 | 0.075 | 0.39606
|  | 2 | 9.4602 | 0.23 | 0.075 | 0.32638
| Sub-total |  |  |  |  | 0.93436 | m3 | 16512.62 | 15428.8067
| VAT calculation | [7 empty] | 1104.4568
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for footing | 1 | 2.4 |  | 0.225 | 0.54
|  | 1 | 0.92 |  | 2.475 | 2.277
| Sub-total |  |  |  |  | 2.817 | m2 | 915.42 | 2578.7381
| VAT calculation | [7 empty] | 171.4883
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For column footing | 6 | 0.6 | 0.39506 | 1.4222 | 0.0014222
| -For column | 4 | 3.075 | 0.88889 | 10.9333 | 0.010933
| -For column stirrups | 16 | 0.71117 | 0.39506 | 4.4953 | 0.0044953
| -For bands | 4 | 20.4402 | 0.61728 | 50.4696 | 0.05047
| -For stirrups | 135 | 0.27939 | 0.39506 | 14.9006 | 0.014901
| Sub-total |  |  |  |  | 0.082221 | MT | 131940 | 10848.2478
| VAT calculation | [7 empty] | 1135.1441
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | [10 empty] | 37.666
| -wall at backyard | 1 | 11.48 | 0.23 | 0.63487 | 1.6763 |  |  |  |  | 11.6324 | 11.48
|  | 1 | 0.406 | 0.23 | 2.5037 | 0.2338
| -deduction for sill/lintel/DPC bands | -2 | 11.48 | 0.23 | 0.075 | -0.39606
| - at instead white wall | 1 | 9.4602 | 0.23 | 2.35 | 5.1132 | [5 empty] | 2.9749 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -deduction for sill/lintel/DPC bands | -2 | 9.4602 | 0.23 | 0.075 | -0.32638
|  | 3 | 0.3566 | 0.3566 | 2.35 | 0.8965
| -for footing | 1 | 10.53 | 0.46 | 0.2 | 0.96876
| -at back yard window | 12 | 0.83816 | 0.23 | 1.2444 | 2.8788
| Sub-total |  |  |  |  | 11.0449 | m3 | 14362.76 | 158635.8406
| VAT calculation | [7 empty] | 14806.0331
10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 2 | 72.7696 |  | 1.8 | 261.9705
| Sub-total |  |  |  |  | 261.9705 | sqm | 405.86 | 106323.3458
| VAT calculation | [7 empty] | 3802.7794
11 | $=% X @) dL=dL= kmnfd] kftfsf] k¦m]ddf !@ x !@ dL=dL=;f]ln8 sf]/ :Sjfo/ /8sf] lu¦n agfO{ vfS;L nufO{ /]8cS;fO8 tyf cNd'lgod k]G6 ;d]t u/L hf]8\g]
| -window | 6 | 1.1938 |  | 1.6519 | 11.8329
| Sub-total |  |  |  |  | 11.8329 | sqm | 2575.34 | 30473.7725
| VAT calculation | [7 empty] | 3744.7793
12 | lh=cfO{=sf9]tf/ -jf/ j]8 jfo/_ nufpg] .
| -at boundary | 1 | 95.5523 |  |  | 95.5523
| Sub-total |  |  |  |  | 95.5523 | rm | 82.59 | 7891.662
| VAT calculation | [7 empty] | 247.4596
13 | %) dL=dL=Aof;sf] :6]Gn];l:6nsf] x\of08/]ndf @ ld6/sf] b"/Ldf %) dL=dL=Aof;sf] :6]Gn];l:6ns} 7f8f] kf]i6 /fvL x\of08/]n / e"O+sf] aLrdf tLg tx t];f]{ @% dL=dL=Aof;sf] :6]Gn];l:6nsf] d]Da/ /fvL @Ú–^Æ b]lv #Ú–)Æ ;Dd prfO{ ePsf] /]lnË pknAw u/fO{ h8fg u/L /+u ;d]t nufpg] sfd .
| -at boundary | 1 | 7.8735 |  |  | 7.8735
| Sub-total |  |  |  |  | 7.8735 | rm | 4132.8 | 32539.6594
| VAT calculation | [7 empty] | 4230.1557
14 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -wall | 2 | 72.7696 |  | 1.8 | 261.9705
| Sub-total |  |  |  |  | 261.9705 | sqm | 251.77 | 65956.312
| VAT calculation | [7 empty] | 4337.3931
15 | kmnfd] u]6 !^ u]h -%)X%)X% dL=dL=sf] k¦m]d ;lxt_ agfO{ hf]8\g] /]8 cS;fO8 k]lG6Ë / Hofnf ;d]t .
| -at door | 2 | 1.0158 |  | 2.5398 | 5.1601
| Sub-total |  |  |  |  | 5.1601 | sqm | 8306.71 | 42863.0706
| VAT 13% for material | [7 empty] | 5572.1992
16 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
17 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 532419.5853
| Total Estimated | 532419.5853 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 89.2154
| User Contribution | 57419.5853 |  | 10.7846
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on C11: Windows User: white wall
Note on C12: Windows User: column as wall support and including footing area
Note on D60: DELL: column part not included
Note on D61: DELL: For RCC column peripheri and ht =3 ft from GL and 225mm depth footing

## grill item changed (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- बेनडोल सडक नयाँबस्ती | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/07/11
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -White wall | 1 | 3.88 | 0.1 | 2.2859 | 0.88692
|  | 3 | 0.3566 | 0.3566 | 2.2859 | 0.87204 |  |  |  |  | kmnfd] sfd -Rofgn PËn 6L cflb_ x6fpg] sfo{ lemSg], 5'6\ofpg] / /fd¦/L yGsfpg] ;d]t
|  | 1 | 0.6 | 0.6 | 1.15 | 0.414
| Sub-total |  |  |  |  | 2.173 | m3 | 1950 | 4237.2778
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -White wall | 1 | 10.53 | 0.46 | 0.75 | 3.6329
| Sub-total |  |  |  |  | 3.6329 | m3 | 64.63 | 234.7911
| VAT calculation | [7 empty] | 25.298
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at backyard | 1 | 0.6 | 0.6 | 0.9 | 0.324
| Sub-total |  |  |  |  | 0.324 | m3 | 663.31 | 214.9124
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing | 1 | 10.53 | 0.46 |  | 4.8438
|  | 1 | 0.6 | 0.6 |  | 0.36
| Sub-total |  |  |  |  | 5.2038 | sqm | 1014.97 | 5281.7009
| VAT calculation | [7 empty] | 582.9484
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for footing | 1 | 10.53 | 0.46 | 0.05 | 0.24219
|  | 1 | 0.6 | 0.6 | 0.05 | 0.018
| Sub-total |  |  |  |  | 0.26019 | m3 | 12983.1 | 3378.0728
| VAT calculation | [7 empty] | 273.2396
6 | ;'k/ :6«Sr/, 8]s :n]a ljdx?df l;d]G6 s+lqm6 ug]{ sfd -!M!.%M#_
| -for footing | 1 | 0.6 | 0.6 | 0.225 | 0.081
|  | 1 | 0.23 | 0.23 | 2.475 | 0.13093
| -sill/lintel/DPC bands | 2 | 11.48 | 0.23 | 0.075 | 0.39606
|  | 2 | 9.4602 | 0.23 | 0.075 | 0.32638
| Sub-total |  |  |  |  | 0.93436 | m3 | 16512.62 | 15428.8067
| VAT calculation | [7 empty] | 1104.4568
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for footing | 1 | 2.4 |  | 0.225 | 0.54
|  | 1 | 0.92 |  | 2.475 | 2.277
| Sub-total |  |  |  |  | 2.817 | m2 | 915.42 | 2578.7381
| VAT calculation | [7 empty] | 171.4883
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For column footing | 6 | 0.6 | 0.39506 | 1.4222 | 0.0014222
| -For column | 4 | 3.075 | 0.88889 | 10.9333 | 0.010933
| -For column stirrups | 16 | 0.71117 | 0.39506 | 4.4953 | 0.0044953
| -For bands | 4 | 20.4402 | 0.61728 | 50.4696 | 0.05047
| -For stirrups | 135 | 0.27939 | 0.39506 | 14.9006 | 0.014901
| Sub-total |  |  |  |  | 0.082221 | MT | 131940 | 10848.2478
| VAT calculation | [7 empty] | 1135.1441
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | [10 empty] | 37.666
| -wall at backyard | 1 | 11.48 | 0.23 | 0.63487 | 1.6763 |  |  |  |  | 11.6324 | 11.48
|  | 1 | 0.406 | 0.23 | 2.5037 | 0.2338
| -deduction for sill/lintel/DPC bands | -2 | 11.48 | 0.23 | 0.075 | -0.39606
| - at instead white wall | 1 | 9.4602 | 0.23 | 2.35 | 5.1132 | [5 empty] | 2.9749 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -deduction for sill/lintel/DPC bands | -2 | 9.4602 | 0.23 | 0.075 | -0.32638
|  | 3 | 0.3566 | 0.3566 | 2.35 | 0.8965
| -for footing | 1 | 10.53 | 0.46 | 0.2 | 0.96876
| -at back yard window | 12 | 0.83816 | 0.23 | 1.2444 | 2.8788
| Sub-total |  |  |  |  | 11.0449 | m3 | 14362.76 | 158635.8406
| VAT calculation | [7 empty] | 14806.0331
10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 2 | 72.7696 |  | 1.8 | 261.9705
| Sub-total |  |  |  |  | 261.9705 | sqm | 405.86 | 106323.3458
| VAT calculation | [7 empty] | 3802.7794
11 | $=% X @) dL=dL= kmnfd] kftfsf] k¦m]ddf !@ x !@ dL=dL=;f]ln8 sf]/ :Sjfo/ /8sf] lu¦n agfO{ vfS;L nufO{ /]8cS;fO8 tyf cNd'lgod k]G6 ;d]t u/L hf]8\g]
| -window | 6 | 1.1938 |  | 1.6519 | 11.8329
| Sub-total |  |  |  |  | 11.8329 | sqm | 2575.34 | 30473.7725
| VAT calculation | [7 empty] | 3744.7793
12 | lh=cfO{=sf9]tf/ -jf/ j]8 jfo/_ nufpg] .
| -at boundary | 1 | 95.5523 |  |  | 95.5523
| Sub-total |  |  |  |  | 95.5523 | rm | 82.59 | 7891.662
| VAT calculation | [7 empty] | 247.4596
13 | %) dL=dL=Aof;sf] :6]Gn];l:6nsf] x\of08/]ndf @ ld6/sf] b"/Ldf %) dL=dL=Aof;sf] :6]Gn];l:6ns} 7f8f] kf]i6 /fvL x\of08/]n / e"O+sf] aLrdf tLg tx t];f]{ @% dL=dL=Aof;sf] :6]Gn];l:6nsf] d]Da/ /fvL @Ú–^Æ b]lv #Ú–)Æ ;Dd prfO{ ePsf] /]lnË pknAw u/fO{ h8fg u/L /+u ;d]t nufpg] sfd .
| -at boundary | 1 | 7.8735 |  |  | 7.8735
| Sub-total |  |  |  |  | 7.8735 | rm | 4132.8 | 32539.6594
| VAT calculation | [7 empty] | 4230.1557
14 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -wall | 2 | 72.7696 |  | 1.8 | 261.9705
| Sub-total |  |  |  |  | 261.9705 | sqm | 251.77 | 65956.312
| VAT calculation | [7 empty] | 4337.3931
15 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -MS Equal angle of 35mm*35mm*2mm For door | 4 | 8.1271 | 1.04 | 33.8087 | 33.8087
| -MS sheet 900mm wide or as per required and of 14G with 2mm | 4 | 2.4383 | 14.13 | 137.8116 | 137.8116
| Sub-total |  |  |  |  | 171.6204 | Kg | 181.17 | 31092.4606
| VAT calculation | [7 empty] | 2204.4662
16 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
17 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 517281.2423
| Total Estimated | 517281.2423 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 91.8263
| User Contribution | 42281.2423 |  | 8.1737
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on C11: Windows User: white wall
Note on C12: Windows User: column as wall support and including footing area
Note on D60: DELL: column part not included
Note on D61: DELL: For RCC column peripheri and ht =3 ft from GL and 225mm depth footing

## callapsible gate added
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- राष्ट्रिय मा. बि. वाल निर्माण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/21
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -White wall | 1 | 3.88 | 0.1 | 2.2859 | 0.88692
|  | 3 | 0.3566 | 0.3566 | 2.2859 | 0.87204 |  |  |  |  | kmnfd] sfd -Rofgn PËn 6L cflb_ x6fpg] sfo{ lemSg], 5'6\ofpg] / /fd¦/L yGsfpg] ;d]t
|  | 1 | 11.5 | 0.23 | 1.2 | 3.174
| Sub-total |  |  |  |  | 4.933 | m3 | 1950 | 9619.2778
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -White wall | 1 | 10.53 | 0.46 | 0.6 | 2.9063
| Sub-total |  |  |  |  | 2.9063 | m3 | 64.63 | 187.8329
| VAT calculation | [7 empty] | 20.2384
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at backyard | 2 | 0.6 | 0.6 | 0.9 | 0.648
| Sub-total |  |  |  |  | 0.648 | m3 | 663.31 | 429.8249
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing | 1 | 10.53 | 0.46 |  | 4.8438
|  | 1 | 0.6 | 0.6 |  | 0.36
| Sub-total |  |  |  |  | 5.2038 | sqm | 1014.97 | 5281.7009
| VAT calculation | [7 empty] | 582.9484
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -for footing | 2 | 10.53 | 0.46 | 0.050344 | 0.48772
|  | 2 | 0.6 | 0.6 | 0.050798 | 0.036574
| Sub-total |  |  |  |  | 0.52429 | m3 | 12983.1 | 6806.9185 |  | 0.65536
| VAT calculation | [7 empty] | 550.5861
6 | ;'k/ :6«Sr/, 8]s :n]a ljdx?df l;d]G6 s+lqm6 ug]{ sfd -!M!.%M#_
| -for footing | 2 | 0.75 | 0.75 | 0.225 | 0.25312
|  | 2 | 0.23 | 0.23 | 2.475 | 0.26186
| Sub-total |  |  |  |  | 0.51498 | m3 | 16512.62 | 8503.669
| VAT calculation | [7 empty] | 608.7273
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for footing | 2 | 3 |  | 0.225 | 1.35
|  | 2 | 0.92 |  | 2.475 | 4.554
| Sub-total |  |  |  |  | 5.904 | m2 | 915.42 | 5404.6397
| VAT calculation | [7 empty] | 359.4133
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For column footing | 24 | 0.6 | 0.88889 | 12.8 | 0.0128
| -For column | 8 | 2.8955 | 0.88889 | 20.5899 | 0.02059
| -For column stirrups | 16 | 0.71117 | 0.39506 | 4.4953 | 0.0044953
| Sub-total |  |  |  |  | 0.037885 | MT | 131940 | 4998.5727
| VAT calculation | [7 empty] | 523.043
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | [10 empty] | 37.666
| -wall at backyard | 1 | 11.73 | 0.23 | 1.65 | 4.4515
| -deduction for column part | -2 | 0.23 | 0.23 | 1.65 | -0.17457
| -wall at front | 1 | 2.9717 | 0.23 | 2.1336 | 1.4583
|  | 1 | 0.35558 | 0.35558 | 2.1336 | 0.26977
|  | 1 | 2.9717 | 0.23 | 2.1336 | 1.4583
|  | 1 | 0.35558 | 0.35558 | 2.1336 | 0.26977
|  | 1 | 2.9717 | 0.23 | 2.1336 | 1.4583
|  | 1 | 0.35558 | 0.35558 | 2.1336 | 0.26977
|  | 1 | 0.43178 | 0.1 | 2.1336 | 0.092125
| Sub-total |  |  |  |  | 9.5533 | m3 | 14362.76 | 137211.5728
| VAT calculation | [7 empty] | 12806.4319
10 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df k'/fgf] O6\6f @% k¦ltzt | [11 empty] | 37.666
| -window top cover at backyard | 1 | 17.1 | 0.23 | 0.125 | 0.49163 |  |  |  |  | 21.49
| -front side right part of gate | 1 | 0.35558 | 0.35558 | 0.12 | 0.015173
|  | 1 | 2.75 | 0.23 | 0.12 | 0.0759
|  | 1 | 0.35558 | 0.35558 | 0.12 | 0.015173
|  | 1 | 2.69 | 0.23 | 0.12 | 0.074244
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 0.95 | 0.23 | 0.12 | 0.02622
|  | 1 | 2.73 | 0.23 | 0.25 | 0.15698
|  | 1 | 0.58 | 0.23 | 0.6 | 0.08004
| -front side left part of gate | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 3.02 | 0.23 | 0.12 | 0.083352
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 3.13 | 0.23 | 0.12 | 0.086388
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 3.17 | 0.23 | 0.12 | 0.087492
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
| -window backyard | 12 | 0.83 | 0.23 | 1.2 | 2.749
| Sub-total |  |  |  |  | 4.0174 | m3 | 8001.86 | 32146.7698
| VAT calculation | [7 empty] | 2063.3799
11 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 2 | 64 |  | 1.8 | 230.4
| Sub-total |  |  |  |  | 230.4 | sqm | 405.86 | 93510.144
| VAT calculation | [7 empty] | 3344.5002
12 | $=% X @) dL=dL= kmnfd] kftfsf] k¦m]ddf !@ x !@ dL=dL=;f]ln8 sf]/ :Sjfo/ /8sf] lu¦n agfO{ vfS;L nufO{ /]8cS;fO8 tyf cNd'lgod k]G6 ;d]t u/L hf]8\g]
| -window | 6 | 1.2 |  | 1.6519 | 11.8939
| -door | 1 | 0.885 |  | 2.05 | 1.8142
| Sub-total |  |  |  |  | 13.7082 | sqm | 2575.34 | 35303.2366
| VAT calculation | [7 empty] | 4338.2495
13 | lh=cfO{=sf9]tf/ -jf/ j]8 jfo/_ nufpg] .
| -at boundary | 1 | 225 |  |  | 225
| Sub-total |  |  |  |  | 225 | rm | 82.59 | 18582.75 |  | 281.25
| VAT calculation | [7 empty] | 582.701
14 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
| -wall | 2 | 64 |  | 1.8 | 230.4
| Sub-total |  |  |  |  | 230.4 | sqm | 251.77 | 58007.808
| VAT calculation | [7 empty] | 3814.6867
15 | c:t/ jfx]s Pssf]6 tof/L Ogfd]n k]G6 ug]{ sfd .
| -gate | 2 | 2.28 |  | 1.97 | 8.9832
|  | 1 | 0.89 |  | 2.13 | 1.8957
| Sub-total |  |  |  |  | 10.8789 | sqm | 128.43 | 1397.1771
| VAT calculation | [7 empty] | 68.9875
16 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (Kg)
| -MS Equal angle of 35mm*35mm*2mm For door | 4 | 8.1271 | 1.04 | 33.8087 | 33.8087
| -MS sheet 900mm wide or as per required and of 14G with 2mm | 4 | 2.4383 | 14.13 | 137.8116 | 137.8116
| Sub-total |  |  |  |  | 171.6204 | Kg | 181.17 | 31092.4606
| VAT calculation | [7 empty] | 2204.4662
17 | %) dL=dL=Aof;sf] :6]Gn];l:6nsf] x\of08/]ndf @ ld6/sf] b"/Ldf %) dL=dL=Aof;sf] :6]Gn];l:6ns} 7f8f] kf]i6 /fvL x\of08/]n / e"O+sf] aLrdf tLg tx t];f]{ @% dL=dL=Aof;sf] :6]Gn];l:6nsf] d]Da/ /fvL @Ú–^Æ b]lv #Ú–)Æ ;Dd prfO{ ePsf] /]lnË pknAw u/fO{ h8fg u/L /+u ;d]t nufpg] sfd .
| -at boundary | 1 | 7.8482 |  |  | 7.8482
| Sub-total |  |  |  |  | 7.8482 | rm | 4132.8 | 32435.1112
| VAT calculation | [7 empty] | 4216.5645
18 | kmnfd] sf]nfK;Lan u]6 k]lG6Ë / h8fg ;d]t ug]{
| -at block D | 1 | 3.23 |  | 2.536 | 8.1913
| Sub-total |  |  |  |  | 8.1913 | sqm | 6391.43 | 52353.9927
| VAT calculation | [7 empty] | 6806.0191
19 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 5000 | 5000
20 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 581664.4022
| Total Estimated | 581664.4022 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 81.6622
| User Contribution | 106664.4022 |  | 18.3378
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on C11: Windows User: white wall
Note on C12: Windows User: column as wall support and including footing area

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 581664.4022 |  |  |  |  | Total Valuated Amount : |  | 450563.3551
Work Started : | [7 empty] | Work Finished:
Project:- राष्ट्रिय मा. बि. वाल निर्माण | [7 empty] | F.Y:2081/2082
Location:- Shankharapur Municipality 9 | [7 empty] | Date:
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd . | m3 | 4.933 | 1950 | 9619.2778 | 4.8615 | 1950 | 9480.0186 | -139.2592 |  | 12024.0973
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. | m3 | 2.9063 | 64.63 | 187.8329 | 2.7911 | 64.63 | 180.3868 | -7.446 |  | 234.7911
| VAT calculation |  |  |  | 20.2384 |  |  | 19.4361 | -0.80229 |  | 25.298
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | m3 | 0.648 | 663.31 | 429.8249 | 0.5346 | 663.31 | 354.6055 | -75.2194 |  | 537.2811
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd | sqm | 5.2038 | 1014.97 | 5281.7009 | 6.6548 | 1014.97 | 6754.3913 | 1472.6905 |  | 6602.1261
| VAT calculation |  |  |  | 582.9484 |  |  | 745.4912 | 162.5428 |  | 728.6855
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_ | m3 | 0.52429 | 12983.1 | 6806.9185 | 0.57995 | 12983.1 | 7529.5515 | 722.633 |  | 8508.6481
| VAT calculation |  |  |  | 550.5861 |  |  | 609.0372 | 58.4511 |  | 688.2327
6 | ;'k/ :6«Sr/, 8]s :n]a ljdx?df l;d]G6 s+lqm6 ug]{ sfd -!M!.%M#_ | m3 | 0.51498 | 16512.62 | 8503.669 | 0.49291 | 16512.62 | 8139.2118 | -364.4572 |  | 10629.5863
| VAT calculation |  |  |  | 608.7273 |  |  | 582.6379 | -26.0893 |  | 760.9091
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd | m2 | 5.904 | 915.42 | 5404.6397 | 4.6162 | 915.42 | 4225.7947 | -1178.845 |  | 6755.7996
| VAT calculation |  |  |  | 359.4133 |  |  | 281.019 | -78.3942 |  | 449.2666
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | MT | 0.037885 | 131940 | 4998.5727 | 0.036819 | 131940 | 4857.8367 | -140.736 |  | 6248.2159
| VAT calculation |  |  |  | 523.043 |  |  | 508.3166 | -14.7264 |  | 653.8038
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | m3 | 9.5533 | 14362.76 | 137211.5728 | 10.9389 | 14362.76 | 157112.5973 | 19901.0245 |  | 171514.466
| VAT calculation |  |  |  | 12806.4319 |  |  | 14663.8636 | 1857.4316 |  | 16008.0399
10 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df k'/fgf] O6\6f @% k¦ltzt | m3 | 4.0174 | 8001.86 | 32146.7698 | 4.0174 | 8001.86 | 32146.7698 | 0 |  | 40183.4623
| VAT calculation |  |  |  | 2063.3799 |  |  | 2063.3799 | 0 |  | 2579.2248
11 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/ | sqm | 230.4 | 405.86 | 93510.144 | 210.797 | 405.86 | 85554.0728 | -7956.0712 |  | 116887.68
| VAT calculation |  |  |  | 3344.5002 |  |  | 3059.942 | -284.5582 |  | 4180.6253
12 | $=% X @) dL=dL= kmnfd] kftfsf] k¦m]ddf !@ x !@ dL=dL=;f]ln8 sf]/ :Sjfo/ /8sf] lu¦n agfO{ vfS;L nufO{ /]8cS;fO8 tyf cNd'lgod k]G6 ;d]t u/L hf]8\g] | sqm | 13.7082 | 2575.34 | 35303.2366 | 11.8939 | 2575.34 | 30630.926 | -4672.3106 |  | 44129.0457
| VAT calculation |  |  |  | 4338.2495 |  |  | 3764.0911 | -574.1584 |  | 5422.8119
13 | lh=cfO{=sf9]tf/ -jf/ j]8 jfo/_ nufpg] . | rm | 225 | 82.59 | 18582.75 | 270 | 82.59 | 22299.3 | 3716.55 |  | 23228.4375
| VAT calculation |  |  |  | 582.701 |  |  | 699.2411 | 116.5402 |  | 728.3762
14 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd | sqm | 230.4 | 251.77 | 58007.808 | 102.3706 | 251.77 | 25773.8451 | -32233.9629 |  | 72509.76
| VAT calculation |  |  |  | 3814.6867 |  |  | 1694.9295 | -2119.7572 |  | 4768.3584
15 | c:t/ jfx]s Pssf]6 tof/L Ogfd]n k]G6 ug]{ sfd . | sqm | 10.8789 | 128.43 | 1397.1771 | 10.8789 | 128.43 | 1397.1771 | 0 |  | 1746.4714
| VAT calculation |  |  |  | 68.9875 |  |  | 68.9875 | 0 |  | 86.2343
16 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | Kg | 171.6204 | 181.17 | 31092.4606 | 128.1679 | 181.17 | 23220.1784 | -7872.2821 |  | 38865.5757
| VAT calculation |  |  |  | 2204.4662 |  |  | 1646.3187 | -558.1475 |  | 2755.5828
17 | %) dL=dL=Aof;sf] :6]Gn];l:6nsf] x\of08/]ndf @ ld6/sf] b"/Ldf %) dL=dL=Aof;sf] :6]Gn];l:6ns} 7f8f] kf]i6 /fvL x\of08/]n / e"O+sf] aLrdf tLg tx t];f]{ @% dL=dL=Aof;sf] :6]Gn];l:6nsf] d]Da/ /fvL @Ú–^Æ b]lv #Ú–)Æ ;Dd prfO{ ePsf] /]lnË pknAw u/fO{ h8fg u/L /+u ;d]t nufpg] sfd . | rm | 7.8482 | 4132.8 | 32435.1112 | 0 | 4132.8 | 0 | -32435.1112 |  | 40543.8891
| VAT calculation |  |  |  | 4216.5645 |  |  | 0 | -4216.5645 |  | 5270.7056
18 | kmnfd] sf]nfK;Lan u]6 k]lG6Ë / h8fg ;d]t ug]{ | sqm | 8.1913 | 6391.43 | 52353.9927 | 0 | 6391.43 | 0 | -52353.9927 |  | 65442.4909
| VAT calculation |  |  |  | 6806.0191 |  |  | 0 | -6806.0191 |  | 8507.5238
19 | Provisional sum for unforseen works | PS | 1 | 5000 | 5000 | 0 | 5000 | 0 | -5000 |  | 6250
20 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0 |  | 625
| Total |  |  |  | 581664.4022 |  |  | 450563.3551 | -131101.0471

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- राष्ट्रिय मा. बि. वाल निर्माण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -White wall | 1 | 3.88 | 0.1 | 2.2859 | 0.88692
|  | 3 | 0.3566 | 0.3566 | 2.2859 | 0.87204 | [5 empty] | kmnfd] sfd -Rofgn PËn 6L cflb_ x6fpg] sfo{ lemSg], 5'6\ofpg] / /fd¦/L yGsfpg] ;d]t
| -at backyard wall | 1 | 11.73 | 0.23 | 1.15 | 3.1026
| Sub-total |  |  |  |  | 4.8615 | m3 | 1950 | 9480.0186
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -White wall | 1 | 10.3373 | 0.45 | 0.6 | 2.7911
| Sub-total |  |  |  |  | 2.7911 | m3 | 64.63 | 180.3868
| VAT calculation | [7 empty] | 19.4361
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at backyard wall | 2 | 0.9 | 0.9 | 0.33 | 0.5346
| Sub-total |  |  |  |  | 0.5346 | m3 | 663.31 | 354.6055
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing | 2 | 0.9 | 0.9 |  | 1.62
| -at front wall | 2 | 9.2959 | 0.23 |  | 4.2761
|  | 6 | 0.35558 | 0.35558 |  | 0.75863
| Sub-total |  |  |  |  | 6.6548 | sqm | 1014.97 | 6754.3913
| VAT calculation | [7 empty] | 745.4912
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -at front wall | 2 | 9.2959 | 0.23 | 0.075 | 0.32071
|  | 6 | 0.35558 | 0.35558 | 0.075 | 0.056898
| -at backyard wall | 1 | 11.73 | 0.23 | 0.075 | 0.20234
| Sub-total |  |  |  |  | 0.57995 | m3 | 12983.1 | 7529.5515
| VAT calculation | [7 empty] | 609.0372
6 | ;'k/ :6«Sr/, 8]s :n]a ljdx?df l;d]G6 s+lqm6 ug]{ sfd -!M!.%M#_
| -for footing | 2 | 0.9 | 0.9 | 0.15 | 0.243
|  | 2 | 0.23 | 0.23 | 2.3621 | 0.24991
| Sub-total |  |  |  |  | 0.49291 | m3 | 16512.62 | 8139.2118
| VAT calculation | [7 empty] | 582.6379
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for footing | 2 | 0.9 |  | 0.15 | 0.27
|  | 2 | 0.92 |  | 2.3621 | 4.3462
| Sub-total |  |  |  |  | 4.6162 | m2 | 915.42 | 4225.7947
| VAT calculation | [7 empty] | 281.019
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For column footing | 22 | 0.6 | 0.88889 | 11.7333 | 0.011733
| -For column | 8 | 2.8955 | 0.88889 | 20.5899 | 0.02059
| -For column stirrups | 16 | 0.71117 | 0.39506 | 4.4953 | 0.0044953
| Sub-total |  |  |  |  | 0.036819 | MT | 131940 | 4857.8367
| VAT calculation | [7 empty] | 508.3166
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | [11 empty] | 37.666
| -wall at backyard | 1 | 11.73 | 0.23 | 1.675 | 4.519
| -deduction for column part | -2 | 0.23 | 0.23 | 1.675 | -0.17722
| -wall at front | 1 | 2.9717 | 0.23 | 2.1336 | 1.4583
|  | 1 | 0.35558 | 0.35558 | 2.1336 | 0.26977
|  | 1 | 2.9717 | 0.23 | 2.1336 | 1.4583
|  | 1 | 0.35558 | 0.35558 | 2.1336 | 0.26977
|  | 1 | 2.9717 | 0.23 | 2.1336 | 1.4583
|  | 1 | 0.35558 | 0.35558 | 2.1336 | 0.26977
|  | 1 | 0.43178 | 0.1 | 2.1336 | 0.092125
|  | 1 | 10.4135 | 0.45 | 0.23 | 1.0778
|  | 2 | 0.9 | 0.45 | 0.3 | 0.243
| Sub-total |  |  |  |  | 10.9389 | m3 | 14362.76 | 157112.5973
| VAT calculation | [7 empty] | 14663.8636
10 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df k'/fgf] O6\6f @% k¦ltzt | [11 empty] | 37.666
| -window top cover at backyard | 1 | 17.1 | 0.23 | 0.125 | 0.49163 |  |  |  |  | 21.49
| -front side right part of gate | 1 | 0.35558 | 0.35558 | 0.12 | 0.015173
|  | 1 | 2.75 | 0.23 | 0.12 | 0.0759
|  | 1 | 0.35558 | 0.35558 | 0.12 | 0.015173
|  | 1 | 2.69 | 0.23 | 0.12 | 0.074244
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 0.95 | 0.23 | 0.12 | 0.02622
|  | 1 | 2.73 | 0.23 | 0.25 | 0.15698
|  | 1 | 0.58 | 0.23 | 0.6 | 0.08004
| -front side left part of gate | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 3.02 | 0.23 | 0.12 | 0.083352
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 3.13 | 0.23 | 0.12 | 0.086388
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 3.17 | 0.23 | 0.12 | 0.087492
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
| -window backyard | 12 | 0.83 | 0.23 | 1.2 | 2.749
| Sub-total |  |  |  |  | 4.0174 | m3 | 8001.86 | 32146.7698
| VAT calculation | [7 empty] | 2063.3799
11 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/ | [9 empty] | inner face of gate side wall | 0 | 1.3
| -wall | 1 | 3 |  | 1.37 | 4.11 | [5 empty] | 3 | 1.44
|  | 1 | 3 |  | 1.41 | 4.23 | [5 empty] | 3 | 1.38
|  | 1 | 3 |  | 1.415 | 4.245 | [5 empty] | 3 | 1.45
|  | 1 | 3 |  | 1.455 | 4.365 | [5 empty] | 3 | 1.46
|  | 1 | 3 |  | 1.505 | 4.515 | [5 empty] | 3 | 1.55
|  | 1 | 3 |  | 1.485 | 4.455 | [5 empty] | 3 | 1.42
|  | 1 | 3.42 |  | 1.47 | 5.0274 |  |  |  |  | upto inner face to gate | 3.42 | 1.52
[11 empty] | outer face of gate side new wall | 0 | 1.7
|  | 1 | 0.14 |  | 1.7 | 0.238 | [5 empty] | 0.14 | 1.7
|  | 1 | 3.01 |  | 1.6 | 4.816 | [5 empty] | 3.01 | 1.6
|  | 1 | 0.58 |  | 1.7 | 0.986 | [5 empty] | 0.58 | 1.7
|  | 1 | 3.12 |  | 1.64 | 5.1168 | [5 empty] | 3.12 | 1.64
|  | 1 | 0.6 |  | 1.65 | 0.99 | [5 empty] | 0.6 | 1.65
|  | 1 | 3.16 |  | 1.65 | 5.214 | [5 empty] | 3.16 | 1.65
|  | 1 | 0.66 |  | 1.65 | 1.089 | [5 empty] | 0.66 | 1.65
|  | 1 | 2.96 |  | 1.71 | 5.0616 | [5 empty] | 2.96 | 1.71
|  | 1 | 0.62 |  | 1.72 | 1.0664 | [5 empty] | 0.62 | 1.72
|  | 1 | 2.96 |  | 1.735 | 5.1356 | [5 empty] | 2.96 | 1.735
|  | 1 | 0.63 |  | 1.7 | 1.071 | [5 empty] | 0.63 | 1.7
|  | 1 | 2.92 |  | 1.635 | 4.7742 | [5 empty] | 2.92 | 1.635
|  | 1 | 0.61 |  | 1.6 | 0.976 | [5 empty] | 0.61 | 1.6
|  | 1 | 0.44 |  | 1.55 | 0.682 |  |  |  |  | upto gate | 0.44 | 1.55
[11 empty] | back compound inner face wall | 0 | 1.5
|  | 1 | 3 |  | 1.525 | 4.575 | [5 empty] | 3 | 1.55
|  | 1 | 3 |  | 1.55 | 4.65 | [5 empty] | 3 | 1.55
|  | 1 | 3 |  | 1.635 | 4.905 | [5 empty] | 3 | 1.72
|  | 1 | 3.06 |  | 1.65 | 5.049 | [5 empty] | 3.06 | 1.65
|  | 1 | 0.16 |  | 1.61 | 0.2576 |  |  |  |  | break point of old wall and new wall | 0.16 | 1.61
| -window | 10 | 0.83816 |  | 1.2 | 10.0579 |  |  |  |  | old wall | 0 | 1.6
|  | 1 | 0.6 |  | 1.6 | 0.96 | [5 empty] | 0.6 | 1.6
|  | 1 | 15.5 |  | 0.2 | 3.1 |  |  |  |  | inner face complete | 15.5 | 0.2
[11 empty] | outside face of back compound | 0 | 1.75 | DPC to top of new wall
|  | 1 | 4 |  | 1.75 | 7 | [5 empty] | 4 | 1.75
|  | 1 | 4 |  | 1.75 | 7 | [5 empty] | 4 | 1.75
|  | 1 | 4.21 |  | 1.75 | 7.3675 | [5 empty] | 4.21 | 1.75 | new wall complete
|  | 1 | 0.49 |  | 2.1 | 1.029 | [5 empty] | 0.49 | 2.1 | old wall starts
|  | 1 | 0 |  | 2.1 | 0 | [5 empty] | 0 | 2.1
|  | 1 | 3.17 |  | 2.1 | 6.657 | [5 empty] | 3.17 | 2.1
|  | 1 | 0.48 |  | 2.1 | 1.008 | [5 empty] | 0.48 | 2.1
|  | 1 | 3.11 |  | 2.1 | 6.531 | [5 empty] | 3.11 | 2.1
|  | 1 | 0.6 |  | 2.1 | 1.26 | [5 empty] | 0.6 | 2.1
|  | 1 | 3.1 |  | 2.1 | 6.51 | [5 empty] | 3.1 | 2.1
|  | 1 | 0.6 |  | 2.1 | 1.26 | [5 empty] | 0.6 | 2.1
|  | 1 | 3.11 |  | 2.155 | 6.7021 | [5 empty] | 3.11 | 2.155
|  | 1 | 0.6 |  | 2.2 | 1.32 | [5 empty] | 0.6 | 2.2
|  | 1 | 3.1 |  | 2.24 | 6.944 | [5 empty] | 3.1 | 2.24
|  | 1 | 0.58 |  | 2.2 | 1.276 | [5 empty] | 0.58 | 2.2
|  | 1 | 3.15 |  | 2.275 | 7.1662 | [5 empty] | 3.15 | 2.275
|  | 1 | 3.25 |  | 2.3 | 7.475 | [5 empty] | 3.25 | 2.3
|  | 1 | 0.57 |  | 2.3 | 1.311 | [5 empty] | 0.57 | 2.3
|  | 1 | 0.97 |  | 2.3 | 2.231 | [5 empty] | 0.97 | 2.3
[11 empty] | baniya gaun baato to gate side | 0 | 1.76
|  | 1 | 0.48 |  | 1.75 | 0.84 | [5 empty] | 0.48 | 1.75
|  | 1 | 2.75 |  | 1.75 | 4.8125 | [5 empty] | 2.75 | 1.75
|  | 1 | 0.57 |  | 1.75 | 0.9975 | [5 empty] | 0.57 | 1.75
|  | 1 | 2.65 |  | 1.775 | 4.7037 | [5 empty] | 2.65 | 1.8
|  | 1 | 0.58 |  | 1.8 | 1.044 | [5 empty] | 0.58 | 1.8
|  | 1 | 1.16 |  | 1.8 | 2.088 | [5 empty] | 1.16 | 1.8
|  | 1 | 0.6 |  | 1.8 | 1.08 | [5 empty] | 0.6 | 1.8
|  | 1 | 2.7431 |  | 1.8 | 4.9375 | [5 empty] | 2.7431 | 1.8
|  | 1 | 0.58 |  | 2.1335 | 1.2374 | [5 empty] | 0.58 | 2.1335
|  | 2 | 0.9 |  | 0.3 | 0.54
| -Chautari | 1 | 15 |  | 0.45 | 6.75
| Sub-total |  |  |  |  | 210.797 | sqm | 405.86 | 85554.0728
| VAT calculation | [7 empty] | 3059.942
12 | $=% X @) dL=dL= kmnfd] kftfsf] k¦m]ddf !@ x !@ dL=dL=;f]ln8 sf]/ :Sjfo/ /8sf] lu¦n agfO{ vfS;L nufO{ /]8cS;fO8 tyf cNd'lgod k]G6 ;d]t u/L hf]8\g]
| -window | 6 | 1.2 |  | 1.6519 | 11.8939
| Sub-total |  |  |  |  | 11.8939 | sqm | 2575.34 | 30630.926 |  | 28262.52
| VAT calculation | [7 empty] | 3764.0911
13 | lh=cfO{=sf9]tf/ -jf/ j]8 jfo/_ nufpg] .
| -at boundary | 3 | 90 |  |  | 270
| Sub-total |  |  |  |  | 270 | rm | 82.59 | 22299.3
| VAT calculation | [7 empty] | 699.2411
14 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd |  | Area of plaster (m2)
| -wall | 1 | 210.797 |  |  | 210.797
| -deduction for incomplete ones | [9 empty] | back compound inner face wall | 0 | 1.5
|  | -1 | 3 |  | 1.525 | -4.575 | [5 empty] | 3 | 1.55
|  | -1 | 3 |  | 1.55 | -4.65 | [5 empty] | 3 | 1.55
|  | -1 | 3 |  | 1.635 | -4.905 | [5 empty] | 3 | 1.72
|  | -1 | 3.06 |  | 1.65 | -5.049 | [5 empty] | 3.06 | 1.65
|  | -1 | 0.16 |  | 1.61 | -0.2576 |  |  |  |  | break point of old wall and new wall | 0.16 | 1.61
| -window | -10 | 0.83816 |  | 1.2 | -10.0579 |  |  |  |  | old wall | 0 | 1.6
|  | -1 | 0.6 |  | 1.6 | -0.96 | [5 empty] | 0.6 | 1.6
|  | -1 | 15 |  | 0.2 | -3 |  |  |  |  | inner face complete | 15 | 0.2
[11 empty] | outside face of back compound | 0 | 1.75 | DPC to top of new wall
|  | -1 | 4 |  | 1.75 | -7 | [5 empty] | 4 | 1.75
|  | -1 | 4 |  | 1.75 | -7 | [5 empty] | 4 | 1.75
|  | -1 | 4.21 |  | 1.75 | -7.3675 | [5 empty] | 4.21 | 1.75 | new wall complete
|  | -1 | 0.49 |  | 2.1 | -1.029 | [5 empty] | 0.49 | 2.1 | old wall starts
|  | -1 | 0 |  | 2.1 | 0 | [5 empty] | 0 | 2.1
|  | -1 | 3.17 |  | 2.1 | -6.657 | [5 empty] | 3.17 | 2.1
|  | -1 | 0.48 |  | 2.1 | -1.008 | [5 empty] | 0.48 | 2.1
|  | -1 | 3.11 |  | 2.1 | -6.531 | [5 empty] | 3.11 | 2.1
|  | -1 | 0.6 |  | 2.1 | -1.26 | [5 empty] | 0.6 | 2.1
|  | -1 | 3.1 |  | 2.1 | -6.51 | [5 empty] | 3.1 | 2.1
|  | -1 | 0.6 |  | 2.1 | -1.26 | [5 empty] | 0.6 | 2.1
|  | -1 | 3.11 |  | 2.155 | -6.7021 | [5 empty] | 3.11 | 2.155
|  | -1 | 0.6 |  | 2.2 | -1.32 | [5 empty] | 0.6 | 2.2
|  | -1 | 3.1 |  | 2.24 | -6.944 | [5 empty] | 3.1 | 2.24
|  | -1 | 0.58 |  | 2.2 | -1.276 | [5 empty] | 0.58 | 2.2
|  | -1 | 3.15 |  | 2.275 | -7.1662 | [5 empty] | 3.15 | 2.275
|  | -1 | 3.25 |  | 2.3 | -7.475 | [5 empty] | 3.25 | 2.3
|  | -1 | 0.57 |  | 2.3 | -1.311 | [5 empty] | 0.57 | 2.3
|  | -1 | 0.97 |  | 2.3 | -2.231 | [5 empty] | 0.97 | 2.3
| -old part | 1 | 1.93 |  | 2.63 | 5.0759
| Sub-total |  |  |  |  | 102.3706 | sqm | 251.77 | 25773.8451
| VAT calculation | [7 empty] | 1694.9295
15 | c:t/ jfx]s Pssf]6 tof/L Ogfd]n k]G6 ug]{ sfd .
| -gate | 2 | 2.28 |  | 1.97 | 8.9832
|  | 1 | 0.89 |  | 2.13 | 1.8957
| Sub-total |  |  |  |  | 10.8789 | sqm | 128.43 | 1397.1771
| VAT calculation | [7 empty] | 68.9875
16 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (Kg) |  |  |  | by actual measurement in digital weighing machine at site
| -metal door with MS sheet 900mm wide or as per required and of 14G including frames | 2 |  |  | 61.25 | 61.25
| -deduction for MS sheet 900mm wide or as per required and of 14G thick | -1 | 0.515 | 14.14 | -7.2821 | -7.2821
| -MS Rectangular Hollow section of 40mm*25mm*2.2mm for window | 6 | 2.54 | 2 | 30.48 | 30.48
|  | 4 | 0.47 | 2 | 3.76 | 3.76
| -MS equal angle of size 50mm*50mm of thickness 3mm | 30 | 0.6 | 2.22 | 39.96 | 39.96
| Sub-total |  |  |  |  | 128.1679 | Kg | 181.17 | 23220.1784
| VAT calculation | [7 empty] | 1646.3187
17 | %) dL=dL=Aof;sf] :6]Gn];l:6nsf] x\of08/]ndf @ ld6/sf] b"/Ldf %) dL=dL=Aof;sf] :6]Gn];l:6ns} 7f8f] kf]i6 /fvL x\of08/]n / e"O+sf] aLrdf tLg tx t];f]{ @% dL=dL=Aof;sf] :6]Gn];l:6nsf] d]Da/ /fvL @Ú–^Æ b]lv #Ú–)Æ ;Dd prfO{ ePsf] /]lnË pknAw u/fO{ h8fg u/L /+u ;d]t nufpg] sfd .
| -at boundary | 0 | 7.8735 |  |  | 0
| Sub-total |  |  |  |  | 0 | rm | 4132.8 | 0
| VAT calculation | [7 empty] | 0
18 | kmnfd] sf]nfK;Lan u]6 k]lG6Ë / h8fg ;d]t ug]{
| -at block D | 0 | 3.23 |  | 2.535 | 0
| Sub-total |  |  |  |  | 0 | sqm | 6391.43 | 0
| VAT calculation | [7 empty] | 0
19 | Provisional sum for unforseen works | 0 |  |  |  | 0 | PS | 5000 | 0
20 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 450563.3551
| Total Valuated | 450563.3551 |  | 100
| Budget allocated | 500000
| Municipal payment | 367930.0358 |  | 81.66
| User Contribution | 82633.3193 |  | 18.34
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on C11: Windows User: white wall
Note on C32: DELL: Must be value 2 so instead 1 if required use 2

## after valuated created for rees (hidden)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- राष्ट्रिय मा. बि. वाल निर्माण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/21
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -White wall | 1 | 3.88 | 0.1 | 2.2859 | 0.88692
|  | 3 | 0.3566 | 0.3566 | 2.2859 | 0.87204 | [5 empty] | kmnfd] sfd -Rofgn PËn 6L cflb_ x6fpg] sfo{ lemSg], 5'6\ofpg] / /fd¦/L yGsfpg] ;d]t
| -at backyard wall | 1 | 11.73 | 0.23 | 1.15 | 3.1026
| Sub-total |  |  |  |  | 4.8615 | m3 | 1950 | 9480.0186
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -White wall | 1 | 10.3373 | 0.45 | 0.6 | 2.7911
| Sub-total |  |  |  |  | 2.7911 | m3 | 64.63 | 180.3868
| VAT calculation | [7 empty] | 19.4361
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at backyard wall | 2 | 0.9 | 0.9 | 0.33 | 0.5346
| Sub-total |  |  |  |  | 0.5346 | m3 | 663.31 | 354.6055
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -at front wall | 2 | 9.2959 | 0.23 | 0.05 | 0.21381
|  | 6 | 0.35558 | 0.35558 | 0.05 | 0.037932
| Sub-total |  |  |  |  | 0.25174 | sqm | 1014.97 | 255.507
| VAT calculation | [7 empty] | 28.2006
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -at front wall | 2 | 9.2959 | 0.23 | 0.05 | 0.21381
|  | 6 | 0.35558 | 0.35558 | 0.05 | 0.037932
| -at backyard wall | 1 | 11.73 | 0.23 | 0.05 | 0.1349
| Sub-total |  |  |  |  | 0.38663 | m3 | 12983.1 | 5019.701
| VAT calculation | [7 empty] | 406.0248
6 | ;'k/ :6«Sr/, 8]s :n]a ljdx?df l;d]G6 s+lqm6 ug]{ sfd -!M!.%M#_
| -for footing | 2 | 0.9 | 0.9 | 0.225 | 0.3645
|  | 2 | 0.23 | 0.23 | 2.3621 | 0.24991
| Sub-total |  |  |  |  | 0.61441 | m3 | 16512.62 | 10145.4951
| VAT calculation | [7 empty] | 726.2559
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for footing | 2 | 0.9 |  | 0.9 | 1.62
|  | 2 | 0.92 |  | 2.3621 | 4.3462
| Sub-total |  |  |  |  | 5.9662 | m2 | 915.42 | 5461.6117
| VAT calculation | [7 empty] | 363.202
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For column footing | 22 | 0.6 | 0.88889 | 11.7333 | 0.011733
| -For column | 8 | 2.8955 | 0.88889 | 20.5899 | 0.02059
| -For column stirrups | 16 | 0.71117 | 0.39506 | 4.4953 | 0.0044953
| Sub-total |  |  |  |  | 0.036819 | MT | 131940 | 4857.8367
| VAT calculation | [7 empty] | 508.3166
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | [11 empty] | 37.666
| -wall at backyard | 1 | 11.73 | 0.23 | 1.75 | 4.7213
| -deduction for column part | -2 | 0.23 | 0.23 | 1.75 | -0.18515
| -wall at front | 1 | 2.9717 | 0.23 | 2.1335 | 1.4582
|  | 1 | 0.35558 | 0.35558 | 2.1335 | 0.26976
|  | 1 | 2.9717 | 1.23 | 2.1335 | 7.7982
|  | 1 | 0.35558 | 0.35558 | 2.1335 | 0.26976
|  | 1 | 2.9717 | 0.23 | 2.1335 | 1.4582
|  | 1 | 0.35558 | 0.35558 | 2.1335 | 0.26976
|  | 1 | 0.43178 | 0.1 | 2.1335 | 0.09212
| Sub-total |  |  |  |  | 16.1522 | m3 | 14362.76 | 231990.0192
| VAT calculation | [7 empty] | 21652.433
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | [11 empty] | 37.666
| -window top cover at backyard | 1 | 17.1 | 0.23 | 0.125 | 0.49163 |  |  |  |  | 21.49
| -front side right part of gate | 1 | 0.35558 | 0.35558 | 0.12 | 0.015173
|  | 1 | 2.75 | 0.23 | 0.12 | 0.0759
|  | 1 | 0.35558 | 0.35558 | 0.12 | 0.015173
|  | 1 | 2.69 | 0.23 | 0.12 | 0.074244
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 0.95 | 0.23 | 0.12 | 0.02622
|  | 1 | 2.73 | 0.23 | 0.25 | 0.15698
|  | 1 | 0.58 | 0.23 | 0.6 | 0.08004
| -front side left part of gate | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 3.02 | 0.23 | 0.12 | 0.083352
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 3.13 | 0.23 | 0.12 | 0.086388
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 3.17 | 0.23 | 0.12 | 0.087492
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
| -window backyard | 12 | 0.83 | 0.23 | 1.2 | 2.749
| Sub-total |  |  |  |  | 4.0174 | m3 | 14362.76 | 57701.127
| VAT calculation | [7 empty] | 5385.4463
10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 0 | 72.7696 |  | 1.8 | 0 |  |  |  |  | inner face of gate side wall | 0 | 1.3
|  | 1 | 3 |  | 1.37 | 4.11 | [5 empty] | 3 | 1.44
|  | 1 | 3 |  | 1.41 | 4.23 | [5 empty] | 3 | 1.38
|  | 1 | 3 |  | 1.415 | 4.245 | [5 empty] | 3 | 1.45
|  | 1 | 3 |  | 1.455 | 4.365 | [5 empty] | 3 | 1.46
|  | 1 | 3 |  | 1.505 | 4.515 | [5 empty] | 3 | 1.55
|  | 1 | 3 |  | 1.485 | 4.455 | [5 empty] | 3 | 1.42
|  | 1 | 3.42 |  | 1.47 | 5.0274 |  |  |  |  | upto inner face to gate | 3.42 | 1.52
[11 empty] | outer face of gate side new wall | 0 | 1.7
|  |  | 0.14 |  | 1.7 | 0.238 | [5 empty] | 0.14 | 1.7
|  |  | 3.01 |  | 1.6 | 4.816 | [5 empty] | 3.01 | 1.6
|  |  | 0.58 |  | 1.7 | 0.986 | [5 empty] | 0.58 | 1.7
|  |  | 3.12 |  | 1.64 | 5.1168 | [5 empty] | 3.12 | 1.64
|  |  | 0.6 |  | 1.65 | 0.99 | [5 empty] | 0.6 | 1.65
|  |  | 3.16 |  | 1.65 | 5.214 | [5 empty] | 3.16 | 1.65
|  |  | 0.66 |  | 1.65 | 1.089 | [5 empty] | 0.66 | 1.65
|  |  | 2.96 |  | 1.71 | 5.0616 | [5 empty] | 2.96 | 1.71
|  |  | 0.62 |  | 1.72 | 1.0664 | [5 empty] | 0.62 | 1.72
|  |  | 2.96 |  | 1.735 | 5.1356 | [5 empty] | 2.96 | 1.735
|  |  | 0.63 |  | 1.7 | 1.071 | [5 empty] | 0.63 | 1.7
|  |  | 2.92 |  | 1.635 | 4.7742 | [5 empty] | 2.92 | 1.635
|  |  | 0.61 |  | 1.6 | 0.976 | [5 empty] | 0.61 | 1.6
|  |  | 0.44 |  | 1.55 | 0.682 |  |  |  |  | upto gate | 0.44 | 1.55
[11 empty] | back compound inner face wall | 0 | 1.5
|  |  | 3 |  | 1.5 | 4.5 | [5 empty] | 3 | 1.5
|  |  | 3 |  | 1.525 | 4.575 | [5 empty] | 3 | 1.55
|  |  | 3 |  | 1.55 | 4.65 | [5 empty] | 3 | 1.55
|  |  | 3 |  | 1.55 | 4.65 | [5 empty] | 3 | 1.55
|  |  | 3 |  | 1.635 | 4.905 | [5 empty] | 3 | 1.72
|  |  | 3.06 |  | 1.65 | 5.049 | [5 empty] | 3.06 | 1.65
|  |  | 0.16 |  | 1.61 | 0.2576 |  |  |  |  | break point of old wall and new wall | 0.16 | 1.61
| -window | 10 | 0.83816 |  | 1.2 | 10.0579 |  |  |  |  | old wall | 0 | 1.6
|  |  | 0.6 |  | 1.6 | 0.96 | [5 empty] | 0.6 | 1.6
|  |  | 15 |  | 0.2 | 3 |  |  |  |  | inner face complete | 15 | 0.2
[11 empty] | outside face of back compound | 0 | 1.75 | DPC to top of new wall
|  |  | 4 |  | 1.75 | 7 | [5 empty] | 4 | 1.75
|  |  | 4 |  | 1.75 | 7 | [5 empty] | 4 | 1.75
|  |  | 4.21 |  | 1.75 | 7.3675 | [5 empty] | 4.21 | 1.75 | new wall complete
|  |  | 0.49 |  | 2.1 | 1.029 | [5 empty] | 0.49 | 2.1 | old wall starts
|  |  | 0 |  | 2.1 | 0 | [5 empty] | 0 | 2.1
|  |  | 3.17 |  | 2.1 | 6.657 | [5 empty] | 3.17 | 2.1
|  |  | 0.48 |  | 2.1 | 1.008 | [5 empty] | 0.48 | 2.1
|  |  | 3.11 |  | 2.1 | 6.531 | [5 empty] | 3.11 | 2.1
|  |  | 0.6 |  | 2.1 | 1.26 | [5 empty] | 0.6 | 2.1
|  |  | 3.1 |  | 2.1 | 6.51 | [5 empty] | 3.1 | 2.1
|  |  | 0.6 |  | 2.1 | 1.26 | [5 empty] | 0.6 | 2.1
|  |  | 3.11 |  | 2.155 | 6.7021 | [5 empty] | 3.11 | 2.155
|  |  | 0.6 |  | 2.2 | 1.32 | [5 empty] | 0.6 | 2.2
|  |  | 3.1 |  | 2.24 | 6.944 | [5 empty] | 3.1 | 2.24
|  |  | 0.58 |  | 2.2 | 1.276 | [5 empty] | 0.58 | 2.2
|  |  | 3.15 |  | 2.275 | 7.1662 | [5 empty] | 3.15 | 2.275
|  |  | 3.25 |  | 2.3 | 7.475 | [5 empty] | 3.25 | 2.3
|  |  | 0.57 |  | 2.3 | 1.311 | [5 empty] | 0.57 | 2.3
|  |  | 0.97 |  | 2.3 | 2.231 | [5 empty] | 0.97 | 2.3
[11 empty] | baniya gaun baato to gate side | 0 | 1.76
|  |  | 0.48 |  | 1.75 | 0.84 | [5 empty] | 0.48 | 1.75
|  |  | 2.75 |  | 1.75 | 4.8125 | [5 empty] | 2.75 | 1.75
|  |  | 0.57 |  | 1.75 | 0.9975 | [5 empty] | 0.57 | 1.75
|  |  | 2.65 |  | 1.775 | 4.7037 | [5 empty] | 2.65 | 1.8
|  |  | 0.58 |  | 1.8 | 1.044 | [5 empty] | 0.58 | 1.8
|  |  | 1.16 |  | 1.8 | 2.088 | [5 empty] | 1.16 | 1.8
|  |  | 0.6 |  | 1.8 | 1.08 | [5 empty] | 0.6 | 1.8
|  |  | 2.7431 |  | 1.8 | 4.9375 | [5 empty] | 2.7431 | 1.8
|  |  | 0.58 |  | 2.1335 | 1.2374 | [5 empty] | 0.58 | 2.1335
| -Chautari | 1 | 15 |  | 0.45 | 6.75
| Sub-total |  |  |  |  | 219.307 | sqm | 405.86 | 89007.9414
| VAT calculation | [7 empty] | 3183.4737
11 | $=% X @) dL=dL= kmnfd] kftfsf] k¦m]ddf !@ x !@ dL=dL=;f]ln8 sf]/ :Sjfo/ /8sf] lu¦n agfO{ vfS;L nufO{ /]8cS;fO8 tyf cNd'lgod k]G6 ;d]t u/L hf]8\g]
| -window | 6 | 1.2 |  | 1.6519 | 11.8939
| Sub-total |  |  |  |  | 11.8939 | sqm | 2575.34 | 30630.926 |  | 28262.52
| VAT calculation | [7 empty] | 3764.0911
12 | lh=cfO{=sf9]tf/ -jf/ j]8 jfo/_ nufpg] .
| -at boundary | 0 | 95.5523 |  |  | 0
| Sub-total |  |  |  |  | 0 | rm | 82.59 | 0
| VAT calculation | [7 empty] | 0
13 | %) dL=dL=Aof;sf] :6]Gn];l:6nsf] x\of08/]ndf @ ld6/sf] b"/Ldf %) dL=dL=Aof;sf] :6]Gn];l:6ns} 7f8f] kf]i6 /fvL x\of08/]n / e"O+sf] aLrdf tLg tx t];f]{ @% dL=dL=Aof;sf] :6]Gn];l:6nsf] d]Da/ /fvL @Ú–^Æ b]lv #Ú–)Æ ;Dd prfO{ ePsf] /]lnË pknAw u/fO{ h8fg u/L /+u ;d]t nufpg] sfd .
| -at boundary | 0 | 7.8735 |  |  | 0
| Sub-total |  |  |  |  | 0 | rm | 4132.8 | 0
| VAT calculation | [7 empty] | 0
14 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd |  | Area (m2)
| -wall | 1 | 219.307 |  |  | 219.307
| Sub-total |  |  |  |  | 219.307 | sqm | 251.77 | 55214.9249
| VAT calculation | [7 empty] | 3631.0222
15 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (Kg) |  |  |  | by actual measurement in digital weighing machine
| -MS Equal angle of 35mm*35mm*2mm For door | 0 | 8.1271 | 1.04 | 0 | 0 |  |  |  |  | 279
| -MS sheet 900mm wide or as per required and of 14G with 2mm | 2 |  |  | 61 | 61
| -MS Rectangular Hollow section of 40mm*25mm*2.2mm for window | 6 | 2.54 | 2 | 30.48 | 30.48
| Sub-total |  |  |  |  | 91.48 | Kg | 181.17 | 16573.4316
| VAT calculation | [7 empty] | 1175.062
16 | kmnfd] sf]nfK;Lan u]6 k]lG6Ë / h8fg ;d]t ug]{
| -at block D | 0 | 3.23 |  | 2.535 | 0
| Sub-total |  |  |  |  | 0 | sqm | 6391.43 | 0
| VAT calculation | [7 empty] | 0
17 | Provisional sum for unforseen works | 0 |  |  |  | 0 | PS | 5000 | 0
18 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 558216.4969
| Total Estimated | 558216.4969 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 85.0924
| User Contribution | 83216.4969 |  | 14.9076
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on C11: Windows User: white wall

## M
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- राष्ट्रिय मा. बि. वाल निर्माण | [9 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [9 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
| -White wall | 1 | 3.88 | 0.1 | 2.2859 | 0.88692
|  | 3 | 0.3566 | 0.3566 | 2.2859 | 0.87204 | [5 empty] | kmnfd] sfd -Rofgn PËn 6L cflb_ x6fpg] sfo{ lemSg], 5'6\ofpg] / /fd¦/L yGsfpg] ;d]t
| -at backyard wall | 1 | 11.73 | 0.23 | 1.15 | 3.1026
| Sub-total |  |  |  |  | 4.8615 | m3 | 1950 | 9480.0186
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
| -White wall | 1 | 10.3373 | 0.45 | 0.6 | 2.7911
| Sub-total |  |  |  |  | 2.7911 | m3 | 64.63 | 180.3868
| VAT calculation | [7 empty] | 19.4361
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -at backyard wall | 2 | 0.9 | 0.9 | 0.33 | 0.5346
| Sub-total |  |  |  |  | 0.5346 | m3 | 663.31 | 354.6055
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing | 2 | 0.9 | 0.9 |  | 1.62
| -at front wall | 2 | 9.2959 | 0.23 |  | 4.2761
|  | 6 | 0.35558 | 0.35558 |  | 0.75863
| Sub-total |  |  |  |  | 6.6548 | sqm | 1014.97 | 6754.3913
| VAT calculation | [7 empty] | 745.4912
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| -at front wall | 2 | 9.2959 | 0.23 | 0.075 | 0.32071
|  | 6 | 0.35558 | 0.35558 | 0.075 | 0.056898
| -at backyard wall | 1 | 11.73 | 0.23 | 0.075 | 0.20234
| Sub-total |  |  |  |  | 0.57995 | m3 | 12983.1 | 7529.5515
| VAT calculation | [7 empty] | 609.0372
6 | ;'k/ :6«Sr/, 8]s :n]a ljdx?df l;d]G6 s+lqm6 ug]{ sfd -!M!.%M#_
| -for footing | 2 | 0.9 | 0.9 | 0.15 | 0.243
|  | 2 | 0.23 | 0.23 | 2.3621 | 0.24991
| Sub-total |  |  |  |  | 0.49291 | m3 | 16512.62 | 8139.2118
| VAT calculation | [7 empty] | 582.6379
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -for footing | 2 | 0.9 |  | 0.15 | 0.27
|  | 2 | 0.92 |  | 2.3621 | 4.3462
| Sub-total |  |  |  |  | 4.6162 | m2 | 915.42 | 4225.7947
| VAT calculation | [7 empty] | 281.019
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For column footing | 22 | 0.6 | 0.88889 | 11.7333 | 0.011733
| -For column | 8 | 2.8955 | 0.88889 | 20.5899 | 0.02059
| -For column stirrups | 16 | 0.71117 | 0.39506 | 4.4953 | 0.0044953
| Sub-total |  |  |  |  | 0.036819 | MT | 131940 | 4857.8367
| VAT calculation | [7 empty] | 508.3166
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | [11 empty] | 37.666
| -wall at backyard | 1 | 11.73 | 0.23 | 1.675 | 4.519
| -deduction for column part | -2 | 0.23 | 0.23 | 1.675 | -0.17722
| -wall at front | 1 | 2.9717 | 0.23 | 2.1336 | 1.4583
|  | 1 | 0.35558 | 0.35558 | 2.1336 | 0.26977
|  | 1 | 2.9717 | 0.23 | 2.1336 | 1.4583
|  | 1 | 0.35558 | 0.35558 | 2.1336 | 0.26977
|  | 1 | 2.9717 | 0.23 | 2.1336 | 1.4583
|  | 1 | 0.35558 | 0.35558 | 2.1336 | 0.26977
|  | 1 | 0.43178 | 0.1 | 2.1336 | 0.092125
|  | 1 | 10.4135 | 0.45 | 0.23 | 1.0778
|  | 2 | 0.9 | 0.45 | 0.3 | 0.243
| Sub-total |  |  |  |  | 10.9389 | m3 | 14362.76 | 157112.5973
| VAT calculation | [7 empty] | 14663.8636
10 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df k'/fgf] O6\6f @% k¦ltzt | [11 empty] | 37.666
| -window top cover at backyard | 1 | 17.1 | 0.23 | 0.125 | 0.49163 |  |  |  |  | 21.49
| -front side right part of gate | 1 | 0.35558 | 0.35558 | 0.12 | 0.015173
|  | 1 | 2.75 | 0.23 | 0.12 | 0.0759
|  | 1 | 0.35558 | 0.35558 | 0.12 | 0.015173
|  | 1 | 2.69 | 0.23 | 0.12 | 0.074244
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 0.95 | 0.23 | 0.12 | 0.02622
|  | 1 | 2.73 | 0.23 | 0.25 | 0.15698
|  | 1 | 0.58 | 0.23 | 0.6 | 0.08004
| -front side left part of gate | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 3.02 | 0.23 | 0.12 | 0.083352
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 3.13 | 0.23 | 0.12 | 0.086388
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
|  | 1 | 3.17 | 0.23 | 0.12 | 0.087492
|  | 1 | 0.3556 | 0.3556 | 0.12 | 0.015174
| -window backyard | 12 | 0.83 | 0.23 | 1.2 | 2.749
| Sub-total |  |  |  |  | 4.0174 | m3 | 8001.86 | 32146.7698
| VAT calculation | [7 empty] | 2063.3799
11 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/ | [9 empty] | inner face of gate side wall | 0 | 1.3
| -wall | 1 | 3 |  | 1.37 | 4.11 | [5 empty] | 3 | 1.44
|  | 1 | 3 |  | 1.41 | 4.23 | [5 empty] | 3 | 1.38
|  | 1 | 3 |  | 1.415 | 4.245 | [5 empty] | 3 | 1.45
|  | 1 | 3 |  | 1.455 | 4.365 | [5 empty] | 3 | 1.46
|  | 1 | 3 |  | 1.505 | 4.515 | [5 empty] | 3 | 1.55
|  | 1 | 3 |  | 1.485 | 4.455 | [5 empty] | 3 | 1.42
|  | 1 | 3.42 |  | 1.47 | 5.0274 |  |  |  |  | upto inner face to gate | 3.42 | 1.52
[11 empty] | outer face of gate side new wall | 0 | 1.7
|  | 1 | 0.14 |  | 1.7 | 0.238 | [5 empty] | 0.14 | 1.7
|  | 1 | 3.01 |  | 1.6 | 4.816 | [5 empty] | 3.01 | 1.6
|  | 1 | 0.58 |  | 1.7 | 0.986 | [5 empty] | 0.58 | 1.7
|  | 1 | 3.12 |  | 1.64 | 5.1168 | [5 empty] | 3.12 | 1.64
|  | 1 | 0.6 |  | 1.65 | 0.99 | [5 empty] | 0.6 | 1.65
|  | 1 | 3.16 |  | 1.65 | 5.214 | [5 empty] | 3.16 | 1.65
|  | 1 | 0.66 |  | 1.65 | 1.089 | [5 empty] | 0.66 | 1.65
|  | 1 | 2.96 |  | 1.71 | 5.0616 | [5 empty] | 2.96 | 1.71
|  | 1 | 0.62 |  | 1.72 | 1.0664 | [5 empty] | 0.62 | 1.72
|  | 1 | 2.96 |  | 1.735 | 5.1356 | [5 empty] | 2.96 | 1.735
|  | 1 | 0.63 |  | 1.7 | 1.071 | [5 empty] | 0.63 | 1.7
|  | 1 | 2.92 |  | 1.635 | 4.7742 | [5 empty] | 2.92 | 1.635
|  | 1 | 0.61 |  | 1.6 | 0.976 | [5 empty] | 0.61 | 1.6
|  | 1 | 0.44 |  | 1.55 | 0.682 |  |  |  |  | upto gate | 0.44 | 1.55
[11 empty] | back compound inner face wall | 0 | 1.5
|  | 1 | 3 |  | 1.525 | 4.575 | [5 empty] | 3 | 1.55
|  | 1 | 3 |  | 1.55 | 4.65 | [5 empty] | 3 | 1.55
|  | 1 | 3 |  | 1.635 | 4.905 | [5 empty] | 3 | 1.72
|  | 1 | 3.06 |  | 1.65 | 5.049 | [5 empty] | 3.06 | 1.65
|  | 1 | 0.16 |  | 1.61 | 0.2576 |  |  |  |  | break point of old wall and new wall | 0.16 | 1.61
| -window | 10 | 0.83816 |  | 1.2 | 10.0579 |  |  |  |  | old wall | 0 | 1.6
|  | 1 | 0.6 |  | 1.6 | 0.96 | [5 empty] | 0.6 | 1.6
|  | 1 | 15.5 |  | 0.2 | 3.1 |  |  |  |  | inner face complete | 15.5 | 0.2
[11 empty] | outside face of back compound | 0 | 1.75 | DPC to top of new wall
|  | 1 | 4 |  | 1.75 | 7 | [5 empty] | 4 | 1.75
|  | 1 | 4 |  | 1.75 | 7 | [5 empty] | 4 | 1.75
|  | 1 | 4.21 |  | 1.75 | 7.3675 | [5 empty] | 4.21 | 1.75 | new wall complete
|  | 1 | 0.49 |  | 2.1 | 1.029 | [5 empty] | 0.49 | 2.1 | old wall starts
|  | 1 | 0 |  | 2.1 | 0 | [5 empty] | 0 | 2.1
|  | 1 | 3.17 |  | 2.1 | 6.657 | [5 empty] | 3.17 | 2.1
|  | 1 | 0.48 |  | 2.1 | 1.008 | [5 empty] | 0.48 | 2.1
|  | 1 | 3.11 |  | 2.1 | 6.531 | [5 empty] | 3.11 | 2.1
|  | 1 | 0.6 |  | 2.1 | 1.26 | [5 empty] | 0.6 | 2.1
|  | 1 | 3.1 |  | 2.1 | 6.51 | [5 empty] | 3.1 | 2.1
|  | 1 | 0.6 |  | 2.1 | 1.26 | [5 empty] | 0.6 | 2.1
|  | 1 | 3.11 |  | 2.155 | 6.7021 | [5 empty] | 3.11 | 2.155
|  | 1 | 0.6 |  | 2.2 | 1.32 | [5 empty] | 0.6 | 2.2
|  | 1 | 3.1 |  | 2.24 | 6.944 | [5 empty] | 3.1 | 2.24
|  | 1 | 0.58 |  | 2.2 | 1.276 | [5 empty] | 0.58 | 2.2
|  | 1 | 3.15 |  | 2.275 | 7.1662 | [5 empty] | 3.15 | 2.275
|  | 1 | 3.25 |  | 2.3 | 7.475 | [5 empty] | 3.25 | 2.3
|  | 1 | 0.57 |  | 2.3 | 1.311 | [5 empty] | 0.57 | 2.3
|  | 1 | 0.97 |  | 2.3 | 2.231 | [5 empty] | 0.97 | 2.3
[11 empty] | baniya gaun baato to gate side | 0 | 1.76
|  | 1 | 0.48 |  | 1.75 | 0.84 | [5 empty] | 0.48 | 1.75
|  | 1 | 2.75 |  | 1.75 | 4.8125 | [5 empty] | 2.75 | 1.75
|  | 1 | 0.57 |  | 1.75 | 0.9975 | [5 empty] | 0.57 | 1.75
|  | 1 | 2.65 |  | 1.775 | 4.7037 | [5 empty] | 2.65 | 1.8
|  | 1 | 0.58 |  | 1.8 | 1.044 | [5 empty] | 0.58 | 1.8
|  | 1 | 1.16 |  | 1.8 | 2.088 | [5 empty] | 1.16 | 1.8
|  | 1 | 0.6 |  | 1.8 | 1.08 | [5 empty] | 0.6 | 1.8
|  | 1 | 2.7431 |  | 1.8 | 4.9375 | [5 empty] | 2.7431 | 1.8
|  | 1 | 0.58 |  | 2.1335 | 1.2374 | [5 empty] | 0.58 | 2.1335
|  | 2 | 0.9 |  | 0.3 | 0.54
| -Chautari | 1 | 15 |  | 0.45 | 6.75
| Sub-total |  |  |  |  | 210.797 | sqm | 405.86 | 85554.0728
| VAT calculation | [7 empty] | 3059.942
12 | $=% X @) dL=dL= kmnfd] kftfsf] k¦m]ddf !@ x !@ dL=dL=;f]ln8 sf]/ :Sjfo/ /8sf] lu¦n agfO{ vfS;L nufO{ /]8cS;fO8 tyf cNd'lgod k]G6 ;d]t u/L hf]8\g]
| -window | 6 | 1.2 |  | 1.6519 | 11.8939
| Sub-total |  |  |  |  | 11.8939 | sqm | 2575.34 | 30630.926 |  | 28262.52
| VAT calculation | [7 empty] | 3764.0911
13 | lh=cfO{=sf9]tf/ -jf/ j]8 jfo/_ nufpg] .
| -at boundary | 3 | 90 |  |  | 270
| Sub-total |  |  |  |  | 270 | rm | 82.59 | 22299.3
| VAT calculation | [7 empty] | 699.2411
14 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd |  | Area of plaster (m2)
| -wall | 1 | 210.797 |  |  | 210.797
| -deduction for incomplete ones | [9 empty] | back compound inner face wall | 0 | 1.5
|  | -1 | 3 |  | 1.525 | -4.575 | [5 empty] | 3 | 1.55
|  | -1 | 3 |  | 1.55 | -4.65 | [5 empty] | 3 | 1.55
|  | -1 | 3 |  | 1.635 | -4.905 | [5 empty] | 3 | 1.72
|  | -1 | 3.06 |  | 1.65 | -5.049 | [5 empty] | 3.06 | 1.65
|  | -1 | 0.16 |  | 1.61 | -0.2576 |  |  |  |  | break point of old wall and new wall | 0.16 | 1.61
| -window | -10 | 0.83816 |  | 1.2 | -10.0579 |  |  |  |  | old wall | 0 | 1.6
|  | -1 | 0.6 |  | 1.6 | -0.96 | [5 empty] | 0.6 | 1.6
|  | -1 | 15 |  | 0.2 | -3 |  |  |  |  | inner face complete | 15 | 0.2
[11 empty] | outside face of back compound | 0 | 1.75 | DPC to top of new wall
|  | -1 | 4 |  | 1.75 | -7 | [5 empty] | 4 | 1.75
|  | -1 | 4 |  | 1.75 | -7 | [5 empty] | 4 | 1.75
|  | -1 | 4.21 |  | 1.75 | -7.3675 | [5 empty] | 4.21 | 1.75 | new wall complete
|  | -1 | 0.49 |  | 2.1 | -1.029 | [5 empty] | 0.49 | 2.1 | old wall starts
|  | -1 | 0 |  | 2.1 | 0 | [5 empty] | 0 | 2.1
|  | -1 | 3.17 |  | 2.1 | -6.657 | [5 empty] | 3.17 | 2.1
|  | -1 | 0.48 |  | 2.1 | -1.008 | [5 empty] | 0.48 | 2.1
|  | -1 | 3.11 |  | 2.1 | -6.531 | [5 empty] | 3.11 | 2.1
|  | -1 | 0.6 |  | 2.1 | -1.26 | [5 empty] | 0.6 | 2.1
|  | -1 | 3.1 |  | 2.1 | -6.51 | [5 empty] | 3.1 | 2.1
|  | -1 | 0.6 |  | 2.1 | -1.26 | [5 empty] | 0.6 | 2.1
|  | -1 | 3.11 |  | 2.155 | -6.7021 | [5 empty] | 3.11 | 2.155
|  | -1 | 0.6 |  | 2.2 | -1.32 | [5 empty] | 0.6 | 2.2
|  | -1 | 3.1 |  | 2.24 | -6.944 | [5 empty] | 3.1 | 2.24
|  | -1 | 0.58 |  | 2.2 | -1.276 | [5 empty] | 0.58 | 2.2
|  | -1 | 3.15 |  | 2.275 | -7.1662 | [5 empty] | 3.15 | 2.275
|  | -1 | 3.25 |  | 2.3 | -7.475 | [5 empty] | 3.25 | 2.3
|  | -1 | 0.57 |  | 2.3 | -1.311 | [5 empty] | 0.57 | 2.3
|  | -1 | 0.97 |  | 2.3 | -2.231 | [5 empty] | 0.97 | 2.3
| -old part | 1 | 1.93 |  | 2.63 | 5.0759
| Sub-total |  |  |  |  | 102.3706 | sqm | 251.77 | 25773.8451
| VAT calculation | [7 empty] | 1694.9295
15 | c:t/ jfx]s Pssf]6 tof/L Ogfd]n k]G6 ug]{ sfd .
| -gate | 2 | 2.28 |  | 1.97 | 8.9832
|  | 1 | 0.89 |  | 2.13 | 1.8957
| Sub-total |  |  |  |  | 10.8789 | sqm | 128.43 | 1397.1771
| VAT calculation | [7 empty] | 68.9875
16 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{ | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (Kg) |  |  |  | by actual measurement in digital weighing machine at site
| -metal door with MS sheet 900mm wide or as per required and of 14G including frames | 2 |  |  | 61.25 | 61.25
| -deduction for MS sheet 900mm wide or as per required and of 14G thick | -1 | 0.515 | 14.14 | -7.2821 | -7.2821
| -MS Rectangular Hollow section of 40mm*25mm*2.2mm for window | 6 | 2.54 | 2 | 30.48 | 30.48
|  | 4 | 0.47 | 2 | 3.76 | 3.76
| -MS equal angle of size 50mm*50mm of thickness 3mm | 30 | 0.6 | 2.22 | 39.96 | 39.96
| Sub-total |  |  |  |  | 128.1679 | Kg | 181.17 | 23220.1784
| VAT calculation | [7 empty] | 1646.3187
17 | %) dL=dL=Aof;sf] :6]Gn];l:6nsf] x\of08/]ndf @ ld6/sf] b"/Ldf %) dL=dL=Aof;sf] :6]Gn];l:6ns} 7f8f] kf]i6 /fvL x\of08/]n / e"O+sf] aLrdf tLg tx t];f]{ @% dL=dL=Aof;sf] :6]Gn];l:6nsf] d]Da/ /fvL @Ú–^Æ b]lv #Ú–)Æ ;Dd prfO{ ePsf] /]lnË pknAw u/fO{ h8fg u/L /+u ;d]t nufpg] sfd .
| -at boundary | 0 | 7.8735 |  |  | 0
| Sub-total |  |  |  |  | 0 | rm | 4132.8 | 0
| VAT calculation | [7 empty] | 0
18 | kmnfd] sf]nfK;Lan u]6 k]lG6Ë / h8fg ;d]t ug]{
| -at block D | 0 | 3.23 |  | 2.535 | 0
| Sub-total |  |  |  |  | 0 | sqm | 6391.43 | 0
| VAT calculation | [7 empty] | 0
19 | Provisional sum for unforseen works | 0 |  |  |  | 0 | PS | 5000 | 0
20 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 450563.3551
| Total Estimated | 450563.3551 |  | 100
| Budget allocated | 500000
| Municipal payment | 367930.0358 |  | 81.66
| User Contribution | 82633.3193 |  | 18.34
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on C11: Windows User: white wall
Note on C32: DELL: Must be value 2 so instead 1 if required use 2

## Sheet2
e'O{tNnfdf lrDgL e§fsf] O{6f pknAw ug]{,
l;d]G6 d;nf -!M^_ tof/ u/L uf/f] nufpg]
sfd #) dL6/;Dd 9'jfgL ;lxt
b/ ljZn]if0fsf] nflu ! 3=ld= lnOPsf]
;¦f]t ;fwg | tx÷lsl;d | kl/df0f | PsfO{ | b/ k¦lt PsfO{ | /sd | k¦To]s ;¦f]t ;fwgsf] hDdf
>lds | s_ l;kfn' | 1.5 | hjfg | 1225 | 1837.5
| v_ HofdL | 2.2 | hjfg | 920 | 2024
| u_ HofdL | 0.2 | hjfg | 920 | 184 | 4045.5
| O{6f | 560 | uf]6f | 15.145 | 8481.2
lgdf{0f ;fdu¦L | l;d]G6 | 0.07 | d]=6= | 12131 | 849.17
| afn'jf vf]nfsf] | 0.3 | 3=dL= | 3177.9 | 953.37
| kfgL | 100 | nL6/ | 0.28 | 28 | 10311.74
| v6sf] ;ffdfg | -u_ sf] #Ü n] |  |  |  | 5.52
|  |  |  | jf:tljs b//]6 |  | 14362.76
| b/ k¦lt 3=dL=sf] |  |  | !%Ü 7]s]bf/ cf]e/x]8 |  | 2154.41
?= | 16517.17 |  |  | hDdf b/ /]6 |  | 16517.17
;¦f]t ;fwg | tx÷lsl;d | kl/df0f | PsfO{ | b/ k¦lt PsfO{ | /sd | k¦To]s ;¦f]t ;fwgsf] hDdf
>lds | s_ l;kfn' | 1.5 | hjfg | 1225 | 1837.5
| v_ HofdL | 2.2 | hjfg | 920 | 2024
| u_ HofdL | 0.2 | hjfg | 920 | 184 | 4045.5
| O{6f | 140 | uf]6f | 15.145 | 2120.3
| k'/fgf] O{6f | 420 | uf]6f | 0 | 0
lgdf{0f ;fdu¦L | l;d]G6 | 0.07 | d]=6= | 12131 | 849.17
| afn'jf vf]nfsf] | 0.3 | 3=dL= | 3177.9 | 953.37
| kfgL | 100 | nL6/ | 0.28 | 28 | 3950.84
| v6sf] ;ffdfg | -u_ sf] #Ü n] |  |  |  | 5.52
|  |  |  | jf:tljs b//]6 |  | 8001.86
| b/ k¦lt 3=dL=sf] |  |  | !%Ü 7]s]bf/ cf]e/x]8 |  | 1200.27
?= | 9202.13 |  |  | hDdf b/ /]6 |  | 9202.13

## Sheet1 (hidden)
S.No. | Description of work
1 | l;d]G6 jf jh¦df hf]8]sf] uf/f] eTsfO{ To;af6 cfPsf] ;fdfu+¦L !) dL= x6fpg] sfd .
2 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
6 | ;'k/ :6«Sr/, 8]s :n]a ljdx?df l;d]G6 s+lqm6 ug]{ sfd -!M!.%M#_
7 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
8 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
10 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
11 | $=% X @) dL=dL= kmnfd] kftfsf] k¦m]ddf !@ x !@ dL=dL=;f]ln8 sf]/ :Sjfo/ /8sf] lu¦n agfO{ vfS;L nufO{ /]8cS;fO8 tyf cNd'lgod k]G6 ;d]t u/L hf]8\g]
12 | lh=cfO{=sf9]tf/ -jf/ j]8 jfo/_ nufpg] .
13 | %) dL=dL=Aof;sf] :6]Gn];l:6nsf] x\of08/]ndf @ ld6/sf] b"/Ldf %) dL=dL=Aof;sf] :6]Gn];l:6ns} 7f8f] kf]i6 /fvL x\of08/]n / e"O+sf] aLrdf tLg tx t];f]{ @% dL=dL=Aof;sf] :6]Gn];l:6nsf] d]Da/ /fvL @Ú–^Æ b]lv #Ú–)Æ ;Dd prfO{ ePsf] /]lnË pknAw u/fO{ h8fg u/L /+u ;d]t nufpg] sfd .
14 | Ps sf]6 k¦fO{d/ ;lxt b'O{ sf]6 j]b/sf]6 k]G6 ug]{ sfd
15 | ljleGg ;fO{hsf] kmnfd] PËn km]lj¦s]zg u/L k¦fOd/ k]G6 ;lxt ug]{
16 | kmnfd] sf]nfK;Lan u]6 k]lG6Ë / h8fg ;d]t ug]{
17 | Provisional sum for unforseen works
18 | Information board (सुचना पाटि)