## Estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- सेतीदेवी मन्दिर जाने बाटो निर्माण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/29
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
|  | 0.5 | 15 | 4 | 3 | 90
| Sub-total |  |  |  |  | 90 | m3 | 663.31 | 59697.9
2 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance
|  | 4 | 15 | 0.38 | 40 | 160
| Sub-total |  |  |  |  | 160 | sack | 92 | 14720
| VAT calculation | [7 empty] | 1913.6
3 | Providing and laying Bamboo for the protection all complete
| -vertical post | 22 | 6 |  |  | 132
| -horizontal post | 3 | 10 |  |  | 30
| Sub-total |  |  |  |  | 27 | No. | 240 | 6480
| VAT calculation | [7 empty] | 842.4
4 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 84153.9
| Total Estimated | 84153.9 |  | 100
| Budget allocated | 250000
| Municipal payment | 237500 |  | 282.221
| User Contribution | -153346.1 |  | -182.221
| Contingencies | 7500 |  | 3
| Maintanince | 5000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | #REF! |  |  |  |  | Total Valuated Amount : |  | 283710.374
Work Started : | [7 empty] | Work Finished:
#REF! | [7 empty] | F.Y:2081/2082
#REF! | [7 empty] | Date:2081/10/24
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 15.003 | 663.31 | 9951.6399 | #REF! |  |  | #REF!
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | m3 | 90 | 663.31 | 59697.9 | 101.6374 | 6.52 | 662.6758 | -59035.2242 |  |  | 74622.375
2 | Filling empty bags with local sand, sewing them closes and pacing them including haulage upto 100 m distance | sack | 160 | 92 | 14720 | 1.84 | 1014.97 | 1867.5448 | -12852.4552 |  |  | 18400
| VAT calculation |  |  |  | 1913.6 |  |  | 206.1234 | -1707.4766 |  |  | 2392
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0.184 | 10634.5 | 1956.748 | #REF! |  |  | #REF!
| #REF! |  |  |  | #REF! |  |  | 193.0226 | #REF! |  |  | #REF!
3 | Providing and laying Bamboo for the protection all complete | #REF! | #REF! | #REF! | #REF! | 1.3785 | 14362.76 | 19798.562 | #REF! |  |  | #REF!
| VAT calculation |  |  |  | 842.4 |  |  | 1847.8684 | 1005.4684 |  |  | 1053
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 135 | 1737.28 | 234532.8 | #REF! |  |  | #REF!
| #REF! |  |  |  | #REF! |  |  | 12193.389 | #REF! |  |  | #REF!
4 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0 |  |  | 625
| Total |  |  |  | #REF! |  |  | 283710.374 | #REF!
[10 empty] | 1070 | 70.2278 | 75143.7929

## Valuation
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- सेतीदेवी मन्दिर जाने बाटो निर्माण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/29
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -Road | 1 | 67.5 | 0.21 | 1 | 14.175
| -For wall | 1 | 8 | 0.23 | 0.45 | 0.828
| Sub-total |  |  |  |  | 15.003 | m3 | 663.31 | 9951.6399
2 | l;d]G6 d;nfsf] uf/f]af6 O{6f lemls nfu]sf] d;nf ;kmf ug]{ tyf k'gM k¦of]u ug]{ ;lsg] u/L yGsfpg] sfd .
| -Road | 1 | 1.9049 | 0.1 | 1 | 53.3374
|  | 1 | 0.75 | 0.23 | 1 | 48.3
| Sub-total |  |  |  |  | 101.6374 | m3 | 6.52 | 662.6758
3 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -Road | 1 | 8 | 0.23 |  | 1.84
| Sub-total |  |  |  |  | 1.84 | sqm | 1014.97 | 1867.5448
| VAT calculation | [7 empty] | 206.1234
4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -for wall at entrance | 1 | 8 | 0.23 | 0.05 | 0.092
|  | 1 | 8 | 0.23 | 0.05 | 0.092
| Sub-total |  |  |  |  | 0.184 | m3 | 10634.5 | 1956.748
| VAT calculation | [7 empty] | 193.0226
5 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -Side wall | 0.5 | 4.85 | 0.1 | 0.65 | 0.15762
|  | 1 | 2.44 | 0.23 | 0.7 | 0.39284
| -at entrance | 1 | 8 | 0.23 | 0.45 | 0.828
| Sub-total |  |  |  |  | 1.3785 | m3 | 14362.76 | 19798.562
| VAT calculation | [7 empty] | 1847.8684
6 | dfn;fdfg pknAw u/L %) dL=dL= df]6f] x]eL 8o"6L OG6/nls+u s+lqm6Ans %) dL=dL=df]6fOsf] qm;/ 8:6 dfyL /fvL la5ofpg]] sfd k'/f
| -for flooring | 1 | 67.5 | 2 |  | 135
| Sub-total |  |  |  |  | 135 | m2 | 1737.28 | 234532.8
| VAT calculation | [7 empty] | 12193.389
7 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 283710.374
| Total Valuated | 283710.374 |  | 100
| Budget allocated | 250000
| Municipal payment | 237500 |  | 83.7121
| User Contribution | 46210.374 |  | 16.2879
| Contingencies | 7500 |  | 3
| Maintanince | 5000 |  | 2

## Sheet3
chainage | Length | Width | Avg. Width
0+000 | 0 | 2.1
0+004.5 | 4.5 | 2.1 | 2.1
0+004.5 to 0+009 | 4.5 | 2 | 2.05 |  | Amount | VAT | With VAT
0+009 to 0+013.5 | 4.5 | 2 | 2 | Brick | 12861.443 | 1671.9876 | 14533.4305
0+013.5 to 0+018 | 4.5 | 2.1 | 2.05 | sand | 1992.2529 | 258.9929 | 2251.2458
0+018 to 0+022.5 | 4.5 | 2.1 | 2.1 | cement | 1774.9915 | 230.7489 | 2005.7404
0+022.5 to 0+027 | 4.5 | 2.1 | 2.1 | aggregate | 534.5767 | 69.495 | 604.0716
0+027 to 0+031.5 | 4.5 | 2.1 | 2.1 | water | 46.2024 | 6.0063 | 52.2087
0+031.5 to 0+036 | 4.5 | 2.1 | 2.1 | formwork | 75.2597 | 9.7838 | 85.0434
0+036 to 0+040.5 | 4.5 | 2.1 | 2.1 | interlock | 81490.86 | 10593.8118 | 92084.6718
0+040.5 to 0+045 | 4.5 | 2.1 | 2.1 | stone dust | 12304.44 | 1599.5772 | 13904.0172
0+045 to 0+049.5 | 4.5 | 2.1 | 2.1
0+049.5 to 0+054 | 4.5 | 2.1 | 2.1 |  | 111080.0261 | 14440.4034
0+054 to 0+058.5 | 4.5 | 2.1 | 2.1 | valuated |  | 14440.4035
0+058.5 to 0+063 | 4.5 | 2.1 | 2.1
0+063 to 0+067.5 | 4.5 | 2.15 | 2.125