## Sheet4 (2)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- ह्युम पाइप बिछ्याउने कार्य | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/14
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने )
| -hume pipe | 1 | 10 | 0.5 | 0.6 | 3
| Sub-total |  |  |  |  | 3 | m3 | 64.63 | 193.89
| VAT calculation | [7 empty] | 20.891
2 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia. | 4 | 2.5 |  |  | 10
| Sub-total |  |  |  |  | 10 | rm | 5144.96 | 51449.6
| VAT calculation | [7 empty] | 5965.9184
3 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 58130.2994
| Total Estimated | 58130.2994 |  | 100
| Budget allocated | 52000
| Municipal payment | 49400 |  | 84.9815
| User Contribution | 8730.2994 |  | 15.0185
| Contingencies | 1560 |  | 3
| Maintanince | 1040 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 58130.2994 |  |  |  |  | Total Valuated Amount : |  | 57630.2994
Work Started : | [7 empty] | Work Finished:
Project:- ह्युम पाइप बिछ्याउने कार्य | [7 empty] | F.Y:2081/82
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2081/11/01
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने ) | m3 | 3 | 64.63 | 193.89 | 3 | 64.63 | 193.89 | 0
| VAT calculation |  |  |  | 20.891 |  |  | 20.891
2 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia. | rm | 10 | 5144.96 | 51449.6 | 10 | 5144.96 | 51449.6 | 0
| Sub-total |  |  |  | 5965.9184 |  |  | 5965.9184
3 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 0 | 500 | 0 | -500
| Total |  |  |  | 58130.2994 |  |  | 57630.2994 | -500

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- ह्युम पाइप बिछ्याउने कार्य | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/11/01
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने )
| -hume pipe | 1 | 10 | 0.5 | 0.6 | 3
| Sub-total |  |  |  |  | 3 | m3 | 64.63 | 193.89
| VAT calculation | [7 empty] | 20.891
2 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia. | 4 | 2.5 |  |  | 10
| Sub-total |  |  |  |  | 10 | rm | 5144.96 | 51449.6
| VAT calculation | [7 empty] | 5965.9184
3 | Information board (सुचना पाटि) | 0 |  |  |  | 0 | no. | 500 | 0
| Grand Total | [7 empty] | 57630.2994
| Total Valuated | 57630.2994 |  | 100
| Budget allocated | 52000
| Municipal payment | 48974.2284 |  | 84.98
| User Contribution | 8656.071 |  | 15.02
| Contingencies | 1560 |  | 3
| Maintanince | 1040 |  | 2

## M
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- ह्युम पाइप बिछ्याउने कार्य | [9 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [9 empty] | Date:2081/11/01
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने )
| -hume pipe | 1 | 10 | 0.5 | 0.6 | 3
| Sub-total |  |  |  |  | 3 | m3 | 64.63 | 193.89
| VAT calculation | [7 empty] | 20.891
2 | Providing and Laying Reinforced cement concrete NP3 Flush jointed pipe for culverts including fixing with cement mortar 1:2 as per Drawing and Technical Specifications., 450 mm internal dia. | 4 | 2.5 |  |  | 10
| Sub-total |  |  |  |  | 10 | rm | 5144.96 | 51449.6
| VAT calculation | [7 empty] | 5965.9184
3 | Information board (सुचना पाटि) | 0 |  |  |  | 0 | no. | 500 | 0
| Grand Total | [7 empty] | 57630.2994
| Total Valuated | 57630.2994 |  | 100
| Budget allocated | 52000
| Municipal payment | 48974.2284 |  | 84.98
| User Contribution | 8656.071 |  | 15.02
| Contingencies | 1560 |  | 3
| Maintanince | 1040 |  | 2