## Estimate
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- भुमेश्वर, सेतीदेबी, गणेश मन्दिर निर्माण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/10/23
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
| -for roof | 1 | 4.7242 | 5.7909 | 2.5907 | 6.0148 |  |  |  |  | 6.5529 | 7.6
|  | 1 | 5.5623 | 5.7909 | 5.1813 | 13.0727 |  |  |  |  | 8.2673
|  | 1 | 4.5718 | 5.1813 | 6.0957 | 11.5443 |  |  |  |  | 7.9244
| Sub-total |  |  |  |  | 30.6319 | rm | 1070.9 | 32803.6487
| VAT calculation | [7 empty] | 3419.715
15 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 2 | 1.2953 |  | 1.9049 | 4.935
|  | 2 | 0.76196 |  | 1.9049 | 2.9029
| -Deduction for opening | -1 | 0.9 |  | 1.2953 | -1.1658
|  | -2 | 0.43178 |  | 0.9 | -0.7772
| sub-total |  |  |  |  | 5.8949 | sqm | 405.86 | 2392.5138
| -VAT 13% for materials | [7 empty] | 85.5711
2 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 39201.4485
| Total Estimated | 39201.4485 |  | 100
| Budget allocated | 35000
| Municipal payment | 33250 |  | 84.8183
| User Contribution | 5951.4485 |  | 15.1817
| Contingencies | 1050 |  | 3
| Maintenance | 700 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | #REF! |  |  |  |  | Total Valuated Amount : |  | #REF!
Work Started : | [7 empty] | Work Finished:
Project:- भुमेश्वर, सेतीदेबी, गणेश मन्दिर निर्माण | [7 empty] | F.Y:2081/2082
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2081/10/20
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd | rm | 30.6319 | 1070.9 | 32803.6487 | #REF! | #REF! | #REF! | #REF!
| VAT calculation |  |  |  | 3419.715 |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  |  | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  |  | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  |  | #REF! |  |  | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | #REF! | #REF! | #REF! | #REF!
| Total |  |  |  | #REF! |  |  | #REF! | #REF!