## Sheet4 (2)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- ૐ शान्ति भवन निर्माण तथा मर्मत | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/11
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd .
| -Kitchen floor | 1 | 1.5873 | 6.9601 |  | 11.0479 |  |  |  | Item 134 from civil rate
| -balcony | 1 | 9.9564 | 0.73758 |  | 7.3437
| -deduction for overlap | -6 | 0.27 | 0.135 |  | -0.2187
|  | -2 | 0.5 | 0.16 |  | -0.16
|  | -1 | 0.5 | 0.08 |  | -0.04
| Sub-total |  |  |  |  | 17.9728 | sqm | 2807.39 | 50456.7236
| VAT calculation | [7 empty] | 1871.2647
2 | White glazed porcelain clay one piece commode with 'P' and 'S' trap and slow falling seat cover all complete set
| -commode for toilet | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | set | 20389 | 20389
| VAT calculation | [7 empty] | 2650.57
3 | Stainless steel commode spray with hose pipe all complete set
| -for commode | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | piece | 1798 | 1798
| VAT calculation | [7 empty] | 233.74
4 | White cement for fixtures
| -white cement | 1 | 2 |  |  | 2
| Sub-total |  |  |  |  | 2 | Kg | 30.75 | 61.5
| VAT calculation | [7 empty] | 7.995
5 | -European pattern C.P Grab Bar for disable all complete set
| -45cm long bend type | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | no. | 5613 | 5613
| VAT calculation | [7 empty] | 729.69
6 | Porcelain clay white glaze wash basin (500*400)mm size regular all complete set
| -for hand washing | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | set | 1070 | 1070 |  | 3658.9
| VAT calculation | [7 empty] | 139.1
7 | Stainless steel single faucet for basin mixture all complete set
| -for basin | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | piece | 4425 | 4425
| VAT calculation | [7 empty] | 575.25
8 | Looking Mirror Modi Guard 450*600mm (18"*24") all complete set
| -for bathroom/toilet | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | no. | 1459 | 1459
| VAT calculation | [7 empty] | 189.67
9 | Wall Mixer shower faucet ( conceal system) all complete set
| -for bathroom | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | no. | 4182 | 4182
| VAT calculation | [7 empty] | 543.66
10 | Stainless steel kitchen sink mixture all complete set
| -for kitchen | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | no. | 5565 | 5565
| VAT calculation | [7 empty] | 723.45
11 | CP Toilet paper holder all complete set
| -fittings | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | no. | 929 | 929
| VAT calculation | [7 empty] | 120.77
12 | Towel rod 1/2" *18" all complete set
| -fittings | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | no. | 510 | 510
| VAT calculation | [7 empty] | 66.3
13 | Glass shelf all complete set
| -fittings | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | no. | 680 | 680
| VAT calculation | [7 empty] | 88.4
14 | Provisional sum for unforseen works | 1 |  |  |  | 1 | PS | 10000 | 10000
15 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 115578.0833
| Total Estimated | 115578.0833 |  | 100
| Budget allocated | 100000
| Municipal payment | 95000 |  | 82.1955
| User Contribution | 20578.0833 |  | 17.8045
| Contingencies | 3000 |  | 3
| Maintanince | 2000 |  | 2
Note on I15: DELL: Item 134 from civil rate
Note on I20: DELL: PG .No. 165 ktm jilla darr rate
Note on I25: DELL: PG No. 169 ktm jilla darr rate
Note on I30: DELL: White cement per 40kg bag rs 1230 PG.no.18 Ktm jilla darr rate
Note on I35: DELL: PG .No. 165 ktm jilla darr rate
Note on I40: DELL: PG. No. 166 ktm jilla darr rate
Note on I45: DELL: PG. No. 169 ktm jilla darr rate
Note on I50: DELL: PG. No. 169 ktm jilla darr rate
Note on I55: DELL: PG. No. 169 ktm jilla darr rate
Note on I60: DELL: PG. No. 169 ktm jilla darr rate
Note on I65: DELL: PG. No. 151 ktm jilla darr rate
Note on I70: DELL: PG. No. 151 ktm jilla darr rate
Note on I75: DELL: PG. No. 151 ktm jilla darr rate

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 115578.0833 |  |  |  |  | Total Valuated Amount : |  | 99181.1755
Work Started : | [7 empty] | Work Finished:
Project:- ૐ शान्ति भवन निर्माण तथा मर्मत | [7 empty] | F.Y:2079/80
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2079/06/13
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd . | sqm | 17.9728 | 2807.39 | 50456.7236 | 18.7184 | 2807.39 | 52549.849 | 2093.1254
| VAT calculation |  |  |  | 1871.2647 |  |  | 1948.8915 | 77.6268
2 | White glazed porcelain clay one piece commode with 'P' and 'S' trap and slow falling seat cover all complete set | set | 1 | 20389 | 20389 | 1 | 20389 | 20389 | 0
| VAT calculation |  |  |  | 2650.57 |  |  | 2650.57 | 0
0
3 | Stainless steel commode spray with hose pipe all complete set | piece | 1 | 1798 | 1798 | 1 | 1798 | 1798 | 0
| VAT calculation |  |  |  | 233.74 |  |  | 233.74 | 0
4 | White cement for fixtures | Kg | 2 | 30.75 | 61.5 | 2 | 30.75 | 61.5 | 0
| VAT calculation |  |  |  | 7.995 |  |  | 7.995 | 0
5 | -European pattern C.P Grab Bar for disable all complete set | no. | 1 | 5613 | 5613 | 0 | 5613 | 0 | -5613
| VAT calculation |  |  |  | 729.69 |  |  | 0 | -729.69
6 | Porcelain clay white glaze wash basin (500*400)mm size regular all complete set | set | 1 | 1070 | 1070 | 1 | 1070 | 1070 | 0
| VAT calculation |  |  |  | 139.1 |  |  | 139.1 | 0
7 | Stainless steel single faucet for basin mixture all complete set | piece | 1 | 4425 | 4425 | 1 | 4425 | 4425 | 0
| VAT calculation |  |  |  | 575.25 |  |  | 575.25 | 0
8 | Looking Mirror Modi Guard 450*600mm (18"*24") all complete set | no. | 1 | 1459 | 1459 | 0 | 1459 | 0 | -1459
| VAT calculation |  |  |  | 189.67 |  |  | 0 | -189.67
9 | Wall Mixer shower faucet ( conceal system) all complete set | no. | 1 | 4182 | 4182 | 1 | 4182 | 4182 | 0
| VAT calculation |  |  |  | 543.66 |  |  | 543.66 | 0
10 | Stainless steel kitchen sink mixture all complete set | no. | 1 | 5565 | 5565 | 1 | 5565 | 5565 | 0
| VAT calculation |  |  |  | 723.45 |  |  | 723.45 | 0
11 | CP Toilet paper holder all complete set | no. | 1 | 929 | 929 | 1 | 929 | 929 | 0
| VAT calculation |  |  |  | 120.77 |  |  | 120.77 | 0
12 | Towel rod 1/2" *18" all complete set | no. | 1 | 510 | 510 | 0 | 510 | 0 | -510
| VAT calculation |  |  |  | 66.3 |  |  | 0 | -66.3
13 | Glass shelf all complete set | no. | 1 | 680 | 680 | 1 | 680 | 680 | 0
| VAT calculation |  |  |  | 88.4 |  |  | 88.4 | 0
14 | Provisional sum for unforseen works | PS | 1 | 10000 | 10000 | 0 | 10000 | 0 | -10000
15 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0
| Total |  |  |  | 115578.0833 |  |  | 99181.1755 | -16396.9079

## Valuated
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- ૐ शान्ति भवन निर्माण तथा मर्मत | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/11
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | kf]/l;lng Un]H8 6fO{n(Ordinary floor and Wall Tile-as per approved standard of manufactured country) !M$ l;d]G6 afn'jfdf 5fKg] sfd .
| -Kitchen floor | 1 | 3.47 | 1.44 |  | 4.9968 |  |  |  | Item 134 from civil rate
|  | -2 | 0.7 | 0.13 |  | -0.182
|  | 1 | 3.56 | 1.535 |  | 5.4646
|  | -1 | 0.7 | 0.45 |  | -0.315
|  | -1 | 0.48 | 0.13 |  | -0.0624
|  | -1 | 0.46 | 0.08 |  | -0.0368
| -balcony | 1 | 8.15 | 0.7 |  | 5.705
|  | 1 | 1.8 | 0.7 |  | 1.26
| -skirting | 1 | 9.95 | 0.12 |  | 1.194
| -at cleansing area | 1 | 0.9 | 0.79 |  | 0.711
|  | 1 | 0.72 | 0.3 |  | 0.216
|  | 1 | 0.9 | 0.34 |  | 0.306
| deduction for skirting area | -1 | 2.54 | 0.12 |  | -0.3048
| -deduction for column offset | -6 | 0.3 | 0.13 |  | -0.234
| Sub-total |  |  |  |  | 18.7184 | sqm | 2807.39 | 52549.849
| VAT calculation | [7 empty] | 1948.8915
2 | White glazed porcelain clay one piece commode with 'P' and 'S' trap and slow falling seat cover all complete set
| -commode for toilet | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | set | 20389 | 20389
| VAT calculation | [7 empty] | 2650.57
3 | Stainless steel commode spray with hose pipe all complete set
| -for commode | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | piece | 1798 | 1798
| VAT calculation | [7 empty] | 233.74
4 | White cement for fixtures
| -white cement | 1 | 2 |  |  | 2
| Sub-total |  |  |  |  | 2 | Kg | 30.75 | 61.5
| VAT calculation | [7 empty] | 7.995
5 | -European pattern C.P Grab Bar for disable all complete set
| -45cm long bend type | 0 |  |  |  | 0
| Sub-total |  |  |  |  | 0 | no. | 5613 | 0
| VAT calculation | [7 empty] | 0
6 | Porcelain clay white glaze wash basin (500*400)mm size regular all complete set
| -for hand washing | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | set | 1070 | 1070
| VAT calculation | [7 empty] | 139.1
7 | Stainless steel single faucet for basin mixture all complete set
| -for basin | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | piece | 4425 | 4425
| VAT calculation | [7 empty] | 575.25
8 | Looking Mirror Modi Guard 450*600mm (18"*24") all complete set
| -for bathroom/toilet | 0 |  |  |  | 0 |  |  |  | size of 350*500mm used
| Sub-total |  |  |  |  | 0 | no. | 1459 | 0
| VAT calculation | [7 empty] | 0
9 | Wall Mixer shower faucet ( conceal system) all complete set
| -for bathroom | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | no. | 4182 | 4182
| VAT calculation | [7 empty] | 543.66
10 | Stainless steel kitchen sink mixture all complete set
| -for kitchen | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | no. | 5565 | 5565
| VAT calculation | [7 empty] | 723.45
11 | CP Toilet paper holder all complete set
| -fittings | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | no. | 929 | 929
| VAT calculation | [7 empty] | 120.77
12 | Towel rod 1/2" *18" all complete set | [8 empty] | size of 1/4" *22" used
| -fittings | 0 |  |  |  | 0
| Sub-total |  |  |  |  | 0 | no. | 510 | 0
| VAT calculation | [7 empty] | 0
13 | Glass shelf all complete set
| -fittings | 1 |  |  |  | 1
| Sub-total |  |  |  |  | 1 | no. | 680 | 680
| VAT calculation | [7 empty] | 88.4
14 | Provisional sum for unforseen works | 0 |  |  |  | 0 | no. | 10000 | 0 | 80*17cm pedestal for basin used and toilet brush holder
15 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 99181.1755
| Total Estimated | 99181.1755 |  | 100
| Budget allocated | 100000
| Municipal payment | 81526.9262 |  | 82.2
| User Contribution | 17654.2492 |  | 17.8
| Contingencies | 3000 |  | 3
| Maintanince | 2000 |  | 2
Note on I24: DELL: Item 134 from civil rate
Note on I29: DELL: PG .No. 165 ktm jilla darr rate
Note on I34: DELL: PG No. 169 ktm jilla darr rate
Note on I39: DELL: White cement per 40kg bag rs 1230 PG.no.18 Ktm jilla darr rate
Note on I44: DELL: PG .No. 165 ktm jilla darr rate
Note on I49: DELL: PG. No. 166 ktm jilla darr rate
Note on I54: DELL: PG. No. 169 ktm jilla darr rate
Note on I59: DELL: PG. No. 169 ktm jilla darr rate
Note on I64: DELL: PG. No. 169 ktm jilla darr rate
Note on I69: DELL: PG. No. 169 ktm jilla darr rate
Note on I74: DELL: PG. No. 151 ktm jilla darr rate
Note on I79: DELL: PG. No. 151 ktm jilla darr rate
Note on I84: DELL: PG. No. 151 ktm jilla darr rate