## FINAL (3)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- लाकिला गणेश मन्दिर निर्माण | [6 empty] | F.Y.: 2080/81
Location:- Shankharapur Municipality 9 | [6 empty] | Date: 2080/10/14
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
A | For Protection work
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] k'g]{ sfd
| -For foundation | 1 | 2.8193 | 2.8193 | 1.5 | 11.9224
| Sub-total |  |  |  |  | 11.9224 | cum | 648.9 | 7736.42
2 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -For foundation | 1 | 2.8193 | 2.8193 |  | 7.9482
| -For flooring | 1 | 2.2097 | 2.2097 |  | 4.8827
| Sub-total |  |  |  |  | 12.831 | sqm | 985.38 | 12643.3911
| -VAT 13% for materials | [7 empty] | 1393.4384
3 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd-lk=;L=;L= !M#M^_
| -For foundation | 1 | 2.8193 | 2.8193 | 0.075 | 0.59612
| Sub-total |  |  |  |  | 0.59612 | cum | 12300.32 | 7332.4427
| -VAT 13% for materials | [7 empty] | 581.2407
4 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
-For footing
| -Rectangular portion | 1 | 2.6693 | 2.6693 | 0.45 | 3.2062
| -Neck column | 4 | 0.3 | 0.3 | 4.4956 | 1.6184 |  |  |  |  | 0.83333 | 0.25399
| -Shear wall | 2 | 2.0573 | 0.23 | 4.4956 | 4.2544
| -Upper plinth beam | 4 | 3.8872 | 0.23 | 0.23 | 0.82253
| -For flooring including peti | 1 | 4.4956 | 4.4956 | 0.125 | 2.5263
| -Column | 4 | 0.3 | 0.3 | 2.7178 | 0.9784
| -Beam | 4 | 2.0573 | 0.23 | 0.23 | 0.43532
| -Secondary beam | 2 | 2.2097 | 0.23 | 0.23 | 0.23379
| -1st floor slab | 1 | 4.4956 | 4.4956 | 0.125 | 2.5263
| -1st floor Inclined Surface | 4 | 1.7784 | 2.87 | 0.1 | 2.0416
| -1st floor column | 4 | 0.23 | 0.23 | 2.0826 | 0.44068
| -1st floor beam | 4 | 1.0667 | 0.23 | 0.23 | 0.22572
| -2nd floor beam | 4 | 1.0667 | 0.23 | 0.23 | 0.22572
| -2nd floor slab | 1 | 3.0224 | 3.0224 | 0.1 | 0.91349
| -2nd floor inclined roof slab | 4 | 1.4736 | 1.6641 | 0.075 | 0.7357
| Sub-total |  |  |  |  | 21.1846 | cum | 14200.82 | 300838.8901
| -VAT 13% for materials | [7 empty] | 28228.5532
5 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
-For footing
| -Rectangular portion | 1 | 10.677 |  | 0.45 | 4.8047
| -Neck column | 4 | 1.2 |  | 3.8098 | 18.2871
| -Shear wall | 2 | 2.0573 |  | 4.4956 | 18.4975
| -Upper plinth beam | 4 | 3.8872 |  | 0.46 | 7.1524
| -Column | 4 | 1.2 |  | 2.7178 | 13.0453
| -Beam | 4 | 2.0573 |  | 0.46 | 3.7854
| -Secondary beam | 2 | 2.2097 |  | 0.46 | 2.0329
| -1st floor slab | 1 | 4.4956 | 4.4956 |  | 20.2102
| -Deduction for column part | -4 | 0.3 | 0.3 |  | -0.36
| -1st floor Inclined Surface | 4 | 1.6001 | 2.87 |  | 18.3695
| -1st floor column | 4 | 0.92 |  | 2.0826 | 7.664
| -2nd floor beam | 4 | 1.0667 |  | 0.46 | 1.9628
| -deduction for column beam intersection | -4 | 0.92 |  | 0.23 | -0.8464
| -2nd floor slab | 1 | 3.0224 | 3.0224 |  | 9.1349
| -2nd floor inclined roof slab | 4 | 1.4736 | 1.6641 |  | 9.8093
| Sub-total |  |  |  |  | 133.5496 | sqm | 905.97 | 120991.9558
| -VAT 13% for materials | [7 empty] | 8129.998
[12 empty] | 192 | 47.9373 | 191.7491
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit weight (m) | Total weight (kg) | Total weight (M.T.) |  |  |  |  | 13.75 | 27.5
| -For footing | 72 | 2.6693 | 0.88889 | 170.8328 | 0.17083 |  |  |  |  | 4.085 | 12.2673 | 8.17
| -shear wall horizontal bars | 60 | 6.5529 | 0.39506 | 155.3275 | 0.15533
| -shear wall vertical bars | 48 | 5.9159 | 0.61728 | 175.2853 | 0.17529
| -Upper plinth beam | 16 | 4.0872 | 0.88889 | 58.129 | 0.058129
| -Stirrups | 120 | 0.81439 | 0.39506 | 38.6079 | 0.038608 | [5 empty] | 684 | 2.2442
| -For flooring including peti | 92 | 4.3956 | 0.39506 | 159.7604 | 0.15976
| -Column | 32 | 7.8991 | 0.88889 | 224.686 | 0.22469 |  |  |  |  | 684 | 0.684 | 2.2442
| -Stirrups | 200 | 1.018 | 0.39506 | 80.4332 | 0.080433
|  | 200 | 0.81439 | 0.39506 | 64.3465 | 0.064347
| -Beam | 20 | 2.2573 | 0.88889 | 40.1298 | 0.04013 |  |  |  |  | 78 | 29.25 | 2.4375
| -Extra bars | 8 | 1.5793 | 0.88889 | 11.2306 | 0.011231
| -Stirrups | 60 | 0.81439 | 0.39506 | 19.304 | 0.019304 | [5 empty] | 2.7431
| -Secondary beam | 10 | 2.8699 | 0.88889 | 25.5098 | 0.02551
| -Stirrups | 32 | 0.81439 | 0.39506 | 10.2954 | 0.010295 |  |  |  |  | 1.9375 | 3.2675 | 1.481
| -Slab doubly reinforcement | 92 | 4.3956 | 0.39506 | 159.7604 | 0.15976 | [5 empty] | 1.5793
-1st floor Inclined Surface
| -horizontal bars | 40 | 2.87 | 0.61728 | 70.8644 | 0.070864 | [5 empty] | 5.75 | 17.2673 | 34.5345
| -vertical bars | 76 | 1.6001 | 0.61728 | 75.0674 | 0.075067
| -1st floor column | 32 | 3.4506 | 0.88889 | 98.1503 | 0.09815
| -Stirrups | 56 | 0.81439 | 0.39506 | 18.017 | 0.018017
|  | 56 | 0.61567 | 0.39506 | 13.6207 | 0.013621
| -2nd floor beam | 16 | 1.4221 | 0.88889 | 20.2258 | 0.020226 | [5 empty] | 0.684
| -Stirrups | 48 | 0.81439 | 0.39506 | 15.4432 | 0.015443
| -2nd floor slab | 34 | 3.0224 | 0.61728 | 63.4331 | 0.063433
-2nd floor inclined roof slab
| -horizontal bars | 36 | 1.6641 | 0.61728 | 36.9806 | 0.036981
| -vertical bars | 44 | 1.4736 | 0.61728 | 40.0247 | 0.040025
| Sub-total |  |  |  |  | 1.8455 | M.T | 130210 | 240298.1082
| -VAT 13% for materials | [7 empty] | 25193.0079
7 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -At between lower and upper tie beam | 2 | 2.0573 | 0.23 | 3.8098 | 3.6054
| Sub-total |  |  |  |  | 3.6054 | cum | 14520.78 | 52353.9076
| -VAT 13% for materials | [7 empty] | 4949.9284
8 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M$_ df
| -At Ground floor | 4 | 2.0573 | 0.1 | 2.4901 | 2.0491
| -Deduction for window | -2 | 0.75 | 0.1 | 0.9 | -0.135
| -Deduction for door | -1 | 1.0667 | 0.1 | 2.1335 | -0.22759
| -At horizontal roof slab | 2 | 1.0667 | 0.1 | 0.83816 | 0.17882
|  | 4 | 1.0667 | 0.1 | 0.68577 | 0.29262
| -Deduction for window | -4 | 0.6 | 0.1 | 0.67 | -0.1608
| Sub-total |  |  |  |  | 1.9972 | cum | 14911.97 | 29782.1095
| -VAT 13% for materials | [7 empty] | 2842.1189
9 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -At basement | 4 | 2.2097 |  | 4.267 | 37.715
| -Deduction for window | -1 | 0.9 |  | 1.2 | -1.08
| -Deduction for door | -1 | 0.9 |  | 2.1335 | -1.9201
| -At Ground floor | 4 | 2.2097 |  | 1.1938 | 10.5521
| -Deduction for window | -2 | 0.75 |  | 0.45 | -0.675
| -Deduction for door | -1 | 1.0667 |  | 1.1938 | -1.2735
| -Basement floor ceiling | 1 | 2.2097 | 2.2097 |  | 4.8827
| Sub-total |  |  |  |  | 0 | sqm | 402.23 | 0
| -VAT 13% for materials | [7 empty] | 0
9 | Traditional Brick (Small Dachi Appa) work in (1:1:2) lime, surkhi, sand mortar
| -At Ground floor | 4 | 2.6669 |  | 2.1335 | 22.759
| -Deduction for window | -2 | 0.75 |  | 0.9 | -1.35
| -Deduction for door | -1 | 1.0667 |  | 2.1335 | -2.2759
| Sub-total |  |  |  |  | 19.1331 | sqm | 5566.6092 | 106506.608
| VAT calculation | [7 empty] | 9204.2978
10 | Traditional Nago Brick work in (1:1:2) lime,surkhi, sand mortar
| -At ground floor | 4 | 1.1429 |  | 2.1335 | 9.7539
| Sub-total |  |  |  |  | 9.7539 | 1 | 467.6783 | 4561.6716
| VAT calculation | [7 empty] | 368.9013
11 | cu¦fv sf7sf] rf}s; agfO hf]8\g] sfd
| Door | 1 | 6.0957 | 0.075 | 0.125 | 0.057147
| Sub-total |  |  |  |  | 0.057147 | cum | 283082.83 | 16177.3943
| VAT calculation | [7 empty] | 1777.2193
12 | Carved salwood Lattice (jali) of Carved Window and door (second type) including wood
| Window | 2 | 0.75 |  | 0.9 | 1.35
|  | 4 | 0.60957 |  | 0.68577 | 1.6721
| Door | 1 | 1.0667 |  | 2.1335 | 2.2759
| Sub-total |  |  |  |  | 5.298 | sqm | 34296.1957 | 181701.0342
| VAT calculation | [7 empty] | 7293.5236
13 | Provisional sum for lab test | 1 |  |  |  | 1 | PS | 15000 | 15000
17 | 20 gauge Brass plate making and fixing on roof
| -Slab | 2 | 3.3526 | 0.45 |  | 3.0174
|  | 2 | 2.4383 | 0.45 |  | 2.1945
| -Inclined Surface | 4 | 1.4224 | 1.2 |  | 6.8277
| Sub-total |  |  |  |  | 0 | sqm | 3251.8875 | 0
| -VAT 13% for materials | [7 empty] | 0
14 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 1186886.1607
| Total Estimated | 1186886.1607 |  | 100
| Budget allocated | 1000000
| Municipal payment | 950000 |  | 80.0414
| User Contribution | 236886.1607 |  | 19.9586 | [6 empty] | from centre | total
| Contingencies | 30000 |  | 3 | [6 empty] | 11m | 22m
| Maintanince | 20000 |  | 2
hanumante
Note: | All the dimensions are taken as per the direction/instruction of senior engineer and the design, dimensions and rates should be first verified and approved by senior engineer of Shankharapur Municipality then only the estimate is authentic.
Note on E36: boom boom: (14.75+12.833)/2=13.833
Note on C78: boom boom: cranked extrra bar in bottom and top

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 1186886.1607 |  |  |  |  | Total Valuated Amount : |  | 873283.9054
Work Started : | [7 empty] | Work Finished:
Project:- लाकिला गणेश मन्दिर निर्माण | [7 empty] | F.Y:2080/2081
Location:- Shankharapur Municipality 9 | [7 empty] | Date:
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] k'g]{ sfd | cum | 11.9224 | 648.9 | 7736.42 | 11.9224 | 648.9 | 7736.42 | 0 |  | 9670.525
2 | ;'Vvf O{6f RofK6f] 5fKg] sfd | sqm | 12.831 | 985.38 | 12643.3911 | 12.831 | 985.38 | 12643.3911 | 0 |  | 15804.2389
| -VAT 13% for materials |  |  |  | 1393.4384 |  |  | 1393.4384 | 0 |  | 1741.798
3 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd-lk=;L=;L= !M#M^_ | cum | 0.59612 | 12300.32 | 7332.4427 | 0.59612 | 12300.32 | 7332.4427 | 0 |  | 9165.5534
| -VAT 13% for materials |  |  |  | 581.2407 |  |  | 581.2407 | 0 |  | 726.5508
4 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_ | cum | 21.1846 | 14200.82 | 300838.8901 | 23.2134 | 14200.82 | 329648.9203 | 28810.0302 |  | 376048.6126 | 31513.3557
| -VAT 13% for materials |  |  |  | 28228.5532 |  |  | 30931.8788 | 2703.3256 |  | 35285.6915 | 69321.9042
5 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd | sqm | 133.5496 | 905.97 | 120991.9558 | 162.7598 | 905.97 | 147455.499 | 26463.5432 |  | 151239.9448
| -VAT 13% for materials |  |  |  | 8129.998 |  |  | 9908.2034 | 1778.2054 |  | 10162.4975
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | M.T | 1.8455 | 130210 | 240298.1082 | 1.912 | 130210 | 248957.0944 | 8658.9862 |  | 300372.6353
| -VAT 13% for materials |  |  |  | 25193.0079 |  |  | 26100.8216 | 907.8137 |  | 31491.2599
7 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | cum | 3.6054 | 14520.78 | 52353.9076 | 2.1766 | 14520.78 | 31606.2634 | -20747.6442 |  | 65442.3845
| -VAT 13% for materials |  |  |  | 4949.9284 |  |  | 2988.2916 | -1961.6368 |  | 6187.4105
8 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M$_ df | cum | 1.9972 | 14911.97 | 29782.1095 | 0 | 14911.97 | 0 | -29782.1095 |  | 37227.6369
| -VAT 13% for materials |  |  |  | 2842.1189 |  |  | 0 | -2842.1189 |  | 3552.6486
9 | Traditional Brick (Small Dachi Appa) work in (1:1:2) lime, surkhi, sand mortar | sqm | 19.1331 | 5566.6092 | 106506.608 | 0 | 5566.6092 | 0 | -106506.608 |  | 133133.2601
| VAT calculation |  |  |  | 9204.2978 |  |  | 0 | -9204.2978 |  | 11505.3722
10 | Traditional Nago Brick work in (1:1:2) lime,surkhi, sand mortar | rm | 9.7539 | 467.6783 | 4561.6716 | 0 | 467.6783 | 0 | -4561.6716 |  | 5702.0896
| VAT calculation |  |  |  | 368.9013 |  |  | 0 | -368.9013 |  | 461.1266
11 | cu¦fv sf7sf] rf}s; agfO hf]8\g] sfd | cum | 0.057147 | 283082.83 | 16177.3943 | 0 | 283082.83 | 0 | -16177.3943 |  | 20221.7428
| VAT calculation |  |  |  | 1777.2193 |  |  | 0 | -1777.2193 |  | 2221.5241
12 | Carved salwood Lattice (jali) of Carved Window and door (second type) including wood | sqm | 5.298 | 34296.1957 | 181701.0342 | 0 | 34296.1957 | 0 | -181701.0342 |  | 227126.2928
| VAT calculation |  |  |  | 7293.5236 |  |  | 0 | -7293.5236 |  | 9116.9045
13 | Provisional sum for lab test | PS | 1 | 15000 | 15000 | 1 | 15000 | 15000 | 0 |  | 18750
14 | Information board (सुचना पाटि) | no. | 1 | 1000 | 1000 | 1 | 1000 | 1000 | 0 |  | 1250
| Total |  |  |  | 1186886.1607 |  |  | 873283.9054 | -313602.2553

## valuated
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- लाकिला गणेश मन्दिर निर्माण | [6 empty] | F.Y.: 2080/81
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
A | For Protection work
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] k'g]{ sfd
| -For foundation | 1 | 2.8193 | 2.8193 | 1.5 | 11.9224
| Sub-total |  |  |  |  | 11.9224 | cum | 648.9 | 7736.42
2 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -For foundation | 1 | 2.8193 | 2.8193 |  | 7.9482 |  |  |  |  | 7.25
| -For flooring | 1 | 2.2097 | 2.2097 |  | 4.8827
| Sub-total |  |  |  |  | 12.831 | sqm | 985.38 | 12643.3911
| -VAT 13% for materials | [7 empty] | 1393.4384
3 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd-lk=;L=;L= !M#M^_
| -For foundation | 1 | 2.8193 | 2.8193 | 0.075 | 0.59612
| Sub-total |  |  |  |  | 0.59612 | cum | 12300.32 | 7332.4427
| -VAT 13% for materials | [7 empty] | 581.2407
4 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
-For footing
| -Rectangular portion | 1 | 2.8193 | 2.8193 | 0.55877 | 4.4413
| -Neck column | 4 | 0.3 | 0.3 | 0.9 | 0.324 |  |  |  |  | 0.83333 | 0.25399 | 3.02 | 0.92045 | 4.4666 | 4.2366
| -Upper plinth beam | 4 | 2.09 | 0.23 | 0.23 | 0.44224
| -Shear wall footing | 2 | 2.67 | 0.50798 | 0.23 | 0.6239 |  |  |  |  | 0.76196 |  |  |  | 37.5 | 3.125
|  | 1 | 1.684 | 0.50798 | 0.23 | 0.19675
| -For flooring including peti | 1 | 1.6519 | 1.854 | 0.075 | 0.2297
| -Shear wall | 1 | 2.09 | 0.23 | 2.4901 | 1.197 |  |  |  |  | 8.163 | 2.488 | 6.8573
|  | 2 | 2.09 | 0.15239 | 2.4901 | 1.5862 |  |  |  |  | 8.7603
| -Column | 4 | 0.3 | 0.3 | 2.7178 | 0.9784 | [6 empty] | 8.9243
| -Beam | 4 | 3.886 | 0.23 | 0.23 | 0.82228 |  |  |  |  | 12.75
| -Ground floor slab | 1 | 4.45 | 4.55 | 0.125 | 2.5309
| -1st floor column | 4 | 0.3 | 0.3 | 2.6416 | 0.95097 |  |  |  |  | 8.92
| -Beam | 4 | 3.2764 | 0.23 | 0.23 | 0.69329 |  |  |  |  | 10.75
| -Secondary beam | 2 | 2.2097 | 0.23 | 0.23 | 0.23379
| -1st floor slab | 1 | 4.45 | 4.55 | 0.127 | 2.5714
| -1st floor Inclined Surface | 4 | 3.0738 | 1.8034 | 0.1016 | 2.2527 |  |  |  |  | 3.0098 | 9.875
| -column | 4 | 1.0667 | 0.3 | 0.3 | 0.38403
| -beam | 4 | 0.91436 | 0.23 | 0.23 | 0.19348
| -column | 4 | 0.67 | 0.3 | 0.3 | 0.2412
| -beam | 4 | 2.1335 | 0.17769 | 0.19049 | 0.28886 |  |  |  |  | 7 | 2.1335 | 7
| -slab | 1 | 3.3526 | 3.3526 | 0.1016 | 1.1419
| -deduction for hollow part | -1 | 1.0667 | 1.0667 | 0.1016 | -0.11561
| -column | 4 | 0.3 | 0.30479 | 0.3 | 0.10972 |  |  |  |  | 1.25
| -inclined slab | 4 | 1.943 | 1.2953 | 0.088896 | 0.89495 |  |  |  |  | 23.2134
| Sub-total |  |  |  |  | 23.2134 | cum | 14200.82 | 329648.9203
| -VAT 13% for materials | [7 empty] | 30931.8788
5 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
-For footing
| -Rectangular portion | 4 | 2.8193 |  | 0.55877 | 6.3013
| -Neck column | 4 | 1.2 |  | 0.9 | 4.32 |  |  |  |  | 0.83333 | 0.25399 | 3.02 | 0.92045 | 4.4666 | 4.2366
| -Shear wall footing | 2 | 5.35 |  | 0.23 | 2.461 |  |  |  |  | 0.76196 |  |  |  | 37.5 | 3.125
|  | 1 | 3.1649 |  | 0.23 | 0.72793 |  |  |  |  | 2.0573 | 5.6367
| -Shear wall | 1 | 7.975 |  | 2.4901 | 19.8585 |  |  |  |  | 8.163 | 2.488 | 6.8573
|  | 3 | 2.09 |  | 2.4901 | 15.6129 |  |  |  |  | 8.7603 | 8.163
| -column | 4 | 0.3 |  | 2.4901 | 2.9881
|  | 1 | 0.45718 |  | 2.4901 | 1.1384
| -Beam | 4 | 3.9622 |  | 0.43178 | 6.8432 |  |  |  |  | 13
| -Ground floor slab | 1 | 4.45 | 4.55 |  | 20.2475
| slab edge | 1 | 17.8 |  | 0.125 | 2.225
| -deduction for beam | -4 | 3.2764 | 0.15 |  | -1.9659
| -1st floor column | 4 | 1.2 |  | 2.4383 | 11.7037 |  |  |  |  | 8.92 | 8.75 | 2.6669
| -Beam | 4 | 3.2764 |  | 0.43178 | 5.6588 |  |  |  |  | 10.75 | 8 | 2.4383
| -Secondary beam | 2 | 2.2097 |  | 0.46 | 2.0329
| -1st floor slab | 1 | 4.45 | 4.55 | 0.125 | 2.5309
| slab edge | 1 | 17.8 |  | 0.125 | 2.225
| -1st floor Inclined Surface | 4 | 3.0738 | 1.8034 |  | 22.173 |  |  |  |  | 3.0098 | 9.96
| -column | 4 | 1.2 |  | 0.99665 | 4.7839
| -beam | 4 | 0.91436 |  | 0.46 | 1.6824
| -column | 4 | 1.2 |  | 0.67 | 3.216
| -beam | 4 | 2.1335 |  | 0.35538 | 3.0328 |  |  |  |  | 7 | 2.1335 | 7
| -slab | 1 | 3.3526 | 3.3526 |  | 11.2402
| slab edge | 1 | 13.4105 |  | 0.1 | 1.3411
| -deduction for hollow part | -1 | 1.0667 | 1.0667 |  | -1.138
| -column | 4 | 1.2 |  | 0.3 | 1.44
| -inclined slab | 4 | 1.9049 | 1.2953 |  | 9.87 |  |  |  |  | 162.5508
| top roof floor | 1 | 0.45718 | 0.45718 |  | 0.20901
| Sub-total |  |  |  |  | 162.7598 | sqm | 905.97 | 147455.499
| -VAT 13% for materials | [7 empty] | 9908.2034
[12 empty] | 192 | 47.9373 | 191.7491
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit weight (m) | Total weight (kg) | Total weight (M.T.) |  |  |  |  | 13.75 | 27.5
| -For footing | 70 | 3.505 | 0.88889 | 218.0907 | 0.21809 |  |  |  |  | 4.085 | 12.2673 | 8.17
| -column | 32 | 7.772 | 0.88889 | 221.0708 | 0.22107
|  | 16 | 0.75 | 0.88889 | 10.6667 | 0.010667
| - column stirrups | 65 | 1.018 | 0.39506 | 26.1408 | 0.026141
|  | 65 | 0.71076 | 0.39506 | 18.2516 | 0.018252
| -plinth beam | 16 | 3.7336 | 0.88889 | 53.1003 | 0.0531 |  |  |  |  | 34
| -Stirrups | 76 | 0.81439 | 0.39506 | 24.4517 | 0.024452 |  |  |  |  | 11.246 | 684 | 2.2442
| -shear wall horizontal bars | 18 | 7.15 | 0.39506 | 50.8444 | 0.050844
| -shear wall vertical bars | 42 | 3.4288 | 0.88889 | 128.0098 | 0.12801 |  |  |  |  | 7.75 | 11.413
| -GF Beam | 20 | 4.4956 | 0.88889 | 79.9214 | 0.079921 |  |  |  |  | 78 | 29.25 | 2.4375
| -Stirrups | 134 | 0.81439 | 0.39506 | 43.1122 | 0.043112 | [5 empty] | 2.7431
| -Slab | 26 | 4.3703 | 0.61728 | 70.1404 | 0.07014 |  |  |  |  | 14.6005 | 14.9285
|  | 78 | 4.4465 | 0.39506 | 137.0174 | 0.13702
| -1st floor beam | 20 | 4.8522 | 0.88889 | 86.261 | 0.086261 |  |  |  |  | 78 | 29.25 | 2.4375
| -Stirrups | 118 | 0.81439 | 0.39506 | 37.9645 | 0.037964 | [5 empty] | 2.7431
| -Secondary beam | 12 | 1.9811 | 0.88889 | 21.1318 | 0.021132
| -Stirrups | 28 | 0.91618 | 0.39506 | 10.1346 | 0.010135
| -Slab doubly reinforcement | 52 | 4.9703 | 0.39506 | 102.1056 | 0.10211 | [5 empty] | #REF!
|  | 52 | 4.4465 | 0.39506 | 91.345 | 0.091345
| -1st floor inclined slab | [9 empty] | 1.538
| -horizontal bars | 44 | 3.0098 | 0.61728 | 81.7464 | 0.081746 |  |  |  |  | 9.25 | 5.75 | 17.2673 | 34.5345
| -vertical bars | 40 | 1.6763 | 0.39506 | 26.49 | 0.02649
|  | 32 | 1.2191 | 0.39506 | 15.4123 | 0.015412
|  | 32 | 1.2191 | 0.39506 | 15.4123 | 0.015412
| -Column from1st floor to roof floor | 32 | 2.996 | 0.88889 | 85.2206 | 0.085221
| -Stirrups | 36 | 1.018 | 0.39506 | 14.478 | 0.014478
|  | 36 | 0.60957 | 0.39506 | 8.6694 | 0.0086694
| -2nd floor beam | 16 | 1.5239 | 0.88889 | 21.6736 | 0.021674 | [5 empty] | 0.684
| -Stirrups | 32 | 0.81439 | 0.39506 | 10.2954 | 0.010295
| -2nd floor slab | 24 | 3.2764 | 0.39506 | 31.0655 | 0.031066
|  | 24 | 3.8098 | 0.39506 | 36.1227 | 0.036123
|  | 28 | 1.0424 | 0.39506 | 11.5304 | 0.01153
|  | 28 | 1.3472 | 0.39506 | 14.9018 | 0.014902
| -2nd floor upper beam | 16 | 2.0573 | 0.88889 | 29.2594 | 0.029259 | [5 empty] | 0.684
| -Stirrups | 32 | 0.56385 | 0.39506 | 7.1282 | 0.0071282
| -2nd floor inclined slab | [9 empty] | 35 | 56
| -horizontal bars | 10 | 1.8668 | 0.39506 | 7.375 | 0.007375 |  |  |  |  | 0.88896
| -vertical bars | 16 | 1.5239 | 0.39506 | 9.6327 | 0.0096327
|  | 8 | 1.3715 | 0.39506 | 4.3347 | 0.0043347
|  | 8 | 1.2191 | 0.39506 | 3.8531 | 0.0038531
|  | 8 | 1.016 | 0.39506 | 3.2109 | 0.0032109
|  | 8 | 0.91436 | 0.39506 | 2.8898 | 0.0028898
|  | 8 | 0.76196 | 0.39506 | 2.4082 | 0.0024082
|  | 8 | 0.50798 | 0.39506 | 1.6055 | 0.0016055
| Sub-total |  |  |  |  | 1.8745
| -wastage 2% |  |  |  |  | 0.03749
| total |  |  |  |  | 1.912 | M.T | 130210 | 248957.0944
| -VAT 13% for materials | [7 empty] | 26100.8216
7 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -At between lower and upper tie beam | 4 | 2.0573 | 0.23 | 1.15 | 2.1766
| Sub-total |  |  |  |  | 2.1766 | cum | 14520.78 | 31606.2634 |  | 34594.555 | 8405.445
| -VAT 13% for materials | [7 empty] | 2988.2916
8 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M$_ df
| -At Ground floor | 0 | 0 | 0 | 0 | 0
| -Deduction for window | 0 | 0 | 0 | 0 | 0
| -Deduction for door | 0 | 0 | 0 | 0 | 0
| -At horizontal roof slab | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
| -Deduction for window | 0 | 0 | 0 | 0 | 0
| Sub-total |  |  |  |  | 0 | cum | 14911.97 | 0
| -VAT 13% for materials | [7 empty] | 0
9 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -At basement | 4 | 2.2097 |  | 4.267 | 37.715
| -Deduction for window | -1 | 0.9 |  | 1.2 | -1.08
| -Deduction for door | -1 | 0.9 |  | 2.1335 | -1.9201
| -At Ground floor | 0 | 2.2097 |  | 1.1938 | 0
| -Deduction for window | 0 | 0 |  | 0.45 | 0
| -Deduction for door | 0 | 0 |  | 1.1938 | 0
| -Basement floor ceiling | 0 | 2.2097 | 2.2097 |  | 0
| Sub-total |  |  |  |  | 0 | sqm | 402.23 | 0
| -VAT 13% for materials | [7 empty] | 0
9 | Traditional Brick (Small Dachi Appa) work in (1:1:2) lime, surkhi, sand mortar
| -At Ground floor | 0 | 0 |  | 0 | 0
| -Deduction for window | 0 | 0 |  | 0 | 0
| -Deduction for door | 0 | 0 |  | 0 | 0
| Sub-total |  |  |  |  | 0 | sqm | 5566.6092 | 0
| VAT calculation | [7 empty] | 0
10 | Traditional Nago Brick work in (1:1:2) lime,surkhi, sand mortar
| -At ground floor | 0 | 0 |  |  | 0
| Sub-total |  |  |  |  | 0 | rm | 467.6783 | 0
| VAT calculation | [7 empty] | 0
11 | cu¦fv sf7sf] rf}s; agfO hf]8\g] sfd
| Door | 0 | 0 | 0 | 0 | 0
| Sub-total |  |  |  |  | 0 | cum | 283082.83 | 0
| VAT calculation | [7 empty] | 0
12 | Carved salwood Lattice (jali) of Carved Window and door (second type) including wood
| Window | 0 | 0 |  | 0 | 0
|  | 0 | 0 |  | 0 | 0
| Door | 0 | 0 |  | 0 | 0
| Sub-total |  |  |  |  | 0 | sqm | 34296.1957 | 0
| VAT calculation | [7 empty] | 0
13 | Provisional sum for lab test | 1 |  |  |  | 1 | PS | 15000 | 15000
17 | 20 gauge Brass plate making and fixing on roof
| -Slab | 2 | 3.3526 | 0.45 |  | 3.0174
|  | 2 | 2.4383 | 0.45 |  | 2.1945
| -Inclined Surface | 4 | 1.4224 | 1.2 |  | 6.8277
| Sub-total |  |  |  |  | 0 | sqm | 3251.8875 | 0
| -VAT 13% for materials | [7 empty] | 0
14 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 873283.9054
| Total Valuated | 873283.9054 |  | 100
| Budget allocated | 1000000 | [8 empty] | 10484.6466 | 688491.7913
| Municipal payment | 698976.4379 |  | 80.04
| User Contribution | 174307.4675 |  | 19.96 | [6 empty] | from centre | total
| Contingencies | 30000 |  | 3 | [6 empty] | 11m | 22m
| Maintanince | 20000 |  | 2
hanumante
Note: | All the dimensions are taken as per the direction/instruction of senior engineer and the design, dimensions and rates should be first verified and approved by senior engineer of Shankharapur Municipality then only the valuation is authentic.
Note on D30: DELL: need to be confirmed
Note on E33: DELL: need to be checked in field
Note on D42: DELL: (13.5+5)/2
Note on D45: DELL: need to be checked at field
Note on D58: DELL: need to be confirmed
Note on D73: DELL: (13.5+5)/2
Note on F76: DELL: need to be checked at field

## m (2)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- लाकिला गणेश मन्दिर निर्माण | [6 empty] | F.Y.: 2080/81
Location:- Shankharapur Municipality 9 | [6 empty] | Date:
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
A | For Protection work
1 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] k'g]{ sfd
| -For foundation | 1 | 2.8193 | 2.8193 | 1.5 | 11.9224
| Sub-total |  |  |  |  | 11.9224 | cum | 648.9 | 7736.42
2 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -For foundation | 1 | 2.8193 | 2.8193 |  | 7.9482 |  |  |  |  | 7.25
| -For flooring | 1 | 2.2097 | 2.2097 |  | 4.8827
| Sub-total |  |  |  |  | 12.831 | sqm | 985.38 | 12643.3911
| -VAT 13% for materials | [7 empty] | 1393.4384
3 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd-lk=;L=;L= !M#M^_
| -For foundation | 1 | 2.8193 | 2.8193 | 0.075 | 0.59612
| Sub-total |  |  |  |  | 0.59612 | cum | 12300.32 | 7332.4427
| -VAT 13% for materials | [7 empty] | 581.2407
4 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
-For footing
| -Rectangular portion | 1 | 2.8193 | 2.8193 | 0.55877 | 4.4413
| -Neck column | 4 | 0.3 | 0.3 | 0.9 | 0.324 |  |  |  |  | 0.83333 | 0.25399 | 3.02 | 0.92045 | 4.4666 | 4.2366
| -Upper plinth beam | 4 | 2.09 | 0.23 | 0.23 | 0.44224
| -Shear wall footing | 2 | 2.67 | 0.50798 | 0.23 | 0.6239 |  |  |  |  | 0.76196 |  |  |  | 37.5 | 3.125
|  | 1 | 1.684 | 0.50798 | 0.23 | 0.19675
| -For flooring including peti | 1 | 1.6519 | 1.854 | 0.075 | 0.2297
| -Shear wall | 1 | 2.09 | 0.23 | 2.4901 | 1.197 |  |  |  |  | 8.163 | 2.488 | 6.8573
|  | 2 | 2.09 | 0.15239 | 2.4901 | 1.5862 |  |  |  |  | 8.7603
| -Column | 4 | 0.3 | 0.3 | 2.7178 | 0.9784 | [6 empty] | 8.9243
| -Beam | 4 | 3.886 | 0.23 | 0.23 | 0.82228 |  |  |  |  | 12.75
| -Ground floor slab | 1 | 4.45 | 4.55 | 0.125 | 2.5309
| -1st floor column | 4 | 0.3 | 0.3 | 2.6416 | 0.95097 |  |  |  |  | 8.92
| -Beam | 4 | 3.2764 | 0.23 | 0.23 | 0.69329 |  |  |  |  | 10.75
| -Secondary beam | 2 | 2.2097 | 0.23 | 0.23 | 0.23379
| -1st floor slab | 1 | 4.45 | 4.55 | 0.127 | 2.5714
| -1st floor Inclined Surface | 4 | 3.0738 | 1.8034 | 0.1016 | 2.2527 |  |  |  |  | 3.0098 | 9.875
| -column | 4 | 1.0667 | 0.3 | 0.3 | 0.38403
| -beam | 4 | 0.91436 | 0.23 | 0.23 | 0.19348
| -column | 4 | 0.67 | 0.3 | 0.3 | 0.2412
| -beam | 4 | 2.1335 | 0.17769 | 0.19049 | 0.28886 |  |  |  |  | 7 | 2.1335 | 7
| -slab | 1 | 3.3526 | 3.3526 | 0.1016 | 1.1419
| -deduction for hollow part | -1 | 1.0667 | 1.0667 | 0.1016 | -0.11561
| -column | 4 | 0.3 | 0.30479 | 0.3 | 0.10972 |  |  |  |  | 1.25
| -inclined slab | 4 | 1.943 | 1.2953 | 0.088896 | 0.89495 |  |  |  |  | 23.2134
| Sub-total |  |  |  |  | 23.2134 | cum | 14200.82 | 329648.9203
| -VAT 13% for materials | [7 empty] | 30931.8788
5 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
-For footing
| -Rectangular portion | 4 | 2.8193 |  | 0.55877 | 6.3013
| -Neck column | 4 | 1.2 |  | 0.9 | 4.32 |  |  |  |  | 0.83333 | 0.25399 | 3.02 | 0.92045 | 4.4666 | 4.2366
| -Shear wall footing | 2 | 5.35 |  | 0.23 | 2.461 |  |  |  |  | 0.76196 |  |  |  | 37.5 | 3.125
|  | 1 | 3.1649 |  | 0.23 | 0.72793 |  |  |  |  | 2.0573 | 5.6367
| -Shear wall | 1 | 7.975 |  | 2.4901 | 19.8585 |  |  |  |  | 8.163 | 2.488 | 6.8573
|  | 3 | 2.09 |  | 2.4901 | 15.6129 |  |  |  |  | 8.7603 | 8.163
| -column | 4 | 0.3 |  | 2.4901 | 2.9881
|  | 1 | 0.45718 |  | 2.4901 | 1.1384
| -Beam | 4 | 3.9622 |  | 0.43178 | 6.8432 |  |  |  |  | 13
| -Ground floor slab | 1 | 4.45 | 4.55 |  | 20.2475
| slab edge | 1 | 17.8 |  | 0.125 | 2.225
| -deduction for beam | -4 | 3.2764 | 0.15 |  | -1.9659
| -1st floor column | 4 | 1.2 |  | 2.4383 | 11.7037 |  |  |  |  | 8.92 | 8.75 | 2.6669
| -Beam | 4 | 3.2764 |  | 0.43178 | 5.6588 |  |  |  |  | 10.75 | 8 | 2.4383
| -Secondary beam | 2 | 2.2097 |  | 0.46 | 2.0329
| -1st floor slab | 1 | 4.45 | 4.55 | 0.125 | 2.5309
| slab edge | 1 | 17.8 |  | 0.125 | 2.225
| -1st floor Inclined Surface | 4 | 3.0738 | 1.8034 |  | 22.173 |  |  |  |  | 3.0098 | 9.96
| -column | 4 | 1.2 |  | 0.99665 | 4.7839
| -beam | 4 | 0.91436 |  | 0.46 | 1.6824
| -column | 4 | 1.2 |  | 0.67 | 3.216
| -beam | 4 | 2.1335 |  | 0.35538 | 3.0328 |  |  |  |  | 7 | 2.1335 | 7
| -slab | 1 | 3.3526 | 3.3526 |  | 11.2402
| slab edge | 1 | 13.4105 |  | 0.1 | 1.3411
| -deduction for hollow part | -1 | 1.0667 | 1.0667 |  | -1.138
| -column | 4 | 1.2 |  | 0.3 | 1.44
| -inclined slab | 4 | 1.9049 | 1.2953 |  | 9.87 |  |  |  |  | 162.5508
| top roof floor | 1 | 0.45718 | 0.45718 |  | 0.20901
| Sub-total |  |  |  |  | 162.7598 | sqm | 905.97 | 147455.499
| -VAT 13% for materials | [7 empty] | 9908.2034
[12 empty] | 192 | 47.9373 | 191.7491
6 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit weight (m) | Total weight (kg) | Total weight (M.T.) |  |  |  |  | 13.75 | 27.5
| -For footing | 70 | 3.505 | 0.88889 | 218.0907 | 0.21809 |  |  |  |  | 4.085 | 12.2673 | 8.17
| -column | 32 | 7.772 | 0.88889 | 221.0708 | 0.22107
|  | 16 | 0.75 | 0.88889 | 10.6667 | 0.010667
| - column stirrups | 65 | 1.018 | 0.39506 | 26.1408 | 0.026141
|  | 65 | 0.71076 | 0.39506 | 18.2516 | 0.018252
| -plinth beam | 16 | 3.7336 | 0.88889 | 53.1003 | 0.0531 |  |  |  |  | 34
| -Stirrups | 76 | 0.81439 | 0.39506 | 24.4517 | 0.024452 |  |  |  |  | 11.246 | 684 | 2.2442
| -shear wall horizontal bars | 18 | 7.15 | 0.39506 | 50.8444 | 0.050844
| -shear wall vertical bars | 42 | 3.4288 | 0.88889 | 128.0098 | 0.12801 |  |  |  |  | 7.75 | 11.413
| -GF Beam | 20 | 4.4956 | 0.88889 | 79.9214 | 0.079921 |  |  |  |  | 78 | 29.25 | 2.4375
| -Stirrups | 134 | 0.81439 | 0.39506 | 43.1122 | 0.043112 | [5 empty] | 2.7431
| -Slab | 26 | 4.3703 | 0.61728 | 70.1404 | 0.07014
|  | 78 | 4.4465 | 0.39506 | 137.0174 | 0.13702
| -1st floor beam | 20 | 4.8522 | 0.88889 | 86.261 | 0.086261 |  |  |  |  | 78 | 29.25 | 2.4375
| -Stirrups | 118 | 0.81439 | 0.39506 | 37.9645 | 0.037964 | [5 empty] | 2.7431
| -Secondary beam | 12 | 1.9811 | 0.88889 | 21.1318 | 0.021132
| -Stirrups | 28 | 0.91618 | 0.39506 | 10.1346 | 0.010135
| -Slab doubly reinforcement | 52 | 4.9703 | 0.39506 | 102.1056 | 0.10211 | [5 empty] | #REF!
|  | 52 | 4.4465 | 0.39506 | 91.345 | 0.091345
| -1st floor inclined slab | [9 empty] | 1.538
| -horizontal bars | 44 | 3.0098 | 0.61728 | 81.7464 | 0.081746 |  |  |  |  | 9.25 | 5.75 | 17.2673 | 34.5345
| -vertical bars | 40 | 1.6763 | 0.39506 | 26.49 | 0.02649
|  | 32 | 1.2191 | 0.39506 | 15.4123 | 0.015412
|  | 32 | 1.2191 | 0.39506 | 15.4123 | 0.015412
| -Column from1st floor to roof floor | 32 | 2.996 | 0.88889 | 85.2206 | 0.085221
| -Stirrups | 36 | 1.018 | 0.39506 | 14.478 | 0.014478
|  | 36 | 0.60957 | 0.39506 | 8.6694 | 0.0086694
| -2nd floor beam | 16 | 1.5239 | 0.88889 | 21.6736 | 0.021674 | [5 empty] | 0.684
| -Stirrups | 32 | 0.81439 | 0.39506 | 10.2954 | 0.010295
| -2nd floor slab | 24 | 3.2764 | 0.39506 | 31.0655 | 0.031066
|  | 24 | 3.8098 | 0.39506 | 36.1227 | 0.036123
|  | 28 | 1.0424 | 0.39506 | 11.5304 | 0.01153
|  | 28 | 1.3472 | 0.39506 | 14.9018 | 0.014902
| -2nd floor upper beam | 16 | 2.0573 | 0.88889 | 29.2594 | 0.029259 | [5 empty] | 0.684
| -Stirrups | 32 | 0.56385 | 0.39506 | 7.1282 | 0.0071282
| -2nd floor inclined slab | [9 empty] | 35 | 56
| -horizontal bars | 10 | 1.8668 | 0.39506 | 7.375 | 0.007375 |  |  |  |  | 0.88896
| -vertical bars | 16 | 1.5239 | 0.39506 | 9.6327 | 0.0096327
|  | 8 | 1.3715 | 0.39506 | 4.3347 | 0.0043347
|  | 8 | 1.2191 | 0.39506 | 3.8531 | 0.0038531
|  | 8 | 1.016 | 0.39506 | 3.2109 | 0.0032109
|  | 8 | 0.91436 | 0.39506 | 2.8898 | 0.0028898
|  | 8 | 0.76196 | 0.39506 | 2.4082 | 0.0024082
|  | 8 | 0.50798 | 0.39506 | 1.6055 | 0.0016055
| Sub-total |  |  |  |  | 1.8745
| -wastage 2% |  |  |  |  | 0.03749
| total |  |  |  |  | 1.912 | M.T | 130210 | 248957.0944
| -VAT 13% for materials | [7 empty] | 26100.8216
7 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -At between lower and upper tie beam | 4 | 2.0573 | 0.23 | 1.15 | 2.1766
| Sub-total |  |  |  |  | 2.1766 | cum | 14520.78 | 31606.2634 |  | 34594.555 | 8405.445
| -VAT 13% for materials | [7 empty] | 2988.2916
8 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M$_ df
| -At Ground floor | 0 | 0 | 0 | 0 | 0
| -Deduction for window | 0 | 0 | 0 | 0 | 0
| -Deduction for door | 0 | 0 | 0 | 0 | 0
| -At horizontal roof slab | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
| -Deduction for window | 0 | 0 | 0 | 0 | 0
| Sub-total |  |  |  |  | 0 | cum | 14911.97 | 0
| -VAT 13% for materials | [7 empty] | 0
9 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -At basement | 4 | 2.2097 |  | 4.267 | 37.715
| -Deduction for window | -1 | 0.9 |  | 1.2 | -1.08
| -Deduction for door | -1 | 0.9 |  | 2.1335 | -1.9201
| -At Ground floor | 0 | 2.2097 |  | 1.1938 | 0
| -Deduction for window | 0 | 0 |  | 0.45 | 0
| -Deduction for door | 0 | 0 |  | 1.1938 | 0
| -Basement floor ceiling | 0 | 2.2097 | 2.2097 |  | 0
| Sub-total |  |  |  |  | 0 | sqm | 402.23 | 0
| -VAT 13% for materials | [7 empty] | 0
9 | Traditional Brick (Small Dachi Appa) work in (1:1:2) lime, surkhi, sand mortar
| -At Ground floor | 0 | 0 |  | 0 | 0
| -Deduction for window | 0 | 0 |  | 0 | 0
| -Deduction for door | 0 | 0 |  | 0 | 0
| Sub-total |  |  |  |  | 0 | sqm | 5566.6092 | 0
| VAT calculation | [7 empty] | 0
10 | Traditional Nago Brick work in (1:1:2) lime,surkhi, sand mortar
| -At ground floor | 0 | 0 |  |  | 0
| Sub-total |  |  |  |  | 0 | sqm | 467.6783 | 0
| VAT calculation | [7 empty] | 0
11 | cu¦fv sf7sf] rf}s; agfO hf]8\g] sfd
| Door | 0 | 0 | 0 | 0 | 0
| Sub-total |  |  |  |  | 0 | cum | 283082.83 | 0
| VAT calculation | [7 empty] | 0
12 | Carved salwood Lattice (jali) of Carved Window and door (second type) including wood
| Window | 0 | 0 |  | 0 | 0
|  | 0 | 0 |  | 0 | 0
| Door | 0 | 0 |  | 0 | 0
| Sub-total |  |  |  |  | 0 | sqm | 34296.1957 | 0
| VAT calculation | [7 empty] | 0
13 | Provisional sum for lab test | 1 |  |  |  | 1 | PS | 15000 | 15000
17 | 20 gauge Brass plate making and fixing on roof
| -Slab | 2 | 3.3526 | 0.45 |  | 3.0174
|  | 2 | 2.4383 | 0.45 |  | 2.1945
| -Inclined Surface | 4 | 1.4224 | 1.2 |  | 6.8277
| Sub-total |  |  |  |  | 0 | sqm | 3251.8875 | 0
| -VAT 13% for materials | [7 empty] | 0
14 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand Total | [7 empty] | 873283.9054
| Total Valuated | 873283.9054 |  | 100
| Budget allocated | 1000000 | [8 empty] | 10484.6466 | 688491.7913
| Municipal payment | 698976.4379 |  | 80.04
| User Contribution | 174307.4675 |  | 19.96 | [6 empty] | from centre | total
| Contingencies | 30000 |  | 3 | [6 empty] | 11m | 22m
| Maintanince | 20000 |  | 2
hanumante
Note: | All the dimensions are taken as per the direction/instruction of senior engineer and the design, dimensions and rates should be first verified and approved by senior engineer of Shankharapur Municipality then only the estimate is authentic.
Note on D30: DELL: need to be confirmed
Note on E33: DELL: need to be checked in field
Note on D42: DELL: (13.5+5)/2
Note on D45: DELL: need to be checked at field
Note on D58: DELL: need to be confirmed
Note on D73: DELL: (13.5+5)/2
Note on F76: DELL: need to be checked at field