## final (2)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- गणपति गणेश मन्दिर निर्माण | [6 empty] | F.Y.: 2080/2081
Location:- Shankharapur Municipality 9 | [6 empty] | Date: 2080/08/24
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -For beam | 2 | 3.4044 | 0.23 | 0.23 | 0.36019
|  | 2 | 2.997 | 0.23 | 0.23 | 0.31708
| -For 1st roof | 4 | 2.9457 | 1.9049 | 0.1 | 2.2446 |  |  |  |  | 1.9049 | 1.8974
| -For shear wall | 4 | 1.2191 | 0.60957 | 0.1 | 0.29726 |  |  |  |  | 1.3206 | 1.363
| -For top roof | 4 | 1.2191 | 1.3206 | 0.075 | 0.48301
| Sub-total |  |  |  |  | 3.7021 | cum | 14200.82 | 52572.7305 |  | 99694.2706
| -VAT calculation | [7 empty] | 4933.0461
2 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -For beam | 1 | 13.7153 |  | 0.46 | 6.3091
|  | 1 | 11.8866 |  | 0.46 | 5.4678
| -For 1st roof | 4 | 1.9049 | 2.9457 |  | 22.4455
| -For shear wall | 4 | 1.2191 | 0.60957 |  | 2.9726
| -For top roof | 4 | 1.2191 | 1.3206 |  | 6.4402
| Sub-total |  |  |  |  | 43.6352 | sqm | 905.97 | 39532.1496
| -VAT 13% for materials | [7 empty] | 2656.3443
3 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit weight (m) | Total weight (kg) | Total weight (M.T.)
| -For beam | 8 | 11.83 | 0.88889 | 84.1244 | 0.084124
|  | 8 | 11.99 | 0.88889 | 85.2622 | 0.085262
| -For 1st roof horizontal bar | 48 | 2.5 | 0.39506 | 47.4074 | 0.047407
| -For 1st roof vertical bar | 72 | 1.9049 | 0.39506 | 54.184 | 0.054184
| -For shear wall horizontal bar | 12 | 1.2191 | 0.39506 | 5.7796 | 0.0057796
| -For shear wall vertical bar | 28 | 0.60957 | 0.39506 | 6.7429 | 0.0067429
| -For top roof horizontal bar | 32 | 1.2191 | 0.39506 | 15.4123 | 0.015412
| -For top roof vertical bar | 28 | 1.3206 | 0.39506 | 14.6085 | 0.014608
| Sub-total |  |  |  |  | 0.31352 | M.T | 130210 | 40823.6299
| -VAT 13% for materials | [7 empty] | 4279.9756
4 | !@=% dL=dL= l;d]G6 afn'jf -!M^_ Knfi6/ |  |  | Area
| -outer face of wall | 2 | 3.4044 |  | 2.5907 | 17.6396
|  | 2 | 3.4532 |  | 2.5907 | 17.8923
| -inner face of wall | 2 | 2.9473 |  | 2.5907 | 15.2708
|  | 2 | 2.996 |  | 2.5907 | 15.5235
| -Deduction for opening | -3 | 1.4477 |  | 1.2191 | -5.295
|  | -3 |  | 1.3133 |  | -3.9398
|  | -6 | 0.38098 |  | 0.38098 | -0.87088
| Sub-total |  |  |  |  | 56.2207 | sqm | 382.48 | 21503.2882
| -VAT 13% for materials | [7 empty] | 690.5717
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand total | [7 empty] | 167991.736
| Total Estimated | 167991.736 |  | 100
| Budget allocated | 150000
| Municipal payment | 142500 |  | 84.8256
| User Contribution | 25491.736 |  | 15.1744
| Contingencies | 4500 |  | 3
| Maintanince | 3000 |  | 2

## valuated
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- गणपति गणेश मन्दिर निर्माण | [6 empty] | F.Y.: 2080/2081
Location:- Shankharapur Municipality 9 | [6 empty] | Date: 2080/11/06
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -For beam | 2 | 3.4288 | 0.23 | 0.23 | 0.36277
|  | 2 | 3.0731 | 0.23 | 0.23 | 0.32514 |  |  |  |  | 0.1016
| -For 1st roof short side | 2 | 3.0224 | 1.7016 | 0.11 | 1.1315 | [5 empty] | 1.7016 | 1.8974
| -For 1st roof long side | 2 | 3.0352 | 1.9049 | 0.101 | 1.1679
| -For shear wall short side | 2 | 1.3969 | 0.60957 | 0.101 | 0.17201 | [5 empty] | 1.1175 | 1.363
| -For shear wall long side | 2 | 1.4985 | 0.60957 | 0.101 | 0.18452
| -For top roof short side | 2 | 1.2069 | 1.1175 | 0.08 | 0.21581
| -For top roof long side | 2 | 1.2064 | 1.1175 | 0.08 | 0.21572
| Sub-total |  |  |  |  | 3.7753 | cum | 14200.82 | 53612.925 |  |  | 97155.2211
| -VAT calculation | [7 empty] | 5030.6505
2 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -For beam | 2 | 3.5303 |  | 0.46 | 3.2479
|  | 2 | 3.4227 |  | 0.46 | 3.1489
| -For 1st roof short side | 2 | 1.7016 | 3.0224 |  | 10.2859
| -For 1st roof long side | 2 | 3.0352 | 1.9049 |  | 11.5636
| -edge | 1 | 18.4395 |  | 0.1 | 1.844
| -For shear wall short side | 2 | 1.3969 |  | 0.60957 | 1.7031
| -For shear wall long side | 2 | 1.4985 |  | 0.60957 | 1.8269
| -For top roof short side | 2 | 1.2069 | 1.1175 |  | 2.6976
| -For top roof long side | 2 | 1.2064 | 1.1175 |  | 2.6965
| -edge | 1 | 8.1786 |  | 0.1 | 0.81786
| Sub-total |  |  |  |  | 39.8322 | sqm | 905.97 | 36086.8093
| -VAT 13% for materials | [7 empty] | 2424.8363
3 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit weight (m) | Total weight (kg) | Total weight (M.T.)
| -For beam | 8 | 3.5538 | 0.88889 | 25.2714 | 0.025271
|  | 8 | 3.4776 | 0.88889 | 24.7296 | 0.02473
| -stirrups | 60 | 8.6376 | 0.39506 | 204.7434 | 0.20474
| -For 1st roof horizontal bar | 14 | 2.1335 | 0.39506 | 11.8001 | 0.0118
|  | 14 | 2.2097 | 0.39506 | 12.2215 | 0.012222
| -For 1st roof vertical bar | 28 | 1.854 | 0.39506 | 20.5085 | 0.020509
|  | 12 | 0.40536 | 0.39506 | 1.9217 | 0.0019217
| -Cantilever bars | 6 | 4.5718 | 0.39506 | 10.8368 | 0.010837
| -For shear wall horizontal bar | 8 | 1.3968 | 0.39506 | 4.4147 | 0.0044147
|  | 8 | 1.4986 | 0.39506 | 4.7364 | 0.0047364
| -For shear wall vertical bar | 32 | 0.60957 | 0.39506 | 7.7062 | 0.0077062
| -For top roof horizontal bar | 14 | 1.1683 | 0.39506 | 6.4619 | 0.0064619
| -For top roof vertical bar | 10 | 1.1175 | 0.39506 | 4.415 | 0.004415
| Sub-total |  |  |  |  | 0.33977 | M.T | 130210 | 44241.089 |  |  | 4940
| -VAT 13% for materials | [7 empty] | 4638.2642
4 | !@=% dL=dL= l;d]G6 afn'jf -!M^_ Knfi6/ |  |  | Area
| -outer face of wall | 2 | 3.4044 |  | 2.5907 | 17.6396
|  | 2 | 3.4532 |  | 2.5907 | 17.8923
| -inner face of wall | 2 | 2.9473 |  | 2.5907 | 15.2708
|  | 2 | 2.996 |  | 2.5907 | 15.5235
| -Deduction for opening | -3 | 1.4477 |  | 1.2191 | -5.295
|  | -3 |  | 1.3133 |  | -3.9398
|  | -6 | 0.38098 |  | 0.38098 | -0.87088
| Sub-total |  |  |  |  | 56.2207 | sqm | 382.48 | 21503.2882
| -VAT 13% for materials | [7 empty] | 690.5717
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand total | [7 empty] | 169228.4342
| Total Valuated | 169228.4342 |  | 100
| Budget allocated | 150000
| Municipal payment | 142500 |  | 84.2057
| User Contribution | 26728.4342 |  | 15.7943
| Contingencies | 4500 |  | 3
| Maintanince | 3000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 167991.736 |  |  |  |  | Total Valuated Amount : |  | 169228.4342
Work Started : | [7 empty] | Work Finished:
Project:- गणपति गणेश मन्दिर निर्माण | [7 empty] | F.Y:2080/81
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2080/11/06
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_ | cum | 3.7021 | 14200.82 | 52572.7305 | 3.7753 | 14200.82 | 53612.925 | 1040.1945 |  | 65715.9131
| -VAT calculation |  |  |  | 4933.0461 |  |  | 5030.6505 | 97.6044 |  | 6166.3077
2 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd | sqm | 43.6352 | 905.97 | 39532.1496 | 39.8322 | 905.97 | 36086.8093 | -3445.3403 |  | 49415.187
| -VAT 13% for materials |  |  |  | 2656.3443 |  |  | 2424.8363 | -231.508 |  | 3320.4304
3 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | M.T | 0.31352 | 130210 | 40823.6299 | 0.33977 | 130210 | 44241.089 | 3417.4591 |  | 51029.5374
| -VAT 13% for materials |  |  |  | 4279.9756 |  |  | 4638.2642 | 358.2886 |  | 5349.9695
4 | !@=% dL=dL= l;d]G6 afn'jf -!M^_ Knfi6/ | sqm | 56.2207 | 382.48 | 21503.2882 | 56.2207 | 382.48 | 21503.2882 | 0 |  | 26879.1103
| -VAT 13% for materials |  |  |  | 690.5717 |  |  | 690.5717 | 0 |  | 863.2147
5 | Information board (सुचना पाटि) | no. | 1 | 1000 | 1000 | 1 | 1000 | 1000 | 0 |  | 1250
| Total |  |  |  | 167991.736 |  |  | 169228.4342 | 1236.6982

## measurement
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- गणपति गणेश मन्दिर निर्माण | [9 empty] | F.Y.: 2080/2081
Location:- Shankharapur Municipality 9 | [9 empty] | Date: 2080/11/06
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remark
1 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -For beam | 2 | 3.4288 | 0.23 | 0.23 | 0.36277
|  | 2 | 3.0731 | 0.23 | 0.23 | 0.32514 |  |  |  |  | 0.1016
| -For 1st roof short side | 2 | 3.0224 | 1.7016 | 0.11 | 1.1315 | [5 empty] | 1.7016 | 1.8974
| -For 1st roof long side | 2 | 3.0352 | 1.9049 | 0.101 | 1.1679
| -For shear wall short side | 2 | 1.3969 | 0.60957 | 0.101 | 0.17201 | [5 empty] | 1.1175 | 1.363
| -For shear wall long side | 2 | 1.4985 | 0.60957 | 0.101 | 0.18452
| -For top roof short side | 2 | 1.2069 | 1.1175 | 0.08 | 0.21581
| -For top roof long side | 2 | 1.2064 | 1.1175 | 0.08 | 0.21572
| Sub-total |  |  |  |  | 3.7753 | cum | 14200.82 | 53612.925 |  |  | 97155.2211
| -VAT calculation | [7 empty] | 5030.6505
2 | kmnfd]sf] kfOk / KnfOaf]8{af6 kmdf{ agfpg] sfd
| -For beam | 2 | 3.5303 |  | 0.46 | 3.2479
|  | 2 | 3.4227 |  | 0.46 | 3.1489
| -For 1st roof short side | 2 | 1.7016 | 3.0224 |  | 10.2859
| -For 1st roof long side | 2 | 3.0352 | 1.9049 |  | 11.5636
| -edge | 1 | 18.4395 |  | 0.1 | 1.844
| -For shear wall short side | 2 | 1.3969 |  | 0.60957 | 1.7031
| -For shear wall long side | 2 | 1.4985 |  | 0.60957 | 1.8269
| -For top roof short side | 2 | 1.2069 | 1.1175 |  | 2.6976
| -For top roof long side | 2 | 1.2064 | 1.1175 |  | 2.6965
| -edge | 1 | 8.1786 |  | 0.1 | 0.81786
| Sub-total |  |  |  |  | 39.8322 | sqm | 905.97 | 36086.8093
| -VAT 13% for materials | [7 empty] | 2424.8363
3 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit weight (m) | Total weight (kg) | Total weight (M.T.)
| -For beam | 8 | 3.5538 | 0.88889 | 25.2714 | 0.025271
|  | 8 | 3.4776 | 0.88889 | 24.7296 | 0.02473
| -stirrups | 60 | 8.6376 | 0.39506 | 204.7434 | 0.20474
| -For 1st roof horizontal bar | 14 | 2.1335 | 0.39506 | 11.8001 | 0.0118
|  | 14 | 2.2097 | 0.39506 | 12.2215 | 0.012222
| -For 1st roof vertical bar | 28 | 1.854 | 0.39506 | 20.5085 | 0.020509
|  | 12 | 0.40536 | 0.39506 | 1.9217 | 0.0019217
| -Cantilever bars | 6 | 4.5718 | 0.39506 | 10.8368 | 0.010837
| -For shear wall horizontal bar | 8 | 1.3968 | 0.39506 | 4.4147 | 0.0044147
|  | 8 | 1.4986 | 0.39506 | 4.7364 | 0.0047364
| -For shear wall vertical bar | 32 | 0.60957 | 0.39506 | 7.7062 | 0.0077062
| -For top roof horizontal bar | 14 | 1.1683 | 0.39506 | 6.4619 | 0.0064619
| -For top roof vertical bar | 10 | 1.1175 | 0.39506 | 4.415 | 0.004415
| Sub-total |  |  |  |  | 0.33977 | M.T | 130210 | 44241.089 |  |  | 4940
| -VAT 13% for materials | [7 empty] | 4638.2642
4 | !@=% dL=dL= l;d]G6 afn'jf -!M^_ Knfi6/ |  |  | Area
| -outer face of wall | 2 | 3.4044 |  | 2.5907 | 17.6396
|  | 2 | 3.4532 |  | 2.5907 | 17.8923
| -inner face of wall | 2 | 2.9473 |  | 2.5907 | 15.2708
|  | 2 | 2.996 |  | 2.5907 | 15.5235
| -Deduction for opening | -3 | 1.4477 |  | 1.2191 | -5.295
|  | -3 |  | 1.3133 |  | -3.9398
|  | -6 | 0.38098 |  | 0.38098 | -0.87088
| Sub-total |  |  |  |  | 56.2207 | sqm | 382.48 | 21503.2882
| -VAT 13% for materials | [7 empty] | 690.5717
5 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 1000 | 1000
| Grand total | [7 empty] | 169228.4342
| Total Valuated | 169228.4342 |  | 100
| Budget allocated | 150000
| Municipal payment | 142500 |  | 84.2057
| User Contribution | 26728.4342 |  | 15.7943
| Contingencies | 4500 |  | 3
| Maintanince | 3000 |  | 2