## Estimate (3)
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- गणपति ढिकुरेपाटी संरक्षण | [6 empty] | F.Y.: 2081/2082 | [5 empty] | subservience
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/09/28
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks |  | 45m
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य) | [10 empty] | 13m | ht=3'9"
| -For stone masonary | 0.5 | 11.8 | 1.5 | 2 | 17.7
| Sub-total |  |  |  |  | 17.7 | m3 | 64.63 | 1143.951
| VAT calculation | [7 empty] | 123.2569
2 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -for footing of wall at truss structure | 2 | 3.4014 | 0.35 | 0.75 | 1.7857
|  | 2 | 6.6047 | 0.35 | 0.75 | 3.4675
| Sub-total |  |  |  |  | 5.2532 | m3 | 663.31 | 3484.5003
3 | 3fF; sf6\g] To;sf] h/f lemSg], l9:sf] k'm6fpg] / n]en u/L :yn ;kmf ug]{ ;a} jf]sgL ;d]t
| -Surrounding environment | 1 | 7.772 | 0.8 |  | 6.2176
|  | 1 | 3.9113 | 0.3 |  | 1.1734
| Sub-total |  |  |  |  | 7.391 | sqm | 21.16 | 156.3937
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing of wall at truss structure | 2 | 3.4014 | 0.35 |  | 2.381
|  | 2 | 6.6047 | 0.35 |  | 4.6233
| Sub-total |  |  |  |  | 7.0043 | sqm | 1014.97 | 7109.1209
| VAT calculation | [7 empty] | 784.6432
5 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | [11 empty] | 3fF; sf6\g] To;sf] h/f lemSg], l9:sf] k'm6fpg] / n]en u/L :yn ;kmf ug]{ ;a} jf]sgL ;d]t
| -For stone masonary | 1 | 11.8 | 1.5 | 0.15 | 2.655
| Sub-total |  |  |  |  | 2.655 | m3 | 4434.52 | 11773.6506
| VAT calculation | [7 empty] | 1022.8589
6 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For stone masonary | 1 | 11.8 | 1.5 | 0.075 | 1.3275
|  | 1 | 11.8 | 0.45 | 0.05 | 0.2655
| -for footing of wall at truss structure | 2 | 3.4014 | 0.35 | 0.075 | 0.17857
|  | 2 | 6.6047 | 0.35 | 0.075 | 0.34675
| -For sill/lintel/DPC band | 2 | 6.8333 | 0.23 | 0.15 | 0.4715
|  | 2 | 3.8098 | 0.23 | 0.15 | 0.26288
| Sub-total |  |  |  |  | 2.8527 | m3 | 10634.5 | 30336.9711
| VAT calculation | [7 empty] | 2992.578
7 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -For stone masonary | 1 | 11.8 | 0.975 | 3 | 34.515
| Sub-total |  |  |  |  | 34.515 | m3 | 9709.43 | 335120.9765
| VAT calculation | [7 empty] | 24312.1796
8 | k'/fgf] ;km]{;df XjfO{6jfz ug]{ sfd
| -wall | 1 | 23.9762 |  | 2.7431 | 65.7684
|  | 1 | 24.2301 |  | 2.5907 | 62.7723
| -deduction for door | -2 | 0.91436 |  | 2.1335 | -3.9015
|  | -2 | 0.76196 |  | 1.8287 | -2.7868
| -deduction for window | -2 | 1.0667 |  | 1.2191 | -2.601
| -as of plaster | 1 |  |  |  | 44.9398
| Sub-total |  |  |  |  | 164.1911 | sqm | 20.82 | 3418.4589
| VAT calculation | [7 empty] | 97.8448
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | [10 empty] | 37.666
| -for footing of wall at truss structure | 2 | 3.4014 | 0.35 | 0.2 | 0.4762 |  |  |  |  | 11.6324 | 11.48 |  | 0.6
|  | 2 | 3.4014 | 0.23 | 1.3 | 2.034
|  | 2 | 6.6047 | 0.35 | 0.2 | 0.92466
|  | 2 | 6.6047 | 0.23 | 1.3 | 3.9496
| -deduction for entrance | -1 | 1.2 | 0.23 | 0.9 | -0.2484
| Sub-total |  |  |  |  | 7.1361 | m3 | 14362.76 | 102494.0719
| VAT calculation | [7 empty] | 9566.1272 |  | 4.267
10 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For bands | 4 | 22.2005 | 0.61728 | 54.8162 | 0.054816
| -For stirrups | 144 | 0.27939 | 0.39506 | 15.894 | 0.015894
| Sub-total |  |  |  |  | 0.07071 | MT | 131940 | 9329.4971
| VAT calculation | [7 empty] | 976.2243
11 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 2 | 12.4666 |  | 0.9 | 22.4398
|  | 2 | 12.5 |  | 0.9 | 22.5
| Sub-total |  |  |  |  | 44.9398 | sqm | 405.86 | 18239.2742
| VAT calculation | [7 empty] | 652.3491
12 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
7.8744
| Grand Total | [7 empty] | 563634.9281
| Total Estimated | 563634.9281 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 84.2744
| User Contribution | 88634.9281 |  | 15.7256
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on B56: DELL: item no. 10
Note on D61: DELL: column part not included

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 563634.9281 |  |  |  |  | Total Valuated Amount : |  | 564688.3131
Work Started : | [7 empty] | Work Finished:
Project:- गणपति ढिकुरेपाटी संरक्षण | [7 empty] | F.Y:2081/82
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2081/12/06
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य) | m3 | 17.7 | 64.63 | 1143.951 | 20.784 | 64.63 | 1343.2699 | 199.3189 |  | 1429.9388 | TRUE
| VAT calculation |  |  |  | 123.2569 |  |  | 144.7328 | 21.4759 |  | 154.0711 | TRUE
2 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | m3 | 5.2532 | 663.31 | 3484.5003 | 1.6865 | 663.31 | 1118.6557 | -2365.8445 |  | 4355.6253 | TRUE
0
3 | 3fF; sf6\g] To;sf] h/f lemSg], l9:sf] k'm6fpg] / n]en u/L :yn ;kmf ug]{ ;a} jf]sgL ;d]t | sqm | 7.391 | 21.16 | 156.3937 | 7.391 | 21.16 | 156.3937 | 0 |  | 195.4922 | TRUE
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd | sqm | 7.0043 | 1014.97 | 7109.1209 | 6.7426 | 1014.97 | 6843.5054 | -265.6155 |  | 8886.4011 | TRUE
| VAT calculation |  |  |  | 784.6432 |  |  | 755.3269 | -29.3163 |  | 980.804 | TRUE
5 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | m3 | 2.655 | 4434.52 | 11773.6506 | 3.0553 | 4434.52 | 13549.0107 | 1775.3601 |  | 14717.0633 | TRUE
| VAT calculation |  |  |  | 1022.8589 |  |  | 1177.0968 | 154.2379 |  | 1278.5737 | TRUE
6 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 | m3 | 2.8527 | 10634.5 | 30336.9711 | 2.6056 | 10634.5 | 27708.803 | -2628.1681 |  | 37921.2138 | TRUE
| VAT calculation |  |  |  | 2992.578 |  |  | 2733.3234 | -259.2546 |  | 3740.7225 | TRUE
7 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications. | m3 | 34.515 | 9709.43 | 335120.9765 | 34.5553 | 9709.43 | 335512.315 | 391.3386 |  | 418901.2206 | TRUE
| VAT calculation |  |  |  | 24312.1796 |  |  | 24340.5702 | 28.3906 |  | 30390.2245 | TRUE
8 | k'/fgf] ;km]{;df XjfO{6jfz ug]{ sfd | sqm | 164.1911 | 20.82 | 3418.4589 | 58.1276 | 20.82 | 1210.2169 | -2208.2419 |  | 4273.0736 | TRUE
| VAT calculation |  |  |  | 97.8448 |  |  | 34.6394 | -63.2054 |  | 122.306 | TRUE
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | m3 | 7.1361 | 14362.76 | 102494.0719 | 7.2089 | 14362.76 | 103539.1152 | 1045.0432 |  | 128117.5899 | TRUE
| VAT calculation |  |  |  | 9566.1272 |  |  | 9663.6647 | 97.5375 |  | 11957.659 | TRUE
10 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | MT | 0.07071 | 131940 | 9329.4971 | 0.0786 | 131940 | 10370.4387 | 1040.9416 |  | 11661.8714 | TRUE
| VAT calculation |  |  |  | 976.2243 |  |  | 1085.1469 | 108.9225 |  | 1220.2804 | TRUE
11 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/ | sqm | 44.9398 | 405.86 | 18239.2742 | 54.48 | 405.86 | 22111.2528 | 3871.9786 |  | 22799.0927 | TRUE
| VAT calculation |  |  |  | 652.3491 |  |  | 790.8349 | 138.4859 |  | 815.4364 | TRUE
12 | Information board (सुचना पाटि) | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0 |  | 625 | TRUE
| Total |  |  |  | 563634.9281 |  |  | 564688.3131 | 1053.3851
[11 empty] | Description | Total amount w/o VAT | VAT 13%
[11 empty] | Skilled | 85610.0021
[11 empty] | unskilled | 123290.8385
[11 empty] | Excavator | 1113.3296 | 144.7328
[11 empty] | Brick | 65428.6578 | 8505.7255
[11 empty] | sand | 60288.2078 | 7837.467
[11 empty] | stone | 111398.9727 | 14481.8665
[11 empty] | aggregate | 7569.9475 | 984.0932
[11 empty] | cement | 55341.5709 | 7194.4042
[11 empty] | water | 2451.9734 | 318.7565
[11 empty] | formwork | 1065.7252 | 138.5443
[11 empty] | चुना | 203.4466 | 26.4481
[11 empty] | गम | 63.0103 | 8.1913
[11 empty] | rod | 8252.9639 | 1072.8853
[11 empty] | wire binding | 94.3196 | 12.2615
[12 empty] | 522172.966 | 40725.3763 | -1789.9709
[12 empty] | 523962.9368 | 40725.3763 | 0

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Valuated Sheet
Project:- गणपति ढिकुरेपाटी संरक्षण | [6 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [6 empty] | Date:2081/12/06
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य)
| -For stone masonary | 0.5 | 12.99 | 1.6 | 2 | 20.784
| Sub-total |  |  |  |  | 20.784 | m3 | 64.63 | 1343.2699
| VAT calculation | [7 empty] | 144.7328
2 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -for footing of wall at truss structure | 1 | 20.95 | 0.35 | 0.23 | 1.6865
| Sub-total |  |  |  |  | 1.6865 | m3 | 663.31 | 1118.6557
3 | 3fF; sf6\g] To;sf] h/f lemSg], l9:sf] k'm6fpg] / n]en u/L :yn ;kmf ug]{ ;a} jf]sgL ;d]t
| -Surrounding environment | 1 | 7.772 | 0.8 |  | 6.2176
|  | 1 | 3.9113 | 0.3 |  | 1.1734
| Sub-total |  |  |  |  | 7.391 | sqm | 21.16 | 156.3937
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing of wall at truss structure | 1 | 22.11 | 0.23 |  | 5.0853
| -for steps | 1 | 2.2097 | 0.75 |  | 1.6573
| Sub-total |  |  |  |  | 6.7426 | sqm | 1014.97 | 6843.5054
| VAT calculation | [7 empty] | 755.3269
5 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -For stone masonary | 1 | 4.53 | 1.6 | 0.15 | 1.0872
|  | 1 | 4.31 | 1.6 | 0.15 | 1.0344
|  | 1 | 4.15 | 1.5 | 0.15 | 0.93375
| Sub-total |  |  |  |  | 3.0553 | m3 | 4434.52 | 13549.0107
| VAT calculation | [7 empty] | 1177.0968
6 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For stone masonary | 1 | 4.53 | 1.6 | 0.05 | 0.3624
|  | 1 | 4.53 | 0.53 | 0.05 | 0.12005
| -For stone masonary | 1 | 4.31 | 1.6 | 0.05 | 0.3448
|  | 1 | 4.31 | 0.53 | 0.05 | 0.11422
| -For stone masonary | 1 | 4.15 | 1.5 | 0.05 | 0.31125
|  | 1 | 4.15 | 0.6 | 0.05 | 0.1245
| -For sill/lintel/DPC band | 1 | 20.95 | 0.23 | 0.05 | 0.24093
|  | 1 | 20.95 | 0.23 | 0.075 | 0.36139
|  | 1 | 20.95 | 0.23 | 0.1 | 0.48185
| -for steps | 1 | 2.2097 | 0.75 | 0.050798 | 0.084185
|  | 0.5 | 0.5 | 0.6 | 0.4 | 0.06
| Sub-total |  |  |  |  | 2.6056 | m3 | 10634.5 | 27708.803
| VAT calculation | [7 empty] | 2733.3234
7 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -For stone masonary | 1 | 4.53 | 1.04 | 2.55 | 12.0136
|  | 1 | 4.31 | 1.04 | 2.55 | 11.4301
|  | 1 | 4.15 | 1.05 | 2.55 | 11.1116
| Sub-total |  |  |  |  | 34.5553 | m3 | 9709.43 | 335512.315
| VAT calculation | [7 empty] | 24340.5702
8 | k'/fgf] ;km]{;df XjfO{6jfz ug]{ sfd
| -wall | 1 | 24.2301 |  | 2.5907 | 62.7723
| -deduction for door | -1 | 0.91436 |  | 2.1335 | -1.9508
|  | -1 | 0.76196 |  | 1.8287 | -1.3934
| -deduction for window | -1 | 1.0667 |  | 1.2191 | -1.3005
| Sub-total |  |  |  |  | 58.1276 | sqm | 20.82 | 1210.2169
| VAT calculation | [7 empty] | 34.6394
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -wall | 1 | 20.95 | 0.23 | 1.24 | 5.9749
|  | 1 | 3.04 | 0.23 | 1.2 | 0.83904
| -entrance | 1 | 1.16 | 0.23 | 0.14 | 0.037352
| -steps | 3.5 | 0.73758 | 0.3 | 0.19049 | 0.14753
| -partition | 1 | 3 | 0.1 | 0.7 | 0.21
| Sub-total |  |  |  |  | 7.2089 | m3 | 14362.76 | 103539.1152
| VAT calculation | [7 empty] | 9663.6647
10 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For bands | 4 | 20.95 | 0.61728 | 51.7284 | 0.051728
| -For stirrups | 206 | 0.33018 | 0.39506 | 26.8713 | 0.026871
| Sub-total |  |  |  |  | 0.0786 | MT | 131940 | 10370.4387
| VAT calculation | [7 empty] | 1085.1469
11 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 1 | 21.87 |  | 1.2 | 26.244
|  | 1 | 20.03 |  | 1.2 | 24.036
| -partition | 2 | 3 |  | 0.7 | 4.2
| Sub-total |  |  |  |  | 54.48 | sqm | 405.86 | 22111.2528
| VAT calculation | [7 empty] | 790.8349
12 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 564688.3131
| Total Valuated | 564688.3131 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 84.1172
| User Contribution | 89688.3131 |  | 15.8828
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on D67: DELL: column part not included

## Measure
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Quantity Measurement Sheet
Project:- गणपति ढिकुरेपाटी संरक्षण | [9 empty] | F.Y.: 2081/2082
Location:- Shankharapur Municipality 9 | [9 empty] | Date:2081/12/06
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य)
| -For stone masonary | 0.5 | 12.99 | 1.6 | 2 | 20.784
| Sub-total |  |  |  |  | 20.784 | m3 | 64.63 | 1343.2699
| VAT calculation | [7 empty] | 144.7328
2 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| -for footing of wall at truss structure | 1 | 20.95 | 0.35 | 0.23 | 1.6865
| Sub-total |  |  |  |  | 1.6865 | m3 | 663.31 | 1118.6557
3 | 3fF; sf6\g] To;sf] h/f lemSg], l9:sf] k'm6fpg] / n]en u/L :yn ;kmf ug]{ ;a} jf]sgL ;d]t
| -Surrounding environment | 1 | 7.772 | 0.8 |  | 6.2176
|  | 1 | 3.9113 | 0.3 |  | 1.1734
| Sub-total |  |  |  |  | 7.391 | sqm | 21.16 | 156.3937
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| -for footing of wall at truss structure | 1 | 22.11 | 0.23 |  | 5.0853
| -for steps | 1 | 2.2097 | 0.75 |  | 1.6573
| Sub-total |  |  |  |  | 6.7426 | sqm | 1014.97 | 6843.5054
| VAT calculation | [7 empty] | 755.3269
5 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -For stone masonary | 1 | 4.53 | 1.6 | 0.15 | 1.0872
|  | 1 | 4.31 | 1.6 | 0.15 | 1.0344
|  | 1 | 4.15 | 1.5 | 0.15 | 0.93375
| Sub-total |  |  |  |  | 3.0553 | m3 | 4434.52 | 13549.0107
| VAT calculation | [7 empty] | 1177.0968
6 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For stone masonary | 1 | 4.53 | 1.6 | 0.05 | 0.3624
|  | 1 | 4.53 | 0.53 | 0.05 | 0.12005
| -For stone masonary | 1 | 4.31 | 1.6 | 0.05 | 0.3448
|  | 1 | 4.31 | 0.53 | 0.05 | 0.11422
| -For stone masonary | 1 | 4.15 | 1.5 | 0.05 | 0.31125
|  | 1 | 4.15 | 0.6 | 0.05 | 0.1245
| -For sill/lintel/DPC band | 1 | 20.95 | 0.23 | 0.05 | 0.24093
|  | 1 | 20.95 | 0.23 | 0.075 | 0.36139
|  | 1 | 20.95 | 0.23 | 0.1 | 0.48185
| -for steps | 1 | 2.2097 | 0.75 | 0.050798 | 0.084185
|  | 0.5 | 0.5 | 0.6 | 0.4 | 0.06
| Sub-total |  |  |  |  | 2.6056 | m3 | 10634.5 | 27708.803
| VAT calculation | [7 empty] | 2733.3234
7 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -For stone masonary | 1 | 4.53 | 1.04 | 2.55 | 12.0136
|  | 1 | 4.31 | 1.04 | 2.55 | 11.4301
|  | 1 | 4.15 | 1.05 | 2.55 | 11.1116
| Sub-total |  |  |  |  | 34.5553 | m3 | 9709.43 | 335512.315
| VAT calculation | [7 empty] | 24340.5702
8 | k'/fgf] ;km]{;df XjfO{6jfz ug]{ sfd
| -wall | 1 | 24.2301 |  | 2.5907 | 62.7723
| -deduction for door | -1 | 0.91436 |  | 2.1335 | -1.9508
|  | -1 | 0.76196 |  | 1.8287 | -1.3934
| -deduction for window | -1 | 1.0667 |  | 1.2191 | -1.3005
| Sub-total |  |  |  |  | 58.1276 | sqm | 20.82 | 1210.2169
| VAT calculation | [7 empty] | 34.6394
9 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -wall | 1 | 20.95 | 0.23 | 1.24 | 5.9749
|  | 1 | 3.04 | 0.23 | 1.2 | 0.83904
| -entrance | 1 | 1.16 | 0.23 | 0.14 | 0.037352
| -steps | 3.5 | 0.73758 | 0.3 | 0.19049 | 0.14753
| -partition | 1 | 3 | 0.1 | 0.7 | 0.21
| Sub-total |  |  |  |  | 7.2089 | m3 | 14362.76 | 103539.1152
| VAT calculation | [7 empty] | 9663.6647
10 | cf/=;L=;L= nflu kmnfd] 808L sf6\g], df]8\g] #) dL6/ ;Dd | No. | Length (m) | Unit wt. (kg/m) | Total wt. (kg) | Total wt. (MT)
| -For bands | 4 | 20.95 | 0.61728 | 51.7284 | 0.051728
| -For stirrups | 206 | 0.33018 | 0.39506 | 26.8713 | 0.026871
| Sub-total |  |  |  |  | 0.0786 | MT | 131940 | 10370.4387
| VAT calculation | [7 empty] | 1085.1469
11 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 1 | 21.87 |  | 1.2 | 26.244
|  | 1 | 20.03 |  | 1.2 | 24.036
| -partition | 2 | 3 |  | 0.7 | 4.2
| Sub-total |  |  |  |  | 54.48 | sqm | 405.86 | 22111.2528
| VAT calculation | [7 empty] | 790.8349
12 | Information board (सुचना पाटि) | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 564688.3131
| Total Valuated | 564688.3131 |  | 100
| Budget allocated | 500000
| Municipal payment | 475000 |  | 84.1172
| User Contribution | 89688.3131 |  | 15.8828
| Contingencies | 15000 |  | 3
| Maintanince | 10000 |  | 2
Note on D67: DELL: column part not included