## as per mistry
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- खुलालटार कार्कीटोल वाटिका निर्माण | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date: 2081/09/29
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 1.8mm thickness for vertical post | 6 | 4.5718 | 3.97 | 108.8997 | 108.8997
| -MS square pipe of 2"*2" of 1.8mm thickness for horizontal member | 5 | 6.7053 | 2.72 | 91.1917 | 91.1917
| -MS square pipe of 2"*2" of 1.8mm thickness for inclined member | 6 | 3.6574 | 2.72 | 59.6891 | 59.6891
| -MS square pipe of 2"*2" of 1.6mm thickness for king post member | 3 | 0.99055 | 2.43 | 7.2211 | 7.2211
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for diagnol member | 6 | 0.99055 | 3.87 | 23.0006 | 23.0006
|  | 6 | 0.83816 | 3.87 | 19.4621 | 19.4621
|  | 6 | 0.73758 | 3.87 | 17.1266 | 17.1266
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for vertical member | 6 | 0.68577 | 3.87 | 15.9235 | 15.9235
|  | 6 | 0.45718 | 3.87 | 10.6157 | 10.6157
|  | 6 | 0.20329 | 3.87 | 4.7204 | 4.7204
| -MS square pipe of 2"*2" of 1.8mm thickness for purlins | 6 | 6.7053 | 2.72 | 109.4301 | 109.4301
| sub-total |  |  |  |  | 467.2806 | Kg | 181.17 | 84657.2258
| -VAT 13% for materials | [7 empty] | 6002.2267
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
|  | 2 | 6.7053 | 3.6574 |  | 49.048
| sub-total |  |  |  |  | 49.048 | sqm | 1070.9 | 52525.5224
| -VAT 13% for materials | [7 empty] | 5475.681
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| ;-for footing | 6 | 0.45 | 0.45 | 0.88997 | 1.0813
| sub-total |  |  |  |  | 1.0813 | cum | 663.31 | 717.2482
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| ;-for footing | 6 | 0.45 | 0.45 |  | 1.215
| -for flooring | 2 | 3.505 | 2.7178 |  | 19.0517
| sub-total |  |  |  |  | 20.2667 | sqm | 1014.97 | 20570.1107
| -VAT 13% for materials | [7 empty] | 2270.3507
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| ;-for footing | 6 | 0.45 | 0.45 | 0.075 | 0.091125
| sub-total |  |  |  |  | 0.091125 | cum | 12983.1 | 1183.085
| -VAT 13% for materials | [7 empty] | 95.6953
6 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -for footing | 6 | 0.45 | 0.45 | 0.75 | 0.91125
|  | 6 | 0.3 | 0.3 | 0.45 | 0.243
| -for flooring | 2 | 3.505 | 2.7178 | 0.075 | 1.4289
| sub-total |  |  |  |  | 2.5831 | cum | 13568.9 | 35050.2169
| -VAT 13% for materials | [7 empty] | 3198.2906
7 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for footing | 4 | 2.5663 | 0.23 | 0.3 | 0.7083
|  | 3 | 3.4288 | 0.23 | 0.3 | 0.70977
| -wall | 4 | 2.7178 | 0.23 | 0.9 | 2.2503
|  | 3 | 3.505 | 0.23 | 0.9 | 2.1766
| sub-total |  |  |  |  | 5.845 | cum | 14362.76 | 83950.3366
| -VAT 13% for materials | [7 empty] | 7835.376
8 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 4 | 6.0957 |  | 0.9 | 21.9445
|  | 4 | 3.505 |  | 0.9 | 12.6181
| sub-total |  |  |  |  | 34.5626 | sqm | 405.86 | 14027.5904
| -VAT 13% for materials | [7 empty] | 501.7133
9 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य) | [9 empty] | 13m | ht=3'9"
| -For wall | 0.5 | 6 | 1.25 | 2 | 7.5
| Sub-total |  |  |  |  | 7.5 | m3 | 64.63 | 484.725
| VAT calculation | [7 empty] | 52.2275
10 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Road | 1 | 6 | 1.25 | 0.15 | 1.125
| Sub-total |  |  |  |  | 1.125 | m3 | 4434.52 | 4988.835
| VAT calculation | [7 empty] | 433.4148
11 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For wall | 1 | 6 | 1.25 | 0.075 | 0.5625
|  | 1 | 6 | 0.5 | 0.05 | 0.15
| Sub-total |  |  |  |  | 0.7125 | m3 | 10634.5 | 7577.0813
| VAT calculation | [7 empty] | 747.4381
12 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -For wall | 1 | 6 | 0.875 | 2.5 | 13.125
| Sub-total |  |  |  |  | 13.125 | m3 | 9709.43 | 127436.2688
| VAT calculation | [7 empty] | 9245.1791
13 | Information board | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 469525.839
| Total Estimated | 469525.839 |  | 100
| Budget allocated | 400000
| Municipal payment | 380000 |  | 80.9327
| User Contribution | 89525.839 |  | 19.0673
| Contingencies | 12000 |  | 3
| Maintanince | 8000 |  | 2

## WCR
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Work Completion Report
Total Estimated Amount: |  | 469525.839 |  |  |  |  | Total Valuated Amount : |  | 459614.2945
Work Started : | [7 empty] | Work Finished:
Project:- ૐ शान्ति भवन निर्माण तथा मर्मत | [7 empty] | F.Y:2081/2082
Location:- Shankharapur Municipality 9 | [7 empty] | Date:2081/12/14
S.No. | Description | Unit | Estimated |  |  | Valuated |  |  | Difference | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | Kg | 467.2806 | 181.17 | 84657.2258 | 439.007 | 181.17 | 79534.9013 | -5122.3245 |  | 105821.5323
| -VAT 13% for materials |  |  |  | 6002.2267 |  |  | 5639.0521 | -363.1746 |  | 7502.7833
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd | sqm | 49.048 | 1070.9 | 52525.5224 | 37.668 | 1070.9 | 40338.6612 | -12186.8612 |  | 65656.903
| -VAT 13% for materials |  |  |  | 5475.681 |  |  | 4205.225 | -1270.456 |  | 6844.6012
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd | cum | 1.0813 | 663.31 | 717.2482 | 1.0813 | 663.31 | 717.2482 | 0 |  | 896.5602
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd | sqm | 20.2667 | 1014.97 | 20570.1107 | 14.4634 | 1014.97 | 14679.8759 | -5890.2348 |  | 25712.6383
| -VAT 13% for materials |  |  |  | 2270.3507 |  |  | 1620.2376 | -650.1131 |  | 2837.9384
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_ | cum | 0.091125 | 12983.1 | 1183.085 | 0.091125 | 12983.1 | 1183.085 | 0 |  | 1478.8562
| -VAT 13% for materials |  |  |  | 95.6953 |  |  | 95.6953 | 0 |  | 119.6191
6 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_ | cum | 2.5831 | 13568.9 | 35050.2169 | 2.1479 | 13568.9 | 29144.3276 | -5905.8893 |  | 43812.7712
| -VAT 13% for materials |  |  |  | 3198.2906 |  |  | 2659.3853 | -538.9054 |  | 3997.8633
7 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df | cum | 5.845 | 14362.76 | 83950.3366 | 5.8525 | 14362.76 | 84057.5447 | 107.2081 |  | 104937.9207
| -VAT 13% for materials |  |  |  | 7835.376 |  |  | 7845.3822 | 10.0061 |  | 9794.2201
8 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/ | sqm | 34.5626 | 405.86 | 14027.5904 | 39.711 | 405.86 | 16117.1065 | 2089.5161 |  | 17534.488
| -VAT 13% for materials |  |  |  | 501.7133 |  |  | 576.4473 | 74.734 |  | 627.1416
9 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य) | m3 | 7.5 | 64.63 | 484.725 | 6.7616 | 64.63 | 437.0017 | -47.7233 |  | 605.9062
| VAT calculation |  |  |  | 52.2275 |  |  | 47.0855 | -5.142 |  | 65.2844
10 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications. | m3 | 1.125 | 4434.52 | 4988.835 | 1.4336 | 4434.52 | 6357.5487 | 1368.7137 |  | 6236.0438
| VAT calculation |  |  |  | 433.4148 |  |  | 552.3245 | 118.9097 |  | 541.7685
11 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 | m3 | 0.7125 | 10634.5 | 7577.0813 | 0.76288 | 10634.5 | 8112.8821 | 535.8009 |  | 9471.3516
| VAT calculation |  |  |  | 747.4381 |  |  | 800.2919 | 52.8539 |  | 934.2976
12 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications. | m3 | 13.125 | 9709.43 | 127436.2688 | 14.8258 | 9709.43 | 143949.7917 | 16513.523 |  | 159295.3359
| VAT calculation |  |  |  | 9245.1791 |  |  | 10443.1935 | 1198.0143 |  | 11556.4739
13 | Information board | no. | 1 | 500 | 500 | 1 | 500 | 500 | 0 |  | 625
| Total |  |  |  | 469525.839 |  |  | 459614.2945 | -9911.5445

## V
Government of Nepal
Shankharapur Municipality Office
Bagmati Province
Sankhu, Kathmandu
Detail Estimated Sheet
Project:- खुलालटार कार्कीटोल वाटिका निर्माण | [6 empty] | F.Y.: 2081/082
Location:- Shankharapur Municipality 9 | [6 empty] | Date: 2081/09/29
S.N. | Description of work | No. | Length | Breadth | Height | Quantity | Unit | Rate | Amount | Remarks
1 | sfnf] kmnfd] kfO{ksf] 6«; agfO{ h8fg ug]{ sfd | No. | Length (m) | Unit length (Kg/m) | Total Weight (kg)
| -MS square pipe of 3" * 3" of 1.8mm thickness for vertical post | 3 | 4.267 | 3.97 | 50.8199 | 50.8199
|  | 3 | 5.4861 | 3.97 | 65.3398 | 65.3398
| -MS square pipe of 2"*2" of 1.8mm thickness for horizontal member | 5 | 6.7053 | 2.72 | 91.1917 | 91.1917
| -MS square pipe of 2"*2" of 1.8mm thickness for inclined member | 6 | 2.58 | 2.72 | 42.1056 | 42.1056
| -MS square pipe of 2"*2" of 1.8mm thickness for king post member | 3 | 0.56 | 2.72 | 4.5696 | 4.5696
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for diagnol member | 6 | 0.95 | 1.83 | 10.431 | 10.431
|  | 6 | 0.86 | 1.83 | 9.4428 | 9.4428
| -MS square pipe of 1.5"*1.5" of 1.6mm thickness for vertical member | 6 | 0.38 | 1.83 | 4.1724 | 4.1724
|  | 6 | 0.19 | 1.83 | 2.0862 | 2.0862
| -MS square pipe of 2"*2" of 1.8mm thickness for purlins | 8 | 7.3 | 2.72 | 158.848 | 158.848
| sub-total |  |  |  |  | 439.007 | Kg | 181.17 | 79534.9013
| -VAT 13% for materials | [7 empty] | 5639.0521
2 | ).#^ lblv ).$ dL.dL.afSnf] sf]?u]6]8 /+lug ss{6 kftfsf] 5fgf 5fpg] sfd
|  | 2 | 7.3 | 2.58 |  | 37.668
| sub-total |  |  |  |  | 37.668 | sqm | 1070.9 | 40338.6612
| -VAT 13% for materials | [7 empty] | 4205.225
3 | g/d k¦sf/sf] Sn] / l;N6L df6f]df ;j} lsl;dsf] vGg] sfd
| ;-for footing | 6 | 0.45 | 0.45 | 0.88997 | 1.0813
| sub-total |  |  |  |  | 1.0813 | cum | 663.31 | 717.2482
4 | ;'Vvf O{6f RofK6f] 5fKg] sfd
| ;-for footing | 6 | 0.45 | 0.45 |  | 1.215
| -for flooring | 1 | 3.6297 | 3.65 |  | 13.2484 | [5 empty] | 13446.6873 | 13960.7559
| sub-total |  |  |  |  | 14.4634 | sqm | 1014.97 | 14679.8759
| -VAT 13% for materials | [7 empty] | 1620.2376
5 | hu leQf kvf{ndf l;d]G6 s+lqm6 ug]{ sfd -lk=;L=;L= !M@M$_
| ;-for footing | 6 | 0.45 | 0.45 | 0.075 | 0.091125
| sub-total |  |  |  |  | 0.091125 | cum | 12983.1 | 1183.085
| -VAT 13% for materials | [7 empty] | 95.6953
6 | d]lzgsf] k¦of]u u/L ;'k/ :6«Sr/df l;d]G6 s+lqm6 ug]{ sfd -!M!=%M#_
| -for footing | 6 | 0.45 | 0.45 | 0.75 | 0.91125
|  | 6 | 0.3 | 0.3 | 0.45 | 0.243
| -for flooring | 1 | 3.6297 | 3.65 | 0.075 | 0.99363
| sub-total |  |  |  |  | 2.1479 | cum | 13568.9 | 29144.3276
| -VAT 13% for materials | [7 empty] | 2659.3853
7 | e'O{+tNnfdf lrDgL e§fsf] O{+6fsf] uf/f] l;d]G6 d;nf -!M^_ df
| -for footing | 4 | 2.5663 | 0.23 | 0.3 | 0.7083
|  | 3 | 3.4288 | 0.23 | 0.3 | 0.70977
| -wall | 1 | 18.2 | 0.23 | 1 | 4.186
| -for steps | 1 | 1.8 | 0.3 | 0.23 | 0.1242
|  | 1 | 1.8 | 0.3 | 0.23 | 0.1242
| sub-total |  |  |  |  | 5.8525 | cum | 14362.76 | 84057.5447
| -VAT 13% for materials | [7 empty] | 7845.3822
8 | !@=% dL=dL= l;d]G6 afn'jf -!M$_ Knfi6/
| -wall | 1 | 17.585 |  | 1 | 17.585
|  | 1 | 19.24 |  | 1.15 | 22.126
| sub-total |  |  |  |  | 39.711 | sqm | 405.86 | 16117.1065
| -VAT 13% for materials | [7 empty] | 576.4473
9 | Earthwork Excavation in Cutting., Roadway Excavation in all types of Soil by Mechanical Means ., Road way Excavation in all types of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer. (खन्ने पुर्ने कार्य)
| -For wall | 0.5 | 6 | 1.1747 | 1.5 | 5.2861
|  | 0.5 | 5.4 | 0.5 | 1.0929 | 1.4755
| Sub-total |  |  |  |  | 6.7616 | m3 | 64.63 | 437.0017
| VAT calculation | [7 empty] | 47.0855
10 | Providing and laying of hand pack locally available Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.
| -Road | 1 | 6 | 1.1429 | 0.15 | 1.0286
|  | 1 | 5.4 | 0.5 | 0.15 | 0.405
| -for DPC base | 0 | 20 | 0.23 | 0.15 | 0
| Sub-total |  |  |  |  | 1.4336 | m3 | 4434.52 | 6357.5487
| VAT calculation | [7 empty] | 552.3245
11 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15
| -For wall | 1 | 6 | 1.1429 | 0.05 | 0.34288
|  | 1 | 6 | 0.5 | 0.05 | 0.15
|  | 1 | 5.4 | 0.5 | 0.05 | 0.135
|  | 1 | 5.4 | 0.5 | 0.05 | 0.135
| Sub-total |  |  |  |  | 0.76288 | m3 | 10634.5 | 8112.8821
| VAT calculation | [7 empty] | 800.2919
12 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:6 in Foundation complete as per Drawing and Technical Specifications.
| -For wall | 1 | 6 | 0.82147 | 2.3494 | 11.5797 |  |  |  |  | 7.4167 | 3.75 | 1.1429 | 0.82147
|  | 1 | 5.4 | 0.55 | 1.0929 | 3.246
| Sub-total |  |  |  |  | 14.8258 | m3 | 9709.43 | 143949.7917
| VAT calculation | [7 empty] | 10443.1935
13 | Information board | 1 |  |  |  | 1 | no. | 500 | 500
| Grand Total | [7 empty] | 459614.2945
| Total Estimated | 459614.2945 |  | 100
| Budget allocated | 400000
| Municipal payment | 380000 |  | 82.678
| User Contribution | 79614.2945 |  | 17.322
| Contingencies | 12000 |  | 3
| Maintanince | 8000 |  | 2
Note on D34: DELL: half quantity as they used stone quantity equal to nearly 14000 rs